## FULL_SUM
XYY PROJCT CITY ABC (INTERIOR FITOUT WORKS)
MATERIAL FINISHES SUBMISSION PROGRESS /STATUS- SUMMARY | [6 empty] | As of:- 26/8/2019
S. NO. | MATERIAL TYPE | TOTAL QUANTITY | SUBMITTED | SENT TO SITE (SITE TEAM TO BE FOLLOWED) | BALANCE TO SUBMIT | REMARKS | MATERIAL APPROVAL STATUS
[7 empty] | A | B | B/C | C | D | P | OD | Balance | FI & X | ISSUED TO SITE
1 | STONE FINISH | 32 | 31 | 0 | 1 |  | 20 | 11 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0
2 | WOOD/VENEER & LACQUER FINISH | 31 | 31 | 0 | 0 |  | 10 | 21 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 0
3 | GLASS & MIRROR | 25 | 25 | 0 | 0 |  | 11 | 12 | 0 | 2 | 0 | 0 | 0 | 0 | 2 | 0
4 | IRONMONGERY | 5 | 5 | 0 | 0 |  | 1 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0
5 | FURNITURE HARDWARE | 14 | 14 | 0 | 0 |  | 10 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 16 | 0
6 | METAL | 11 | 11 | 0 | 0 |  | 4 | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7 | FABRIC / LEATHER UPHOLSTRY | 14 | 14 | 0 | 0 |  | 4 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8 | GYPSUM CEILINGS & PAINT | 9 | 9 | 0 | 0 |  | 3 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 0
9 | WALLCOVERING | 12 | 12 | 0 | 0 |  | 4 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| TOTAL | 153 | 152 | 0 | 1 | 0 | 67 | 83 | 0 | 2 | 0 | 0 | 0 | 1 | 34 | 0

## MS_LOG
XYY PROJCT CITY ABC (INTERIOR FITOUT WORKS)
FINISHES MATERIAL SCHEDULE & SUBMITTAL TRACKING LOG | [9 empty] | As of:- | 2019-08-26 | STATUS LEGEND
[12 empty] | A - Approved |  | P - Issued for Approval | [6 empty] | X - No Longer in Use/Not in Scope
[12 empty] | B - Approved as Noted |  | OD - Overdue | [6 empty] | FI - For Information only
[12 empty] | C - Resubmit |  | IR- Internal Review Return for Correction | [6 empty] | B/C- Approved as Noted / Resubmit
[12 empty] | D - Rejected |  | SS - Superseded by New Revision
Sr. No. | GLI Ref. No. | ARK | Rev. No: | Type of Material | Type of Submittal | Specs. Ref: | Material Description As Per Specification/ Contract Doc. | Manufacturer / Supplier | Proposed / Submitted Material | Manufacturer / Supplier | Location of Use | Area of Application | Initiator/ Follow-up By | Issued To | Planned Submission Start Date | Planned Submission Finish Date | Tracking | [9 empty] | Private Apartment
|  | Material Ref. | [14 empty] | Date Submitted | Date Commented | Time taken to reply | STATUS | No. of Days OverDue | Latest Status | Remarks
STONE FINISH | [26 empty] | PA
1 | MS-0053-00 |  | 0 | MARBLE | SAMPLE | ST 008 | 20 mm Marroun Scurro Marble, polished, 100% natural. Cut to size |  | Marrone Scuro Marble - 20mm thick | Stone Factory |  | Vanity Counter - Guest Toilet | NAM | MKM |  |  | 2017-03-09 | 2017-03-13 | 4 | A | 0 | A | APPROVED | 1 2 3
2 | MS-0054-00 |  | 0 | MARBLE | SAMPLE | ST 009 | 20 mm Sina Beige, honed, 100% natural. Cut to size |  | Sina Beige - 20mm Thick (Honed) | Stone Factory |  | Cistern Ledge & Threshold (Bathroom Vanity Counter) | NAM | MKM |  |  | 2017-03-09 | 2017-03-13 | 4 | A | 0 | A | APPROVED | 1 2 4
3 | MS-0019-00 |  | 0 | PORCELAIN TILE | SAMPLE | ST 010 | Argenta Ceramica - Spain, 11 mm, 450x900 mm, honed, Full body porcelain |  | 11mm Thick 450x900mm Argenta Wafi Sina Full Body Porcelain Tile, Beige Colour Honed Finish With Pre-Incision (As per sample) | Argenta Spain |  | Bathroom Flooring & Wall Cladding All Units. | NAM | MKM |  |  | 2017-01-03 | 2017-01-08 | 5 | A | 0 | A | TO FOLLOW THE PREPARED METHOD OF TILING FOR WALL PATTERN. | 1 2 5
4 | MS-0030-00 |  | 0 | PORCELAIN TILE | SAMPLE | ST-011 ST010.1 Bill No-02, Page-32 | Argenta Ceramica - Spain, 11 mm, 600x600 mm, honed, Full body porcelain |  | Argenta Ceramica Tiles 11mm thick WAFI SINA BEIGE 600 x 600MM Honed (For Sample finish please refer to 300 x 600 sample under submittal # 0031-00) | Argenta Spain |  | 1 Bedroom Suite B Guest Toilet Flooring | NAM | MKM |  |  | 2017-01-29 | 2017-02-06 | 8 | A | 0 | A | Revised specification sheet attached for record. | 1 2 5
5 | MS-0031-00 |  | 0 | PORCELAIN TILE | SAMPLE | ST 011.1 ST010.2 WF7 | Argenta Ceramica - Spain, 11 mm, 300x600 mm, honed, Full body porcelain |  | Argenta Ceramica Tiles 11mm thick WAFI SINA BEIGE 300 X 600mm Honed | Argenta Spain |  | Bathroom Wall Cladding 2 Bedroom Ty-4 & 3 Bedroom Ty-5 | NAM | MKM |  |  | 2017-01-29 | 2017-02-06 | 8 | A | 0 | A | Revised specification sheet attached for record. | 1 2 5
6 | MS-0018-00 |  | 0 | PORCELAIN TILE | SAMPLE | ST 011 ST 011.1 | SW |  | 11mm Thick 600x600mm Full Body Porcelain Tile "Fotiles TD126008M" Beige Colour Honed Finish and 11mm Thick 120x600mm Skirting. (As per sample) | Fotiles China |  | Apartment Entrance, Living, Kitchen & Corridor | NAM | MKM |  |  | 2017-01-02 | 2017-01-08 | 6 | A | 0 | A |  | 1 2 6
7 | MS-0018-00 |  | 0 | PORCELAIN TILE | SAMPLE | ST 011.1 | Fotiled TD 126008M, 11 mm, 120x600 mm, beige & honed, full body porcelain |  | As Above | [12 empty] | FI | Refer to Submittal No: 0018 | 1 2 7
8 | MS-0035-00 |  | 0 | CERAMIC TILE | SAMPLE | ST 012 | RAK ceramics - Calixto flooring - Beige, 330x330 mm, 10 mm thick, Matt - non slip |  | 330x330mm Ceramic Tile A04RZSPC-WH0-MOU Model ref: 4/KJ-SPC-WH (As per sample selected vide RFI Ref: MKM-05Q-IDP-01-RFI-0009 Rev-02) | RAK Ceramics |  | Apartment -Flooring for Maid Room-Laundry-Storage | NAM | MKM |  |  | 2017-02-06 | 2017-02-12 | 6 | A | 0 | A | TILE APPROVED VIA RFI-0009 | 1 2 8
9 | MS-0020-00 |  | 0 | CERAMIC TILE | SAMPLE | ST 013 | RAK ceramics - Calixto white + beige, 250x330 mm, 12 mm thick, Glossy |  | 8.5mm Thick 250x330mm Ceramic Tile CALIXTO "A50RCALX-WH0.G0U" White Colour and CALIXTO "A50RCALX-BE0.G0U" Beige Colour Glossy Finish (As per sample) | RAK Ceramics |  | Apartment -Wall Cladding-Maid Toilet-Laundry-Storage | NAM | MKM |  |  | 2017-01-03 | 2017-01-08 | 5 | B | 0 | B | DARK TILE (REF: A50RCALX) IS FOR FLOOR, THE OTHER LIGHT TILE IS FOR WALLS. | 1 2 9
10 | MS-0055-00 |  | 0 | RECONSTITUTED STONE | SAMPLE | ST 016 SWA-118 | BFP stone - Nano glass, 20 mm thick, polished. Cut to size |  | Nano Crystal - 20mm Thick (Polished Finish) | Stone Factory |  | Counter Top - Kitchen Counter | NAM | MKM |  |  | 2017-03-09 | 2017-03-13 | 4 | A | 0 | SS | APPROVED | 1 2 10
11 | MS-0055-01 |  | 1 | RECONSTITUTED STONE | SAMPLE | SWA-118 | BFP stone - Nano glass, 20 mm thick, polished. Cut to size |  | Nano Crystal - 20mm Thick (Polished Finish) (Subject to Previous Approval) | Stone Factory |  | Counter Top - Kitchen Counter | HHS | MKM |  |  | 2018-06-28 | 2018-07-04 | 6 | A | 0 | A | Material is approved as confirmed earlier. | 1 2 10
12 | MS-0056-0 |  | 0 | GRANITE | SAMPLE | ST 017 SWA-119 | Black absoluto, 20 mm (+20 mm for edge profile), polished, 100% natural stone |  | Black Absolute Granite - 20mm Thick (Polished Finish) | Stone Factory |  | Counter Top - Kitchen High Counter | NAM | MKM |  |  | 2017-03-09 | 2017-03-13 | 4 | A | 0 | SS | APPROVED | 1 2 12
13 | MS-0056-1 |  | 1 | GRANITE | SAMPLE | SWA-119 | Black absoluto, 20 mm (+20 mm for edge profile), polished, 100% natural stone |  | Black Absolute Granite - 20mm Thick (Polished Finish) (Subject to Previous Approval) | Stone Factory |  | Counter Top - Kitchen High Counter | HHS | MKM |  |  | 2018-06-28 | 2018-07-04 | 6 | A | 0 | A | Material is approved as confirmed earlier. | 1 2 12
14 | MS-0086-0 |  | 0 | MARBLE | SAMPLE | ST-009 | Stone SINA BEIGE |  | SINA BEIGE - 30mm THICK | Stone Factory |  | Bathroom Threshold | NAM | MKM |  |  | 2017-06-11 | 2017-06-15 | 4 | B | 0 | B | A Marble for Counters, Ledge, Wall Rib Threshold must Receive Sealant to Proterct Sealant Specs to be Submitted for approval. | 1 2 17
15 | MS-0105-00 |  | 0 | MARBLE | SAMPLE | SWA-112 SWGS-112 | Stone: Statuario Marble |  | Stone: Statuario Marble (Natural White) - 20mm Thick - Polished (As per Sample) | Stone Factory |  | Joinery | NAM | MKM |  |  | 2018-01-14 | 2018-01-14 | 0 | B | 0 | SS | Sample piece is approved, site review prior to it production. Mrble installation to be in line with commented shop drawings. | 1 2 4
16 | MS-0105-1 |  | 1 | STONE | SAMPLE | SWA-112 & SWGS-112 |  |  | Stone Volakas Marble - 2 cm (Sample as Selected By Client) | Stone Factory |  | Master Room Bedside Table & TV Desk | HHS | MKM |  |  | 2018-07-02 | 2018-07-05 | 3 | B | 0 | B | Sample piece is approved in principal, however we need to review slabs prior to in Procurement. | 1 2 17 |  |  | PA
17 | MS-0057-0 |  | 0 | ADHESIVE | SAMPLE | N/A | Adhesive |  | MAPEI Keraflex Cementitious Adhesive to Fix Marble Thresholds | MAPEI / Stone Factory |  | To Fix Marble Thresholds (Wherever Applicable) | NAM | MKM |  |  | 2017-03-09 | 2017-03-13 | 4 | B | 0 | B | Follow manufacture recommendations for application. | 1 2 12
18 | MS-0058-0 |  | 0 | ADHESIVE | SAMPLE | N/A | Adhesive |  | MAPEI Kerapoxy - Epoxy Adhesive to Fix Marble and Granite Over Counter Top and Facia | MAPEI / Stone Factory |  | To Fix Marble & Granite (Wherever Applicable) | NAM | MKM |  |  | 2017-03-09 | 2017-03-13 | 4 | B | 0 | B | Follow manufacture recommendations for application. | 1 2 12
19 | MS-0059-0 |  | 0 | ADHESIVE | SAMPLE | N/A | Grout |  | MAPEI - Ultracolor Plus Grout - To Grout Marble Joints in Thresholds | MAPEI / Stone Factory |  | To Grout Marble Joint in Thresholds (Wherever Applicable) | NAM | MKM |  |  | 2017-03-09 | 2017-03-13 | 4 | B | 0 | B | Grout product approved (previously approved via MS-0034) obtain grout color approval prior to use submit sample mock up | 1 2 12
20 | MS-0184-0 | 0015 | 0 | ADHESIVE | SAMPLE | N/A |  |  | ADHESIVE: Sudal Wall Panel Adhesive | Sudal | Joinery & Furniture |  | HS | MKM |  |  | 2019-03-13 | 2019-03-17 | 4 | A | 0 | A | Approved | 1 2 12
21 | MS-0060-0 |  | 0 | SEALER | TECHNICAL SHEET | S-009 | 15 Gold - Acqua mix Inc. |  | AQUAMIX - Sealer Choice Gold - Sealer Coat for Marble and Granite | AQUAMIX / Stone Factory |  | Sealer Coat for Marble and Granite (Wherever Applicable) | NAM | MKM |  |  | 2017-03-09 | 2017-03-13 | 4 | B | 0 | B | Follow manufacture recommendations for application. | 1 2 14
22 | MS-0034-0 |  | 0 | GROUT | TECHNICAL SHEET | ST-010, ST-011, ST-011.1, ST-012 & ST-013 | Mapei-131-Vanilla |  | MAPEI GROUT (ULTRA COLOR PLUS) - Specific Colours to be Selected by the Employer from the Colour Chart Provided | MAPEI | Wall & Flooring (Wherever Applicable) | Wall & Flooring (Wherever Applicable) | NAM | MKM |  |  | 2017-01-31 | 2017-02-06 | 6 | B | 0 | B | Product Approved. Colour is "131 Vanilla" approved for guest toilets. Submit colour proposal for Maid's Toilet | 1 2 15
23 | MS-0033-0 |  | 0 | ADHESIVE | TECHNICAL SHEET | ST-010, ST-011, ST-011.1, ST-012 & ST-013 | Keraset grey - Mapei |  | MAPEI ADHESIVE (KERASET GREY) | MAPEI | Wall & Flooring (Wherever Applicable) | Wall & Flooring (Wherever Applicable) | NAM | MKM |  |  | 2017-01-31 | 2017-02-06 | 6 | B | 0 | B | Approved for Ceramic Tiles only as per data sheet Submit suitable material for stone tile, marble, tiles over waterproofing. | 1 2 17
24 | MS-0070-0 |  | 0 | GROUT | TECHNICAL SHEET |  | Grout |  | MAPEI - Ultracolor Plus Grout - Colour Jasmine 130 | MAPEI |  | Porcelain Tile (Foshan Tile) joints (Wherever applicable). | NAM | MKM |  |  | 2017-04-19 | 2017-04-20 | 1 | B | 0 | B | Inspection for Grout colour approved Note : Tiles not levelled, space between tiles not correct, Gap must be maintained consistant. | 1 2 17
25 | MS-0130-0 |  | 0 | STONE | SAMPLE | RTR | Rough Open Pore Finishing Light |  | Stone Light Traventine Stone (Rough Open Pore Finishing) - 2cm (Sample as Selected By Client) | Stone Factory |  | 16th Floor Private Apartment - Wall Cladding | HHS | MKM |  |  | 2018-04-12 | 2018-05-12 | 30 | A | 16 | A | Approved as discussed by Stone Factory with Client. | 1 2 17 |  |  | PA
26 | MS-0129-0 |  | 0 | STONE | SAMPLE | HTR | Honed Travertine Stone |  | Stone Honed Traventine Stone - 2cm (Sample as Selected By Client) | Stone Factory |  | 16th Floor Private Apartment | HHS | MKM |  |  | 2018-04-12 | 2018-05-12 | 30 | A | 16 | A | Approved as discussed by Stone Factory with Client. | 1 2 17 |  |  | PA
27 | MS-0146-0 |  | 0 | STONE | SAMPLE | HTR1 | Honed Travertine Stone |  | Stone Light Travertine - Sand Blasted Finish (Sample as Selected By Client) | Stone Factory |  | 16th Floor Private Apartment - Master Bathroom Flooring | HHS | MKM |  |  | 2018-05-01 | 2018-05-09 | 8 | A | 0 | A | Approved as discussed by Stone Factory with Client. | 1 2 17 |  |  | PA
28 | MS-0139-0 |  | 0 | STONE | SAMPLE | BRE | Breccia Capraia Marble Honed |  | Stone Breccia Capraia Marble - Honed Finish (Sample as Selected By Client) | Stone Factory |  | 16th Floor Private Apartment | HHS | MKM |  |  | 2018-04-25 | 2018-05-12 | 17 | A | 3 | A | Approved as discussed by Stone Factory with Client. | 1 2 17 |  |  | PA
29 | MS-0131-0 |  | 0 | STONE | SAMPLE | GR | Gris du Marais Marbl Matt Hound |  | Stone Gris Du Marais Marble Stone (Sample as Selected By Client) | Stone Factory |  | 16th Floor Private Apartment - Master Bedroom Wall Cladding/Flooring | HHS | MKM |  |  | 2018-04-15 | 2018-05-12 | 27 | A | 13 | A | Approved as discussed by Stone Factory with Client. | 1 2 17 |  |  | PA
30 | MS-0145-0 |  | 0 | STONE | SAMPLE | GR1 | Gris du Marais Marbl Matt Hound |  | Stone Gris Du Marais - Sand Blasted Finish (Sample as Selected By Client) | Stone Factory |  | 16th Floor Private Apartment - Master Bathroom Flooring | HHS | MKM |  |  | 2018-05-01 | 2018-05-09 | 8 | A | 0 | A | Approved as discussed by Stone Factory with Client. | 1 2 17 |  |  | PA
31 | MS-0132-0 |  | 0 | STONE | SAMPLE | CR | Cerma D'Orcia Limestone |  | Stone Crema D'Orcia Limestone (Sample as Selected By Client) | Stone Factory |  | 16th Floor Private Apartment | HHS | MKM |  |  | 2018-04-15 | 2018-05-12 | 27 | A | 13 | A | Approved as discussed by Stone Factory with Client. | 1 2 17 |  |  | PA
32 |  |  | 0 | STONE | SAMPLE | TT | I gioielli handmade Terracotta by Fornace Brioni |  |  |  |  | 16th Floor Private Apartment | HHS | MKM |  |  |  |  | 43703 |  | 43689 | 0 |  | 1 2 17 |  |  | PA
33 | MS-0140-0 |  | 0 | STONE | SAMPLE | SEN | Sensation Marble |  | Stone Sensation Marble - 2cm (Sample as Selected By Client) | Stone Factory |  | 16th Floor Private Apartment | HHS | MKM |  |  | 2018-04-25 | 2018-05-12 | 17 | A | 3 | A | Approved as discussed by Stone Factory with Client. | 1 2 17 |  |  | PA
34 | MS-0141-0 |  | 0 | STONE | SAMPLE | FWG | Fantastico White Granite & Match Grout |  | Stone Fantastico White Granite 2cm - Polished Finish (Sample as Selected By Client) | Stone Factory |  | 16th Floor Private Apartment | HHS | MKM |  |  | 2018-04-25 | 2018-05-12 | 17 | A | 3 | A | Approved as discussed by Stone Factory with Client. | 1 2 17 |  |  | PA
35 | MS-0155-0 |  | 0 | STONE | SAMPLE | ST-051 |  |  | Stone Capuccino Onyx (Sample as Selected By Client) | Stone Factory |  | Mini Bar Counter & Back Splash - Guestroom (L19 to L41) | HHS | MKM |  |  | 2018-06-09 | 2018-06-21 | 12 | B | 0 | B | Sample piece is approved. However we need to review its slab. Application as per ID drawings. | 1 2 17 |  |  | PA
36 | MS-0133-0 |  | 0 | Wall Tile | SAMPLE | HR | HEX ROMBO 12x21 Col Avorio by Etruria Design | Etruria | Wall Tile HEX ROMBO 12x21 Col Avorio (As per Sample) | Etruria |  | 16th Floor Private Apartment - Kitchen | HHS | MKM |  |  | 2018-04-22 | 2018-04-29 | 7 | A | 0 | A | Approved as Specified by I.D. | 1 2 17 |  |  | PA
WOOD/VENEER & LACQUER FINISH | [26 empty] | PA
37 |  |  | 0 | MDF | SAMPLE |  | 6mm THICK PLAIN MDF | [12 empty] | FI |  | FI | Refer to MS-0001 | 1 2 19
38 |  |  | 0 | MDF | SAMPLE |  | 12mm THICK PLAIN MDF | [12 empty] | FI |  | FI | Refer to MS-0001 | 1 2 20
39 | MS-0001-00 |  | 0 | MDF | SAMPLE | 09951 | 18mm THICK PLAIN MDF |  | Plain MDF - Adequate Thickness as per Contract Documents. (Sample Provided 12 & 18mm for Indicative Purpose) | Evergreen |  | Wherever Applicable | NAM | MKM |  |  | 2016-12-05 | 2016-12-07 | 2 | C | 0 | SS | -MDF to comply with BSEN 622-1-2003 & 622-5-2009 '- Self Certificate by manufacturer is not acceptable. -Submit test report from DCL approved laboratory | 1 2 21
40 | MS-0001-01 |  | 1 | MDF | SAMPLE | 09951 | 18mm THICK PLAIN MDF |  | Plain MDF - Adequate Thickness as per Contract Documents. (Sample Provided 12 & 18mm for Indicative Purpose) | Evergreen |  | Wherever Applicable | NAM | MKM |  |  | 2016-12-20 | 2016-12-28 | 8 | D | 0 | SS | PREVIOUS COMMENTS NOT ADDRESSED, TEST CERTIFICATE NOT AVAILABLE. | 1 2 21
41 | MS-0001-02 |  | 2 | MDF | SAMPLE | 09951 | 18mm THICK PLAIN MDF |  | Plain MDF - Adequate Thickness as per Contract Documents. (Sample Provided 12 & 18mm for Indicative Purpose) | Evergreen |  | Wherever Applicable | NAM | MKM |  |  | 2017-04-10 | 2017-04-11 | 1 | B | 0 | B | • PROCEED WITH PROCUREMENT NOTE: DEMONSTRATE TO MKM, ON SPECIFIC SOURCE OF PROCUREMENT WITH DELIVERY NOTE, I.E. FROM M/S EVERGREEN. | 1 2 21
42 |  |  | 0 | MDF | SAMPLE |  | 30mm THICK PLAIN MDF | [12 empty] | FI |  | FI | Refer to MS-0001 | 1 2 22
43 | MS-0002-00 |  | 0 | MDF | SAMPLE | 09951 | 18mm THICK MDF FR |  | High Moisture Resistant MDF - Adequate Thickness as per Contract Documents. (Sample provided is 18mm thick) | Evergreen |  | Wet Areas -Wherever Applicable | NAM | MKM |  |  | 2016-12-05 | 2016-12-07 | 2 | C | 0 | SS | -MDF to comply with BSEN 622-1-2003 & 622-5-2009 -Submit test report from DCL approved laboratory | 1 2 23
44 | MS-0002-01 |  | 1 | MDF | SAMPLE | 09951 | 18mm THICK MDF FR |  | High Moisture Resistant MDF - Adequate Thickness as per Contract Documents. (Sample provided is 18mm thick) | Evergreen |  | Wet Areas -Wherever Applicable | NAM | MKM |  |  | 2016-12-20 | 2016-12-28 | 8 | D | 0 | SS | PREVIOUS COMMENTS NOT ADDRESSED, TEST CERTIFICATE NOT AVAILABLE. | 1 2 23
45 | MS-0002-02 |  | 2 | MDF | SAMPLE | 09951 | 18mm THICK MDF FR |  | High Moisture Resistant MDF - Adequate Thickness as per Contract Documents. (Sample provided is 18mm thick) | Evergreen |  | Wet Areas -Wherever Applicable | NAM | MKM |  |  | 2017-04-10 | 2017-04-11 | 1 | B | 0 | B | • PROCEED WITH PROCUREMENT NOTE: DEMONSTRATE TO MKM, ON SPECIFIC SOURCE OF PROCUREMENT WITH DELIVERY NOTE, I.E. FROM M/S EVERGREEN. | 1 2 23
46 |  |  | 0 | MDF | SAMPLE |  | 18mm MDF MR | [12 empty] | FI |  | FI | Refer to MS-0002 | 1 2 24
47 |  |  | 0 | MDF | SAMPLE |  | 30mm MDF MR | [12 empty] | FI |  | FI | Refer to MS-0002 | 1 2 25
48 | MS-0027-0 |  | 0 | WOOD | SAMPLE | WD1 | SOLID MAHOGANY |  | Solid Wood - African Mohagony | Chabros |  | Frames of Fire Rated Wooden Doors | NAM | MKM |  |  | 2017-01-29 | 2017-02-06 | 8 | B | 0 | SS | Random moisture test to be conducted on site as a part of quality assurance by GLI QA/QC. To comply with local authority requirement for fire rated doors. | 1 2 26
49 | MS-0027-1 |  | 1 | WOOD | SAMPLE | WD1 | SOLID MAHOGANY |  | Solid Wood - African Mohagony | Chabros |  | Frames of All Wooden Doors | NAM | MKM |  |  | 2017-02-28 | 2017-03-02 | 2 | B | 0 | SS | LOCAL AUTHORITY COMPLIANCE TO BE ENSURED FOR FIRE RATED AND NON-FIRE RATED DOORS. | 1 2 26
50 | MS-0027-2 |  | 2 | WOOD | SAMPLE | WD1 | SOLID MAHOGANY |  | Solid Wood - African Mohagony | Chabros |  | Frames of All Wooden Doors | NAM | MKM |  |  | 2017-07-18 | 2017-07-19 | 1 | B | 0 | B | • PROVIDE RECENT CERTIFICATE OF ORIGIN, ATTACHED CERTIFICATE IS DATED SEPT 2015. • COMPLY WITH LOCAL AUTHORITY REQUIREMENTS FOR FIRE RATED DOOR. | 1 2 26
51 | MS-0029-0 |  | 0 | WOOD | SAMPLE | N/A | SOLID MERANTI |  | Solid Wood - Meranti | Global Lumber |  | Backing Support & Wooden Frame Structure for Joinery | NAM | MKM |  |  | 2017-01-29 | 2017-02-06 | 8 | B | 0 | B | Random moisture test to be conducted on site as a part of quality assurance by GLI QA/QC. Fire retardent paint as per attachment to be applied before delivery to site. | 1 2 27
52 | MS-0028-0 |  | 0 | WOOD | SAMPLE | WD2,WD2a & WD3 | SOLID BEACH WOOD |  | Solid Wood - European Beech | Chabros |  | Frames of Non Fire Rated Doors | NAM | MKM |  |  | 2017-01-29 | 2017-02-06 | 8 | D | 0 | X | Refer to attached comments sheet | 1 2 28 | Cancelled- superseded by MS-0027-01
53 | MS-0003-00 |  | 0 | PLYWOOD | SAMPLE | 09951-3 | PLYWOOD |  | Plywood - Adequate Thickness as per Contract Documents. (Sample Provided 12 & 18mm for Indicative Purpose) | Tridel Supreme |  | Central Panel Products- Singapore | NAM | MKM |  |  | 2016-12-05 | 2016-12-07 | 2 | C | 0 | SS | -Provided data sheet and test certificate are contredictry each other -Manufacturer & origin different in data sheet & test report. -M/s. GLI to provide verifyable proof that material is confirming to specs (BS 1088) | 1 2 29
54 | MS-0003-01 |  | 1 | PLYWOOD | SAMPLE | 09951-3 | PLYWOOD |  | Plywood - Adequate Thickness as per Contract Documents. (Sample Provided 12 & 18mm for Indicative Purpose) | Tridel Supreme |  | Central Panel Products- Singapore | NAM | MKM |  |  | 2016-12-20 | 2016-12-28 | 8 | D | 0 | SS | REV.00 COMMNETS NOT ADDRESSED, TEST CERTIFICATE NOT ATTACHED. | 1 2 29
55 | MS-0003-02 |  | 2 | PLYWOOD | SAMPLE | 09951-3 | PLYWOOD |  | Plywood - Adequate Thickness as per Contract Documents. (Sample Provided 12 & 18mm for Indicative Purpose) | Tridel Supreme |  | Central Panel Products- Singapore | NAM | MKM |  |  | 2017-04-10 | 2017-04-11 | 1 | B | 0 | B | • PROCEED WITH PROCUREMENT NOTE: DEMONSTRATE TO MKM, ON SPECIFIC SOURCE OF PROCUREMENT WITH DELIVERY NOTE, I.E. FROM M/S EVERGREEN. | 1 2 29
56 | MS-0004-01 |  | 1 | PLYWOOD | SAMPLE | 09951-3 | PLYWOOD |  | 18mm Thick Marine Plywood - Film Faced | Tridel Supreme |  | Wherever Applicable | NAM | MKM |  |  | 2017-07-18 | 2017-07-19 | 1 | B | 0 | B | OPTION 1: TEKCOM APPROVED, PROVIDED DATA SHEET AND TEST REPORT IS COMPLYING TO INTERNATIONAL STANDARDS. OPTION 2: KORINDO – NOT APPROVED, PROVIDE SIMILAR TEST REPORT. | 1 2 29
57 | MS-0004-02 |  | 2 | PLYWOOD | SAMPLE | 09951-3 | PLYWOOD |  | 18mm Thick Marine Plywood - Film Faced (Incorporating Previous Comments) | Korindo |  | Wherever Applicable | NAM | MKM |  |  | 2017-08-09 | 2017-08-22 | 13 | B | 0 | B | 1- FORMALDEHYDE CONTENT & FORMALDEHYDE RELEASE NOT TESTED. 2- REST OF THE TEST VALUES ARE WITHIN ACCEPTABLE LIMITS. | 1 2 29
58 | MS-0090-00 |  | 0 | PLYWOOD | SAMPLE |  | PLYWOOD |  | WBP Plywood - Adequate Thickness as per Contract Documents. (Sample Provided 18mm for Indicative Purpose) | Central Panel Products / Greenline |  | Joinery Items As per Contract | NAM | MKM |  |  | 2017-07-18 | 2017-07-19 | 1 | C | 0 | SS | TEST REPORTS NOT PROVIDED. PLEASE PROVIDE TEST REPORT SIMILAR TO ATTACHED SAMPLE REPORT. | 1 2 29
59 | MS-0090-01 |  | 1 | PLYWOOD | SAMPLE | 09951 | PLYWOOD |  | WBP Plywood - Adequate Thickness as per Contract Documents. (Incorporating Previous Comments) | Central Panel Products / Greenline |  | Joinery Items As per Contract | NAM | MKM |  |  | 2017-08-09 | 2017-08-22 | 13 | B | 0 | B | NOTE: 1- % SWELLING FOR WBP (6.46%) AS PER REPORT ATTACHED IS ALMOST THERE OF REGULAR PAY (2.5%) REPORT ATTACHED WITH MS-0003-02. 2- ASSUME THAT WON’T BE AFFECTING THE INTERNAL USE | 1 2 29
60 | MS-0009-00 |  | 0 | WOOD | SAMPLE | WD-01 | FIRE RATED DOOR CORE (60MIN FR) |  | 60min Fire Rated Door Core 54mm - Halspan 60 Optima (FD60) | Halspan |  | 60min Fire Rated Doors from L8 to L41 | NAM | MKM |  |  | 2016-12-07 | 2016-12-07 | 0 | C | 0 | SS | Refer to email dated 07/12/16 Resubmit with sample boards, filled in check list & dividers | 1 2 30
61 | MS-0009-01 |  | 1 | WOOD | SAMPLE | WD-01 | FIRE RATED DOOR CORE (60MIN FR) |  | 60min Fire Rated Door Core 54mm - Halspan 60 Optima (FD60) | Halspan |  | 60min Fire Rated Doors from L8 to L41 | NAM | MKM |  |  | 2016-12-20 | 2016-12-28 | 8 | B | 0 | B | SUBMIT MATERIAL INSPECTIONS, WILL CONDUCT RANDOM FACTORY VISITS. | 1 2 30
62 | MS-0010-00 |  | 0 | WOOD | SAMPLE | WD-2, WD-2a, WD-3, WD-3a,WD-13 | NFR DOOR CORE 44mm |  | Non Fire Rated 44mm thick Solid Door Core - Linex France | LINEX |  | Non Fire Rated Doors from L8 to L41 | NAM | MKM |  |  | 2016-12-07 | 2016-12-07 | 0 | C | 0 | SS | Refer to email dated 07/12/16 Resubmit with sample boards, filled in check list & dividers | 1 2 31
63 | MS-0010-01 |  | 1 | WOOD | SAMPLE | WD-2, WD-2a, WD-3, WD-3a,WD-13 | NFR DOOR CORE 44mm |  | Non Fire Rated Core: Linex 44mm thick Solid Door Core | LINEX |  | Non Fire Rated Doors from L8 to L41 | NAM | MKM |  |  | 2016-12-20 | 2016-12-28 | 8 | B | 0 | B | SUBMIT MATERIAL INSPECTIONS, WILL CONDUCT RANDOM FACTORY VISITS. | 1 2 31
64 | MS-0039-00 |  | 0 | WOOD | SAMPLE | WD-11 | FIRE RATED DOOR CORE (90MIN FR) |  | 90min FIRE RATED DOOR: 64mm THICK HALSPAN FD90 DOOR CORE |  |  | Lift Lobby Door (As per Schedule) | NAM | MKM |  |  | 2017-02-20 | 2017-02-21 | 1 | C | 0 | SS | COMPLIANCE WITH LOCAL AUTHORITY REGULATIONS TO BE ASSURED HALSPAN CORE AUTHORITY CERTIFICATE TO BE SUBMITTED INCORPORATE TO TESTED DOOR DETAILS INTO DOOR DRAWING (MKM-05Q-10P-01-DWG-0509) | 1 2 32
65 | MS-0039-01 |  | 1 | WOOD | SAMPLE |  | FIRE RATED DOOR CORE (90MIN FR) |  | 90min FIRE RATED DOOR: 64mm THICK HALSPAN FD90 DOOR CORE |  |  | Lift Lobby Door (As per Schedule) | NAM | MKM |  |  | 2017-03-15 | 2017-03-19 | 4 | B | 0 | B | COMPLIANCE WITH LOCAL AUTHORITY REGULATIONS TO BE ENSURED | 1 2 32
66 | MS-0026-0 |  | 0 | VENEER | SAMPLE | TM-101 | Reconstituted Ebony Veneer - FF - 040-5902/3, 0.5-0.6mm, 25% GLOSSY |  | Ebony Veneer -Reconsitituted EB M2/3 FY Extra | Busnelli Int'l |  |  | NAM | MKM |  |  | 2017-01-25 | 2017-02-19 | 25 | B | 11 | B | Veneer sample + % of lacquer (finish) is OK. No data available to verify the durability and consistency of lacquer product. MKM suggest "Sayerlak" products as per attached datasheet or equivalent | 1 2 33
67 | MS-0045-0 |  | 0 | VENEER | SAMPLE | TM 105 SWA-102 SWA-103 | Reconstituted Walnut Veneer, 0.5-0.6mm, 25% GLOSSY |  | Walnut Reconstituted Veneer, 2 crown up & down pattern with colour lab sample N-M379/1F | Busnelli |  |  | NAM | MKM |  |  | 2017-02-23 | 2017-02-23 | 0 | B | 0 | SS | VENEER SAMPLE AS WOOD/COLOR APPROVED. GLOSS LEVEL TO BE CHANGED TO 15%. | 1 2 34
68 | MS-0045-1 |  | 0 | VENEER | SAMPLE | SWA-102 | Reconstituted Walnut Veneer, 0.5-0.6mm, 25% GLOSSY |  | Walnut Reconstituted Veneer, 2 crown up & down pattern with colour lab sample N-M379/1F (Subject to previous approval) | Busnelli |  |  | HHS | MKM |  |  | 2018-06-28 | 2018-07-04 | 6 | A | 0 | A | Material is approved as confirmed earlier. | 1 2 34
69 | MS-0066-0 |  | 0 | WOOD | SAMPLE |  | FRIT WOOD |  | Fret Cut Decorative Timber Screen | Greenline |  |  | NAM | MKM |  |  | 2017-03-19 | 2017-03-30 | 11 | C | 0 | SS | 1- COLOR NOT BRONZE, PAINTED TO MATCH THE VENEER. 2- JUST FOR CONFIRMATION PROPOSE ANOTHER ACRYLIC CODE AP_000-CLEAR 1SMF | 1 2 36
70 | MS-0066-1 |  | 1 | WOOD | SAMPLE | N/A | FRIT WOOD |  | Mashrabiya: 'Fret Cut Decorative Timber Screen 'Timber Paint Color S 8500 N 3mm Acrylic ref AP-000 Clear | Greenline |  |  | NAM | MKM |  |  | 2017-04-10 | 2017-04-24 | 14 | B | 0 | SS | Acrylic Ref .AP-000 SMF Approved paint on fret cut screed is yet to be approved. Note : Polished side of acrylic to face the wall and the frosted side is facing bedroom. | 1 2 36 | As per Hassan
71 | MS-0036-0 |  |  | FORMICA | SAMPLE |  | ICE WHITE 0953 |  | 18mm Both Side Melamine MDF Option1: SF-MF101 - Designer White Option2: SF-MF102 - Frosty White | Emilam |  | Apartment - Pantry Unit & High Counters | NAM | MKM |  |  | 2017-02-06 | 2017-02-14 | 8 | D | 0 | SS | Melamine MDF not acceptable. Submit 'Formica' or equalent as specified
72 | MS-0036-1 |  |  | FORMICA | SAMPLE |  | ICE WHITE 0953 |  | White lily suede finish Ref# LAM/21081-WL | Marino Laminate |  | Apartment - Pantry Unit & High Counters | NAM | MKM |  |  | 2017-03-08 | 2017-03-14 | 6 | D | 0 | SS | Proposed alternative is not matching with specified item – Formica as discussed during progress meeting, submit Formica refer tender addendum drawing ‘DET-0334’. Finish to be as per RFI-0002
73 | MS-0036-2 |  |  | FORMICA | SAMPLE | SWA-116 | ICE WHITE 0953 |  | LAMINATE ICE WHITE 0953 | FORMICA |  | Apartment - Pantry Unit & High Counters | NAM | MKM |  |  | 2017-03-19 | 2017-03-22 | 3 | A | 0 | SS | APPROVED |  | As per Hassan
74 | MS-0036-3 |  |  | FORMICA | SAMPLE | SWA-116 | ICE WHITE 0953 |  | LAMINATE ICE WHITE 0953 (Subject to Previous Approval) | FORMICA |  | Apartment - Pantry Unit & High Counters | HHS | MKM |  |  | 2018-06-28 | 2018-07-04 | 6 | A | 0 | A | Material is approved as confirmed earlier. |  | As per Hassan
75 | MS-0037-0 |  |  | FORMICA | SAMPLE |  | BATTALON 0806 |  | 18mm Both Side Melamine MDF - Slate Grey - SF-MF132 | Emilam |  | Apartments - Pantry Unit & High Counter | NAM | MKM |  |  | 2017-02-06 | 2017-02-14 | 8 | D | 0 | SS | Melamine MDF not acceptable. Submit 'Formica' or equalent as specified
76 | MS-0037-1 |  |  | FORMICA | SAMPLE |  | BATTALON 0806 |  | Grey Colour Laminate: Slate Suede Finish Ref: LAM/22099-SLT (As per Sample) | Marino Laminate |  | Apartments - Pantry Unit & High Counter | NAM | MKM |  |  | 2017-03-09 | 2017-03-14 | 5 | D | 0 | SS | Proposed alternative is not matching with specified item – Formica as discussed during progress meeting, submit Formica refer tender addendum drawing ‘DET-0334’. Finish to be as per RFI-0002
77 | MS-0037-2 |  |  | FORMICA | SAMPLE | SWA-117 | BATTALON 0806 |  | BATTALON 0806 | Formica |  | Apartments - Pantry Unit & High Counter | NAM | MKM |  |  | 2017-03-19 | 2017-03-22 | 3 | A | 0 | SS | APPROVED |  | As per Hassan
78 | MS-0037-3 |  |  | FORMICA | SAMPLE | SWA-117 | BATTALON 0806 |  | BATTALON 0806 (Subject to Previous Approval) | Formica |  | Apartments - Pantry Unit & High Counter | HHS | MKM |  |  | 2018-06-28 | 2018-07-04 | 6 | A | 0 | A | Material is approved as confirmed earlier. |  | As per Hassan
79 | MS-0038-0 |  |  | FORMICA | SAMPLE | N/A |  |  | 2mm PVC Lipping - SF-MF101, 102, 132 | Emilam |  | Apartments - Pantry Unit & High Counter | NAM | MKM |  |  | 2017-02-06 | 2017-02-19 | 13 | D | 0 | SS | LIPPING TO BE COMPATIBLE WITH “FORMICA” OR EQUIVALENT TO BE SUBMITTED. LIPPING THICKNESS TO BE AS PER MOCKUP |  | As per Hassan
80 |  |  |  | FORMICA | SAMPLE |  | BATTALON 0806 | [14 empty] | FI | REFER TO MS-0036-0
81 |  |  |  | FORMICA | SAMPLE |  | ICE WHITE 0953 | [14 empty] | FI | REFER TO MS-0037-0
82 | MS-0072-0 |  |  | FORMICA | SAMPLE | N/A | Walnut matching to TM-105 |  | Option 1: Formica Colors Wood Laminate American Walnut (F5150) Option 2: Century Laminate 421 Classic Wain SU 0.8mm | Formica & Centuryply |  |  | NAM | MKM |  |  | 2017-04-20 | 2017-04-26 |  | B |  | SS | Laminate new proposed supplier matches the walnut veneer. Provide single side finish sample for review. |  | As per Hassan
83 |  |  | 0 | LACQUER FINISH | TECHNICAL SHEET |  | LACQUER | [14 empty] | FI | (INCLUDED IN VENEER SUBMITTAL MS-0026) | 1 2 37
84 | MS-0064-0 |  | 0 | WOOD | SAMPLE |  |  |  | Solid Wood - Irokko Movingui Wood | Arabuild |  | Frames of all Wooden Doors | NAM | MKM |  |  | 2017-03-15 | 2017-03-27 | 12 | D | 0 | X | REFER THE ATTACHED COMMENTS SHEET | 1 2 37
85 | MS-0077-0 |  | 0 | MDF | SAMPLE | N/A | Melamine Faced MR MDF |  | 18mm Thick 2 Side White Colour (MF-101) Melamine Faced MR MDF with 2mm thick PVC Lipping | Emilam |  | Laundry Cabinets @ Apartments (Wherever Aplicable) | NAM | MKM |  |  | 2017-05-02 | 2017-05-09 | 7 | A | 0 | A |  | 1 2 37
86 | MS-0078-0 |  | 0 | PVC LIPPING | SAMPLE | N/A | PVC Edge Banding |  | 2mm thick PVC Edge Banding (Lipping) with Century Laminate Classic Walnut 421 | Trient |  | Pantry Units & High Counter @ Apartments (Wherever Aplicable) | NAM | MKM |  |  | 2017-05-02 | 2017-05-07 | 5 | A | 0 | A | APPROVED | 1 2 37
87 | MS-0080-0 |  | 0 | PVC | SAMPLE |  | PVC Edge Banding |  | 2mm Thick PVC Lipping White | Emilam / Al Jamoom |  | Apartment - Pantry Unit & High Counters | NAM | MKM |  |  | 2017-05-07 | 2017-05-09 | 2 | C | 0 | SS | THE WHITE BANDING IS NOT A PERFECT MATCH TO FORMICA ICE WHITE COLOR. | 1 2 37
88 | MS-0080-1 |  | 1 | PVC | SAMPLE | SWA-116.1 | PVC Edge Banding |  | 2mm Thick PVC Lipping White | Trient |  | Apartment - Pantry Unit & High Counters | NAM | MKM |  |  | 2017-05-18 | 2017-05-21 | 3 | A | 0 | A |  | 1 2 37
89 | MS-0081-0 |  | 0 | PVC | SAMPLE | SWA-117.1 | PVC Edge Banding |  | 2mm Thick PVC Lipping Grey | Emilam / Al Jamoom |  | Apartments - Pantry Unit & High Counter | NAM | MKM |  |  | 2017-05-07 | 2017-05-09 | 2 | B | 0 | B | SAMPLE: OPTION 2 IS APPROVED | 1 2 37
90 | MS-0083-0 |  | 0 | RAW MATERIAL | SAMPLE |  | Calcium Silicate |  | SILICATE BOARD: Calcium Silicate 6mm thick panel | Dexone/Gemini Trading |  | WC Back Wall to Receive Tile Finish | NAM | MKM |  |  | 2017-05-20 | 2017-05-21 | 1 | C | 0 | SS | • FOLLOW CHECKLIST REQUIREMENTS. • ATTACH RECENT TEST REPORT, TRADE LICENSE OF MANUFACTURER / SUPPLIER • COUNTRY OF ORIGIN, PREVIOUS PROJECT APPROVAL. | 1 2 37
91 | MS-0083-1 |  | 1 | RAW MATERIAL | SAMPLE |  | Calcium Silicate |  | SILICATE BOARD: Calcium Silicate 6mm thick panel | Dexone/Gemini Trading |  | WC Back Wall to Receive Tile Finish | NAM | MKM |  |  | 2017-05-23 | 2017-05-25 | 2 | B | 0 | SS | TEST REPORT (RECENT) AND ATTACHED. REQUIRED AS PER REV-00 COMMENTS. | 1 2 37
92 | MS-0083-2 |  | 2 | RAW MATERIAL | SAMPLE | N/A | Calcium Silicate |  | SILICATE BOARD: Calcium Silicate 6mm thick panel | Lesso /Gemini Trading |  | WC Back Wall to Receive Tile Finish | NAM | MKM |  |  | 2017-06-11 | 2017-06-15 | 4 | B | 0 | B | • SUBJECT MATERIAL IS NOT APPROVED, REV00 COMMENTS WERE NOT ADDRESSED, CHECKLIST REQUIREMENTS WERE NOT SATISFIED. • FIBER REINFORCED CALCIUM SILICATE BOARD MANUFACTURED BY LESSO IS APPROVED BASED ON THE DATA SHEET PROVIDED BY M/S GLI POST SUBMISSION (ATTACHED HERE) | 1 2 37
93 | MS-0097-00 |  | 0 | LACQUER FINISH | SAMPLE | LW1 | Lacquered wood - Sikkens code 5051 E1.03.77 (or NCS S 1505-Y70R) |  | Lacquered Finish Wood - NCS S 1505-Y70R | EVI |  | Wall Cladding @ Master Bedroom & Twin Room | NAM | MKM |  |  | 2017-11-29 | 2018-02-06 | 69 | SS | 55 | SS | LACQUER FINISH (LW), SIKKENS COLOR CONCEPT 5051FN.01.86 THIS WAS REPLACED BY LW1-SIKKENS CODE 5051E1.03.77 & CAN BE REPLACED BY NCS S 1505-Y70R | 1 2 37
94 | MS-0097-01 |  | 1 | LACQUER FINISH | SAMPLE | LW1 | Lacquered wood - Sikkens code 5051 E1.03.77 (or NCS S 1505-Y70R) |  | Lacquered Finish Wood - NCS S 1505-Y70R | EVI |  | Wall Cladding @ Master Bedroom & Twin Room | NAM | MKM |  |  | 2018-03-21 | 2018-03-27 | 6 | A | 0 | A | Approved: Lacquered Finish Color Ref: NCS S 1505-Y70R with 20% Glossy. | 1 2 37 |  |  | PA
95 | MS-0098-00 |  | 0 | LACQUER FINISH | SAMPLE | LW2 | Lacquered grey: Sikkens 5051 F0.03.66 (or NCS S 3502-Y) |  | Lacquered Finish Wood - NCS S 3502-Y | EVI |  | Master Wardrobe | NAM | MKM |  |  | 2017-11-29 | 2018-01-31 | 63 | SS | 49 | SS | As for specs should be Matt Finish - Matt Lacquered Ivory (Lacquered Grey) - NCS S 3502 Y. | 1 2 37
96 | MS-0098-01 |  | 1 | LACQUER FINISH | SAMPLE | LW2 | Lacquered grey: Sikkens 5051 F0.03.66 (or NCS S 3502-Y) | Jotun | Lacquered Finish Wood - NCS S 3502-Y | EVI |  | Master Wardrobe | NAM | MKM |  |  | 2018-02-07 | 2018-02-24 | 17 | B | 3 | B | Follow the colour from Jotun. Photo Attached. | 1 2 37 |  |  | PA
97 | MS-0099-0 |  | 0 | WOOD | SAMPLE | W01 | Wood Veneer: Busnelli - Natural Walnut Custom DGA - Basswood Walnut Dogato | Busnelli | Wood Veneer: Busnelli - Nero Dark Wood Veneer M 2002/F (Sample from Specified Source) | Busnelli | 16th Floor Gym Veneered Strip |  | NAM | MKM |  |  | 2017-12-06 | 2018-01-31 | 56 | SS | 42 | SS | • AS PER BUSNELLI, ORIGINAL CODE IS 0298 NATURAL WALNUT CUSTOM DGA • RESUBMIT BIGGER SAMPLE – 600X1200MM | 1 2 34
98 | MS-0099-1 |  | 1 | WOOD | SAMPLE | W01 | Wood Veneer: Busnelli - Natural Walnut Custom DGA - Basswood Walnut Dogato | Busnelli | Wood Veneer: Busnelli - 0298 Natural Walnut Custom DGA - Basswood Walnut Dogato (Sample from Specified Source Incorporating Previous Comments) | Busnelli | 16th Floor Joinery |  | NAM | MKM |  |  | 2018-02-13 | 2018-02-24 | 11 | C | 0 | SS | Material veneer cutting pattern width is only 100mm, it should be 250mm to 300mm width quarter cut pattern pointing upward direction. | 1 2 34
99 | MS-0099-2 |  | 2 | WOOD | SAMPLE | W01 | Wood Veneer: Busnelli - Natural Walnut Custom DGA - Basswood Walnut Dogato | Busnelli | Wood Veneer: Reconsituted Veneer- Walnut Crown Cut FKBU (Sample as specified by Client) | Busnelli/Fritz Kohi | 16th Floor Joinery |  | HHS | MKM |  |  | 2018-04-05 | 2018-04-29 | 24 | C | 10 | SS | Based on the attached coordination emails, the sample you have provided is rejected by Duccio Grassi Architect. Please wait for the exact sample by before you re-submit the sample. | 1 2 34 |  |  | PA
100 | MS-0099-3 |  | 3 | WOOD | SAMPLE | W01 | Wood Veneer: Busnelli - Natural Walnut Custom DGA - Basswood Walnut Dogato | Busnelli | Wood Veneer: Reconsituted Veneer- Walnut Crown Cut FKBU (2 Options) (Sample as specified by Client) | Busnelli & Greenline | 16th Floor Joinery |  | HHS | MKM |  |  | 2018-05-24 | 2018-05-27 | 3 | A | 0 | A | Based on the attached email by DGA, the material submitted / W01 is approved. | 1 2 34 |  |  | PA
101 | MS-0100-0 |  | 0 | WOOD | SAMPLE |  | Wood Veneer: Busnelli - Nero Dark Wood Veneer M 2002/F | Busnelli | Wood Veneer: Busnelli - Natural Walnut Custom DGA - Basswood Walnut Dogato (Sample from Specified Source) | Busnelli | 16th Floor Joinery |  | NAM | MKM |  |  | 2017-12-06 | 2018-01-31 | 56 | C | 42 | SS | • REFER TO DUCCUO GRASSI ARCHITECTS DRAWING NO 6-2- REV.1 DETAIL A TAT (DARK WOOD VENEER NERO M 2165/F BY BUSNELLI) PARQUET FLOOR. • COLOR IS CORRECT BUT IT SHOULD BE PARQUET FLOOR • SUBMIT BIGGER SAMPLE | 1 2 34 |  |  | PA
102 | MS-0100-1 |  | 1 | WOOD | SAMPLE | N/A | Wood Veneer: Busnelli - Nero Dark Wood Veneer M 2002/F | Busnelli | Wood: Solid Wood - Ash (Stained to Match Specified Sample) (Incorporating Previous Comments) | Busnelli/Chabros | 16th Floor Joinery |  | HHS | MKM |  |  | 2018-04-17 | 2018-04-29 | 12 | B | 0 | B | Approved with Comments. By Busnelli as Specified Source. | 1 2 34 |  |  | PA
103 | MS-0178-0 | ARK-0009 | 0 | WOOD | SAMPLE | WES-102 / WES-102.1 | TIMBER VENEER - BUSNELLI - NOCE WALNUT NM 116XX - 20% GLOSSY / TIMBER VENEER - BUSNELLI - NOCE WALNUT NM 116XX - 20% GLOSSY - TO BE MOISTURE RESISTANT AND SUITABLE FOR WET AREA / TIMBER VENEER STAINED TO AppROVED SAMpLE WITh HEAVY DUTY, UV-STABLE, ANTI-SCRATCh AND LOW VOC LEVEL pOLYUREThANE LACQUER SATIN FINISh. / TO BE MOISTURE RESISTANT AND SUITABLE FOR WET AREA | Busnelli | TIMBER VENEER - BUSNELLI - NOCE WALNUT NM 116XX - 20% GLOSSY / TIMBER VENEER | Busnelli | (45th TO 50th FLOOR EXECUTIVE SUITE) WALL PANELING AND JOINERY BATHROOM CEILING PANELING |  | HHS | ARK |  |  | 2018-10-24 | 2018-11-04 | 11 | B | 0 | B | Material sample is approved application as per ID drawings and specifications. Mock up sample is required at site prior to any bulk production. | 1 2 34 |  |  | PA
104 | MS-0179-0 | ARK-0010 | 0 | WOOD | SAMPLE | WLC-102 | TIMBER VENEER - NOCE WALNUT N 0116/1F mT - 20% GLOSSY TIMBER VENEER STAINED TO APPROVED SAMPLE WITH HEAVY DUTY, UV-STABLE, ANTI-SCRATCH AND LOW VOC LEVEL POLYURETHJANE LACQUER SATIN FINISH. | Busnelli | Timber Veneer - Noce Walnut N 0116/1F MT - 20% Glossy | Busnelli | (45th TO 50th FLOOR EXECUTIVE SUITE) (LIFT CAR) JOINERY |  | HHS | ARK |  |  | 2018-10-24 | 2018-11-04 | 11 | C | 0 | SS | Veneer to have straight quarter cut grains, no crown cut and knots. Verify & resubmit accordingly. | 1 2 34 |  |  | PA
105 | MS-0179-1 | ARK-0010 | 1 | WOOD | SAMPLE | WLC-102 | TIMBER VENEER - NOCE WALNUT N 0116/1F mT - 20% GLOSSY TIMBER VENEER STAINED TO APPROVED SAMPLE WITH HEAVY DUTY, UV-STABLE, ANTI-SCRATCH AND LOW VOC LEVEL POLYURETHJANE LACQUER SATIN FINISH. | Busnelli | Veneer Timber Veneer - Walnut N 0116 Quarter Cut | Busnelli | (45th TO 50th FLOOR EXECUTIVE SUITE) (LIFT CAR) JOINERY | Lift Car | MW | ARK |  |  | 2018-12-23 | 2019-01-03 | 11 | B | 0 | B | Sample piece is approved, installation to be inline with commented shop drawings. Mock up sample for approvals prior to any bulk procurement/production. | 1 2 34 |  |  | PA
106 | MS-0180-0 | ARK-0011 | 0 | WOOD | SAMPLE | WLC-103, WES-112 WES-115 | TIMBER VENEER - STAINED TO BLACK FINISH - 25% GLOSSY TIMBER VENEER STAINED TO APPROVED SAMPLE WITh HEAVY DUTY, UV-STABLE, ANTI-SCRATCH AND LOW VOC LEVEL POLYURETHANE LACQUER SATIN FINISH. | Busnelli | Timber Veneer - Stained To Black Finish - 25% Glossy | Busnelli | (45th TO 50th FLOOR EXECUTIVE SUITE) (LIFT CAR) JOINERY |  | HHS | ARK |  |  | 2018-10-24 | 2018-11-04 | 11 | B | 0 | B | Material sample is approved for veneer (WLC-103 & WES-112). Solid wood sample to match (WES-115) to be provided. Application as per ID drawings & specs. Mock up sample is required at site prior to any bulk production | 1 2 34 |  |  | PA
107 | MS-0106-0 |  | 0 | WOOD | SAMPLE | N/A | Headboard - CNC Engravement |  | Furniture: Headboard - CNC Engravement (As per Sample) | Greenline | Mock - Up Apartment - Twin Bedrrom |  | NAM | MKM |  |  | 2018-01-15 | 2018-01-16 | 1 | B | 0 | SS | Comments on Attached Image. | 1 2 34 | As per Hassan
108 | MS-0120-0 |  | 0 | RAW MATERIAL | SAMPLE |  |  |  | Mock Up Sample of Fret Cut Design on Veneered MDF for T.V Wall Unit (As per Sampel) | Greenline | T.V Wall Unit @ Studio Type -A |  | NAM | MKM |  |  | 2018-03-12 | 2018-03-26 | 14 | C | 0 | SS | Fret pattern to be in solid wood. Dimensions to be as per new site dimensions/heights. | 1 2 37
109 | MS-0120-1 |  | 1 | RAW MATERIAL | SAMPLE | SWA-102 |  |  | Fret Cut pattern Screen: 25mm Thick MDF Fret Cut Pattern Screen with Veneer SWA-102 Finish (As per Sample) | Greenline | T.V Wall Unit @ Studio Type -A |  | HHS | MKM |  |  | 2018-06-21 | 2018-06-26 | 5 | B | 0 | B | Sample piece approved in principal. However its finishing within thickness to improve. | 1 2 37
110 | MS-0134-0 |  | 0 | FORMICA | SAMPLE | LM 01 |  |  | Formica Laminate Colour Collection CYGNET | Formica/Modec |  | 16th Floor Private Apartment - Kitchen | HHS | MKM |  |  | 2018-04-23 | 2018-04-29 | 6 | A | 0 | A | Approved as Specified by I.D | 1 2 37 |  |  | PA
111 | MS-0135-0 |  | 0 | FORMICA | SAMPLE | LM 02 |  |  | Formica Laminate Wood Grains Beige Oak 0868 | Formica/Modec |  | 16th Floor Private Apartment - Kitchen | HHS | MKM |  |  | 2018-04-23 | 2018-04-29 | 6 | A | 0 | SS | Approved as Specified by I.D Wood Grains Beige Oak 0868. | 1 2 37 | As per Hassan |  | PA
112 | MS-0136-0 |  | 0 | PVC Lipping | SAMPLE | N/A |  |  | PVC Lipping to Match with Formica Laminate Submittal Ref.: MS-0135_Rev.00 Emilam MF 702 Grey Antique (As Per Sample) | Emilam |  | 16th Floor Private Apartment - Kitchen | HHS | MKM |  |  | 2018-04-23 | 2018-04-29 | 6 | B | 0 | SS | *Approved with Comment. *Material provided should match with wood grain beige Oak 0868 as specified by I.D. | 1 2 37 | As per Hassan |  | PA
113 | MS-0137-0 |  | 0 | PVC Lipping | SAMPLE |  |  |  | 2mm Hranipex - ABS-HU 121343 PVC Lipping to Match with Formica Laminate Submittal Ref: MS-0134 Rev.00 (As per Sample) | Hranipex |  | 16th Floor Private Apartment - Kitchen | HHS | MKM |  |  | 2018-04-28 | 2018-05-05 | 7 | C | 0 | SS | The colour of the sample is not matching with the Formica (MS-0134) Submit the matching colour. | 1 2 37 |  |  | PA
0 | MS-0137-1 |  | 1 | PVC Lipping | SAMPLE | N/A |  |  | 2mm Hranipex - ABS-HU 188533 PVC Lipping to Match with Formica Laminate Submittal Ref: MS-0134 Rev.00 (As per Sample) | Hranipex |  | 16th Floor Private Apartment - Kitchen | HHS | MKM |  |  | 2018-07-11 | 2018-07-19 | 8 | A | 0 | A | Approved, 2mm Hranifex - ABS-HU-12208 PVC lipping. | 1 2 37 |  |  | PA
1 | MS-0143-0 |  | 0 | FORMICA | SAMPLE |  | HPL Laminate RAL 9001 |  | Formica Sno White Ref: F2296 - Matt Finish (As per Sample) | Formica |  | 16th Floor Private Apartment - Twin Samll bedroom bathroom vanity | HHS | MKM |  |  | 2018-04-30 | 2018-05-05 | 5 | C | 0 | SS | As per dwg.data sheet no.5-2 Rev.02, spefied as RAL-9001. Please submit formula with RAL-9001. | 1 2 37 |  |  | PA
2 | MS-0143-1 |  | 1 | FORMICA | SAMPLE | N/A | HPL Laminate RAL 9001 |  | Formica :HPL Option-1: Irish Cream Matte 58 (MAT) - F1534 Option-2: Magnolia Matte 58 (MAT) - F15341 (As per Sample) | Formica |  | 16th Floor Private Apartment - Twin Samll bedroom bathroom vanity | HHS | MKM |  |  | 2018-05-21 | 2018-05-28 | 7 | OD | 0 | SS | Based on the attached email dated; 24 May 2018 DGA advise to use W01 Veneer wood finish instead of Laminated Wood RAL 9001. | 1 2 37 | As per Hassan |  | PA
3 | MS-0144-0 |  | 0 | PVC Lipping | SAMPLE | N/A |  |  | 2mm Hranipex - ABS-HU 10911 PVC Lipping to Match with Formica Laminate Submittal Ref: MS-0143 Rev.00 (As per Sample) | Hranipex |  | 16th Floor Private Apartment - Twin Samll bedroom bathroom vanity | HHS | MKM |  |  | 2018-04-30 | 2018-05-05 | 5 | C | 0 | SS | Submit the Sample with RAL 9001, as colour as specified in dwg. | 1 2 37 | As per Hassan |  | PA
4 | MS-0182-0 | ARK-0013 | 0 | WOOD | SAMPLE | N/A |  |  | Wood: Wooden Pattern for Lift Car as requested by Client (Sample only for Pattern Reference not Material Finish) | Greenline | Lift Car | Lift Car | LI | ARK |  |  | 2018-11-26 | 2018-12-22 | 26 | B | 12 | B | Sample piece with recessed metal in timber panel is fine, however colors are not inline with ID specifications. Kindly verify. | 1 2 34 |  |  | PA
GLASS & MIRROR | [26 empty] | PA
5 | MS-0012-00 |  | 0 | MIRROR | SAMPLE | N/A | SILVER BACKING MIRROR FOR TV UNIT, 940X740 mm, 6mm THICK, CLEAR |  | Silver Mirror 6mm thick | Touch Of Glass |  | All Guest Rooms | NAM | MKM |  |  | 2016-12-20 | 2017-01-15 | 26 | D | 12 | SS | Incomplete Submission. Manufacturer is not accepted. Comply to MKM technical specifications. Refer attached comments. | 1 2 40
6 | MS-0012-01 |  | 1 | MIRROR | SAMPLE | N/A | SILVER BACKING MIRROR FOR TV UNIT, 940X740 mm, 6mm THICK, CLEAR |  | Silver Mirror 6mm thick | AGC |  | All Guest Rooms | NAM | MKM |  |  | 2017-02-06 | 2017-02-22 | 16 | A | 2 | SS | NO CODE FOR NORMAL SILVER BACKING MIRROR – USED WITH THE FRAMED TV-MIRROR UNIT IN BEDROOM. | 1 2 40 | As per Hassan
7 | MS-0085-00 |  | 0 | MIRROR | SAMPLE | AW 701 |  |  | Grey Mirror 6mm thick | Mirodec |  | Apt 1, 2 & 3 Bedroom unit level 8 to 17 Floor & Junior Sutie A + B | NAM | MKM |  |  | 2017-06-12 | 2017-06-15 | 3 | A | 0 | SS |  | 1 2 40 | As per Hassan
8 | MS-0008-00 |  | 0 | MIRROR | SAMPLE | AW 703 | ANTIQUE BRONZE MIRROR, 6MM THICK |  | 6mm Thick Antique Mirror on Clear Glass (1) Ant 001, (2) Ant 002, (3) Ant 003, (4)- Ant 004 | Touch Of Glass |  | Standard Room & Executive Room | NAM | MKM |  |  | 2016-12-07 | 2016-12-07 | 0 | C | 0 | SS | Resubmit it with (a) sample boards (b) checklist attached & (c ) Dividers | 1 2 41
9 | MS-0008-01 |  | 0 | MIRROR | SAMPLE | AW 703 | ANTIQUE BRONZE MIRROR, 6MM THICK |  | 6mm Thick Antique Bronze Finished Mirror | Mirodec |  | Standard Room & Executive Room JUNIOR SUITE ONLY | NAM | MKM |  |  | 2017-01-02 | 2017-01-08 | 6 | B | 0 | B | * APARTMENT, JUNIOR SUITE & STANDARD ROOM /EXECUTIVE ARE HAVING DIFFERENT SAMPLE. * THE SUBMITTED SAMPLE IS FOR JUNIOR SUITE ONLY | 1 2 41
10 | MS-0069-00 |  | 0 | MIRROR | SAMPLE | AW 703.B |  |  | 6mm Thick Gold Antique Mirror | Mirodec |  | Guest Rooms (Except Junior Suite) | NAM | MKM |  |  | 2017-04-09 | 2017-04-11 | 2 | A | 0 | A |  | 1 2 41
11 | MS-0014-00 |  | 0 | GLASS | SAMPLE | AW 704 | TOUGHENED CRYSTAL CLEAR GLASS - LOW IRON, 10MM THICK, TRANSAPRENT POLISHED, FOR SHOWER DOOR |  | Thick Clear Toughened Glass 10mm | Touch Of Glass |  | Guest Rooms Shower Enclosures | NAM | MKM |  |  | 2016-12-20 | 2017-01-15 | 26 | D | 12 | SS | Submission is incomplete Attached test certificate is "FAKE" Refer attached comments. | 1 2 42
12 | MS-0014-01 |  | 1 | GLASS | SAMPLE | AW 704 | Clear Toughened Glass |  | 10mm Thick Clear Toughened Glass for shower Enclosure | Al Diwan Glass & Aluminum Cont |  | All Shower Enclosers | NAM | MKM |  |  | 2017-05-07 | 2017-05-09 | 2 | A | 0 | A | PROPOSED PRODUCT “SGG DIAMANT” MANUFACTURED BY “SAINT GOBAIN” AND SUPPLIED BY “AL DIWAN” IS APPROVED. | 1 2 42
13 | MS-0051-00 |  | 0 | GLASS | SAMPLE | AW 704 | Glass Door Hardware |  | 1- 10mm Clear Low Iron Tempered Glass for Shower Enclosure 2- Glass to Glass Hinge (316 Grade) 3- Wall to Glass Hinge (316 Grade) 4- Plastic Lipseal 5- SS U Channel 20x16x20mm (316 Grade) | Dubai Glass Industry |  | All Shower Enclosers | NAM | MKM |  |  | 2017-03-02 | 2017-03-14 | 12 | D | 0 | SS | Meeting was conducted at MKM office with proposed supplier representative and GLI team, Refer to attached comments sheet based on meeting discussion. | 1 2 42
14 | MS-0051-01 |  | 1 | GLASS | SAMPLE | AW 704 | Glass Door Hardware |  | 1- Glass Hinge (316 Grade) 2- Plastic Lipseal 3- SS U Channel 20x16x20mm (316 Grade) | Dubai Glass Industry |  | All Shower Enclosers | NAM | MKM |  |  | 2017-04-02 | 2017-04-06 | 4 | D | 0 | SS | • REFER ATTACHED COMMENTS SHEET. RESUBMIT AS PER THE MOCK UP. | 1 2 42
15 | MS-0051-02 |  | 2 | GLASS | SAMPLE | AW 704 | Glass Door Hardware |  | 1- Glass to Wall Hinge - 981.53.152 2- Glass to Glass Hinge - 981.53.182 | HAFELE |  | All Shower Enclosers | NAM | MKM |  |  | 2017-05-04 | 2017-05-08 | 4 | A | 0 | A | PROPOSED PRODUCT’S “HAFELE – AQUASYS”, “CHROME PLATED POLISHED BRASS” IS APPROVED. | 1 2 42
16 | MS-0079-00 |  | 0 | GLASS IRONMONGREY | SAMPLE | AW 704 | Glass Door Hardware |  | 1- Plastic Lipseal 2- SS U Channel 20x16x20mm (316 Grade) 3- Dow Coring Silicone 781 | Al Diwan Glass & Aluminum Cont |  | All Shower Enclosers | NAM | MKM |  |  | 2017-05-07 | 2017-05-09 | 2 | A | 0 | SS | PROPOSED MATERIALS ARE APPROVED. 1- 316 GRADE SS “U” CHANNEL, FROM TAIWAN (PYRAMID / YC INOX) 2- DOW CORNING 781 SEALANT 3- TRANSPARENT LIPSEAL BY “ROYAL” | 1 2 42
17 | MS-0079-01 |  | 1 | GLASS IRONMONGREY | SAMPLE | AW 704 | Glass Door Hardware |  | 1- Plastic Lipseal 2- SS U Channel 20x16x20mm (316 Grade) 3- Dow Coring Silicone 781 | Al Diwan Glass & Aluminum Cont |  | All Shower Enclosers | HHS | MKM |  |  | 2018-06-18 | 2018-06-21 | 3 | B | 0 | B | Proposed material is approved to provide Mock Up sample for our review application. | 1 2 42
18 | MS-0082-00 |  | 0 | TOWEL RAIL | SAMPLE | As per Mock Up | Glass Door Hardware |  | Towel Rail - 316 Grade for Glass Door, 450mm long | West Gate |  | All Bathrooms - Shower Enclosures | NAM | MKM |  |  | 2017-05-07 | 2017-05-09 | 2 | A | 0 | A | PROPOSED PRODUCT IS EXACTLY THE SAME USED IN MOCK-UP. | 1 2 42
19 | MS-0013-00 |  | 0 | GLASS | SAMPLE | AW 706 | REFLECTIVE TEMPERED BACK PAINTED GLASS, MIRODEC-RAL 7006 COLOR, LOW IRON, CRYSTAL CLEAR, BEVELLED POLISHED EDGE |  | Thick Back Painted Glass (RAL 7006) with Polished Chamfered Edge 6mm | Touch Of Glass |  | Guest Rooms Corridors | NAM | MKM |  |  | 2016-12-20 | 2017-01-08 | 19 | D | 5 | SS | GLASS IS BACK PAINTED, LOW IRON, REFLECTIVE & TOUGHENED PROVIDE JUSTIFICATION FOR ALTERNATIVE SUPPLIER | 1 2 43
20 | MS-0013-01 |  | 1 | GLASS | SAMPLE | AW 706 | REFLECTIVE TEMPERED BACK PAINTED GLASS, MIRODEC-RAL 7006 COLOR, LOW IRON, CRYSTAL CLEAR, BEVELLED POLISHED EDGE |  | 6mm Reflected Tempered Back Painted Glass (RAL 7006) with Polished Chamfered Edge | Touch Of Glass |  | Guest Rooms Corridors | NAM | MKM |  |  | 2017-02-06 | 2017-02-22 | 16 | A | 2 | A | APPROVED | 1 2 43
21 | MS-0044-00 |  | 0 | GLASS | SAMPLE | AW 703 |  |  | 6mm Black Back Painted Glass Tempered | Guardian |  | TV Wall Unit | NAM | MKM |  |  | 2017-02-23 | 2017-02-26 | 3 | A | 0 | A | APPROVED | 1 2 43
22 | MS-0015-00 |  | 0 | ACRYLIC | SAMPLE | AR 103 | MILKY WHITE, 5-6 MM THICK, 22% TRANSPARENT |  | 6mm thick Frosted Acrylic | Asia Poly Ind. |  | Vanity Counter Front Panels | NAM | MKM |  |  | 2017-01-02 | 2017-01-08 | 6 | B | 0 | SS | ACRYLIC TO BE MILKY WHITE FROSTED | 1 2 44
23 | MS-0015-01 |  | 0 | ACRYLIC | SAMPLE | AR 103 | MILKY WHITE, 5-6 MM THICK, 22% TRANSPARENT |  | 6mm thick Milky White Acrylic Ref : AP-445-Opal | Asia Poly Ind. |  | Vanity Counter Front Panels + Corridor Panel Cover | NAM | MKM |  |  | 2017-04-30 | 2017-05-02 | 2 | A | 0 | A | MILKY WHITE – OPAL IS APPROVED | 1 2 44
24 | MS-0016-00 |  | 0 | ACRYLIC | SAMPLE | N/A | 10MM THICK TRANSPARENT FASCIA FOR DRAWERS |  | 10mm thick Clear Acrylic | Asia Poly Ind. |  | Wardrobe Drawer Fascia | NAM | MKM |  |  | 2017-01-02 | 2017-01-08 | 6 | A | 0 | A |  | 1 2 45
25 | MS-0032-0 |  | 0 | ADHESIVE | TECHNICAL SHEET | N/A | ADHESIVE FOR MIRROR |  | Mirror Adhesive & Silicon Sealant (VT-210 Clear) | V-Tech |  | Mirror Installation Wherver Applicable | NAM | MKM |  |  | 2017-01-29 | 2017-02-06 | 8 | B | 0 | B | M/s. GLI to ensure the compatability of sealant with mirror coating. Safety Data Sheet provided in Unknown Language. | 1 2 46
26 |  |  | 0 | SS CHANNEL FOR GLASS | SAMPLE |  | STAINLESS STEEL U CHANNEL | [14 empty] | FI | REFER TO MS-0051 | 1 2 47
27 |  |  | 0 | SEALANT | SAMPLE |  | SILICONE SEALANT | [14 empty] | FI | REFER TO MS-0032 | 1 2 48
28 | MS-0096-00 |  | 0 | GLASS | SAMPLE | ANT1, SM & BG | ANTELIO GLASS - BLACK BACK PAINTED, STOPSOL CLASSIC 6mm GREY, PLANIBAL BRONZE 6mm | AGC GLASS | 1. Black BP Glass - Tempered Float Backpainted Glass in RAL Black; Polished Edge (THK-6mm) 2. Grey Reflective - Tempered Grey Reflective Glass; Polished Edge (THK-6mm) 3. Bronze Glass - Tempered Bronze Tinted Glass; Polished Edge (THK-6mm) | MIRODEC | 16th Floor Private Apartment | 16th Floor Private Apartment | NAM | MKM |  |  | 2017-11-23 | 2017-12-04 | 11 | C | 0 | SS | No BOQ Reference No drawings with highlighted the locations to use. No proper manufacturer details, incomplete documents. | 1 2 45 | As per Hassan |  | PA
29 | MS-0115-00 |  | 0 | GLASS | SAMPLE | ANT1 | Antello Glass Black Painted Glass |  | Glass: Antello Glass Black Painted Glass - Polished Egde (Thickness: 6mm) | Saint Gobin / ACG Glass | 16th Floor Private Apartment | 16th Floor Private Apartment | NAM | MKM |  |  | 2018-02-06 | 2018-02-24 | 18 | SS | 4 | SS | Material should be exactly as per control sample. Antelio glass black back painted (ANT1). Not matching with control sample. | 1 2 45 |  |  | PA
30 | MS-0115-01 |  | 1 | GLASS | SAMPLE | ANT1 | Antello Glass Black Painted Glass |  | Glass: 6mm thick Grey Tinted Mirror (Matching Control Sample) | Saint Gobin / ACG Glass | 16th Floor Private Apartment | 16th Floor Private Apartment | HHS | MKM |  |  | 2018-04-05 | 2018-04-29 | 24 | B | 10 | SS | The sample should match exactly with the control sample, reflection effect with RAL 9004. | 1 2 45 |  |  | PA
31 | MS-0115-02 |  | 2 | GLASS | SAMPLE | ANT1 | Antello Glass Black Painted Glass |  | Glass: 6mm thick Black backpainted Antelio Glass Option 1: MNT(ST)-GL-108-BP Ral 9004 Option 2: MNT(ST)-GL-120-BP Ral 9004 Option 3: MNT(ST)-GL-136-BP Ral 9004 (Matching Control Sample attached) | Saint Gobin / ACG Glass | 16th Floor Private Apartment | 16th Floor Private Apartment | HHS | MKM |  |  | 2018-05-31 | 2018-06-03 | 3 | B | 0 | B | Approved, Option 3. | 1 2 45 |  |  | PA
32 | MS-0116-00 |  | 0 | GLASS | SAMPLE | SM | Stopsol Classic 6mm Grey by AGC Glass | AGC GLASS | Glass: 6mm thick Black backpainted Antelio Glass Option 1: MNT(ST)-GL-108-BP Ral 9004 Option 2: MNT(ST)-GL-120-BP Ral 9004 Option 3: MNT(ST)-GL-136-BP Ral 9004 (Matching Control Sample attached) | Mirodec | 16th Floor Private Apartment | 16th Floor Private Apartment | NAM | MKM |  |  | 2018-04-04 | 2018-04-07 | 3 | SS | 0 | SS | GLASS REFLECTION SHOULD MATCH THE CONTROL SAMPLE | 1 2 45 |  |  | PA
33 | MS-0116-01 |  | 1 | GLASS | SAMPLE | SM | Stopsol Classic 6mm Grey by AGC Glass | AGC GLASS | Glass: Tempered Grey Reflected Glass; Polished Egde (Thickness: 6mm) Mirodec Ref: KB/056(2)-18 (Sample Incorporating Previous Comments & Matching to Control Sample) | AGC Glass / Mirodec | 16th Floor Private Apartment | 16th Floor Private Apartment | HHS | MKM |  |  | 2018-04-25 | 2018-05-08 | 13 | B | 0 | B | One sample approved which is 98% matching with control sample. One sample rejected. | 1 2 45 |  |  | PA
34 | MS-0121-00 |  | 0 | MIRROR | SAMPLE | SWGS-114 |  |  | 6mm Thick Etched Bronze Tinted Mirror (As per Sample Installed at Site) | Glaverbel / Five Stars Aluminium | Bathrooms @ Guest Rooms & Suites and Apartment Master Bedrooms | Bathrooms @ Guest Rooms & Suites and Apartment Master Bedrooms | NAM | MKM |  |  | 2018-03-27 | 2018-04-02 | 6 | B | 0 | SS | Material inspected and found acceptable. To be reviewd after installation of main back lit mirror in front of it. | 1 2 45 | As per Hassan
35 | MS-0125-00 |  | 0 | MIRROR | SAMPLE | MRR |  |  | Silver Mirror 6mm thick (As per Sample) | Gardian | 1601 Apartment | 1601 Apartment | HHS | MKM |  |  | 2018-04-05 | 2018-04-29 | 24 | B | 10 | B | GLI to ensure that the mirror provided will have a high & long lasting quality of both front & backing materials. | 1 2 45 |  |  | PA
36 | MS-0174-00 | ARK-0004 | 0 | MIRROR | SAMPLE | WES-119 |  |  | Mirror Silver Backed Mirror 6mm thick (As per Technical Data) Note: Previously approved with MKM-05Q-IDP-01-MS-0125-00 | Gardian | 45th to 50th Floor Executive Suite - Joinery | 45th to 50th Floor Executive Suite - Joinery | HHS | ARK |  |  | 2018-09-26 | 2018-10-08 | 12 | C | 0 | SS | Contractor to provide attach ID spec/cut sheet along with their submittal along with its physical sample. | 1 2 45 |  |  | PA
37 | MS-0174-01 | ARK-0004 | 1 | MIRROR | SAMPLE | WES-119 WLC-105 |  |  | Mirror Silver Backed Mirror 6mm thick (As per Technical Data) Note: Previously approved with MKM-05Q-IDP-01-MS-0125-00 | Gardian | 45th to 50th Floor Executive Suite - Joinery | 45th to 50th Floor Executive Suite - Joinery | HHS | ARK |  |  | 2018-10-10 | 2018-10-22 | 12 | B | 0 | B | Contractor to follow similar instructions as provided on your material submittal earlier. | 1 2 45 |  |  | PA
38 | MS-0126-00 |  | 0 | GLASS | SAMPLE | BG | Plainibel Bronze Glass | AGC GLASS | Bronze Glass: Tempered Bronze Tinted Glass - Polished Edge (Thickness:6mm (As per Sample) | ACG Glass / Mirodec | 16th Floor Private Apartment | 16th Floor Private Apartment | HHS | MKM |  |  | 2018-04-05 | 2018-04-29 | 24 | B | 10 | SS | The attached sample to be match with the colour as specified on ID drawings. Planibel Bronze 6mm Thick by AGC Glass unlimited. | 1 2 45 |  |  | PA
39 | MS-0126-01 |  | 1 | GLASS | SAMPLE | BG | Plainibel Bronze Glass | AGC GLASS | Bronze Glass: Tempered Bronze Tinted Glass - Polished Edge (Thickness:6mm (As per Sample) | ACG Glass / Mirodec | 16th Floor Private Apartment | 16th Floor Private Apartment | HHS | MKM |  |  | 2018-05-31 | 2018-06-03 | 3 | B | 0 | B | Approved as specified. | 1 2 45 |  |  | PA
40 | MS-0156-00 |  | 0 | GLASS | SAMPLE | SWGS-109 |  |  | Glass 6mm thick Grey Tinted Glass (Gr-GL) (As per Sample) | Mirodec | Top of Coffee Table (SWGS-325) | Top of Coffee Table (SWGS-325) | HHS | MKM |  |  | 2018-06-17 | 2018-06-21 | 4 | B | 0 | B | Sample piece is approved. Application to be as per ID drawings. | 1 2 45 |  |  | PA
41 | MS-0158-00 |  | 0 | MIRROR | SAMPLE |  |  |  | Mirror: 6mm thick Grey Tinted Mirror with Custom Etched Pattern (As per Sample) | Joseph Decorative Glass/Mirodec | Junior Suite 19th to 23rd Floor Dining Units |  | HHS | MKM |  |  | 2018-06-21 | 2018-06-26 | 5 | C | 0 | SS | Sample piece provided is not approved. Pattern to sum down. Etched pattern finishing is poor please discuss. | 1 2 45 |  |  | PA
42 | MS-0158-01 |  | 1 | MIRROR | SAMPLE | SWGS-107 |  |  | Mirror: 6mm thick Grey Tinted Etched Mirror (As per Sample) | Mirodec | Junior Suite 19th to 23rd Floor Dining Units |  | HHS | MKM |  |  | 2018-08-09 | 2018-08-19 | 10 | A | 0 | A | Sample Approved. | 1 2 45 |  |  | PA
43 | MS-0168-00 |  | 0 | MIRROR | SAMPLE | SWGS-106 |  |  | Mirror: 6mm thick Grey Tinted Mirror Mirror (As per Sample) | Mirodec | Junior Suite 19th to 23rd Floor Dining Units |  | HHS | MKM |  |  | 2018-08-09 | 2018-08-19 | 10 | A | 0 | A | Sample Approved. | 1 2 45 |  |  | PA
44 | MS-0175-00 | ARK-0005 | 0 | MIRROR | SAMPLE | WES-120 |  |  | Mirror 6mm thick Grey Tinted Mirror (As per Technical Data) Note: Previously approved with MKM-05Q-IDP-01-MS-0168-00 | Mirodec | 45th to 50th Floor Executive Suite - Joinery | 45th to 50th Floor Executive Suite - Joinery | HHS | ARK |  |  | 2018-09-26 | 2018-10-08 | 12 | C | 0 | SS | Contractor to provide attach ID spec/cut sheet along with their submittal along with its physical sample. | 1 2 45 |  |  | PA
45 | MS-0175-01 | ARK-0005 | 1 | MIRROR | SAMPLE | WES-120 |  |  | Mirror 6mm thick Grey Tinted Mirror (As per Technical Data) Note: Previously approved with MKM-05Q-IDP-01-MS-0168-00 | Mirodec | 45th to 50th Floor Executive Suite - Joinery | 45th to 50th Floor Executive Suite - Joinery | HHS | ARK |  |  | 2018-10-10 | 2018-10-22 | 12 | B | 0 | B | Contractor to follow similar comments as made on previous submittals. Application as per approved shop drawings. | 1 2 45 |  |  | PA
46 | MS-0176-00 | ARK-0006 | 0 |  | SAMPLE | WES-110 | BRONZE MIRROR / 6 MM THICK BRONZE MIRROR WITh BEVELLED EDGES | JOSEPH DECORATIVE GLASS | Mirror 6mm thick Bronze Mirror with Beveled Edges (As per Sample) | JOSEPH DECORATIVE GLASS |  | (45th TO 50th FLOOR EXECUTIVE SUITE) JOINERY | HHS | ARK |  |  | 2018-10-01 | 2018-10-15 | 14 | C | 0 | SS | Contractor to provide all relevant documents inclusive of ID spec & Cut Sheets (Check you submittal documents) | 1 2 45 |  |  | PA
47 | MS-0176-01 | ARK-0006 | 1 |  | SAMPLE | WES-110 | BRONZE MIRROR / 6 MM THICK BRONZE MIRROR WITh BEVELLED EDGES | JOSEPH DECORATIVE GLASS | Mirror 6mm thick Bronze Mirror with Beveled Edges (As per Sample) | JOSEPH DECORATIVE GLASS |  | (45th TO 50th FLOOR EXECUTIVE SUITE) JOINERY | HHS | ARK |  |  | 2018-10-22 | 2018-11-08 | 17 | B | 3 | B | Material is approved. Application as per ID specs / Drwg | 1 2 45 |  |  | PA
48 | MS-0177-00 | ARK-0007 | 0 |  | SAMPLE | WES-111 | GREY TINTED MIRROR WITh CUSTOM ETChED pATTERN - REFER TO DRAWINGS FOR Pattern / 6 MM ThICK GREY TINTED MIRROR WITh CUSTOM ETChED PATTERN | JOSEPH DECORATIVE GLASS | Mirror 6mm thick Grey Tinted Mirror with Etched Pattern (As per Sample) | JOSEPH DECORATIVE GLASS |  | (45th TO 50th FLOOR EXECUTIVE SUITE) JOINERY | HHS | ARK |  |  | 2018-10-01 | 2018-10-21 | 20 | C | 6 | SS | To provide ID spec/Cut sheet along with your submittals. Also physical sample piece is required for the same. | 1 2 45 |  |  | PA
49 | MS-0177-01 | ARK-0007 | 1 |  | SAMPLE | WES-111 | GREY TINTED MIRROR WITh CUSTOM ETChED pATTERN - REFER TO DRAWINGS FOR Pattern / 6 MM ThICK GREY TINTED MIRROR WITh CUSTOM ETChED PATTERN | JOSEPH DECORATIVE GLASS | Mirror 6mm thick Grey Tinted Mirror with Etched Pattern (As per Sample) | JOSEPH DECORATIVE GLASS |  | (45th TO 50th FLOOR EXECUTIVE SUITE) JOINERY | HHS | ARK |  |  | 2018-10-22 | 2018-11-08 | 17 | B | 3 | B | Material in principal is fine. Contractor to provide size, artwork / drawing prior to its procurement. | 1 2 45 |  |  | PA
50 | MS-0181-00 | ARK-0012 | 0 |  | SAMPLE | N/A | BRONZE GLASS |  | Glass 10mm thick Tempered Bronze Glass (As per Sample) | Emirates Float Glass LLC |  | EXECUTIVE SUITE | HHS | ARK |  |  | 2018-11-04 | 2018-11-08 | 4 | C | 0 | C | Sample submitted is too light in color. It needs to be much darker but not 100% opaque. Revise & resubmit. | 1 2 45 |  |  | PA
51 | MS-0185-00 | ARK-0016 | 0 |  | SAMPLE | N/A | Mirror 6mm Thk Grey Tinted Etched Mirror |  | Mirror 6mm Thk Grey Tinted Etched Mirror | Emirates Float Glass LLC |  | EXECUTIVE SUITE | HHS | ARK |  |  | 2018-11-04 | 2018-11-08 | 4 | C | 0 | C | Sample submitted is too light in color. It needs to be much darker but not 100% opaque. Revise & resubmit. | 1 2 45 |  |  | PA
52 | MS-0185-00 | ARK-0016 | 0 |  | SAMPLE | SWGS-107 | Mirror 6mm Thk Grey Tinted Etched Mirror |  | Mirror 6mm Thk Grey Tinted Etched Mirror | Touch Of Glass |  | EXECUTIVE SUITE | HHS | ARK |  |  | 2019-06-27 | 2019-07-13 | 16 | a | 2 | a | The material was approved on liast year. -Now the supplier only changed. | 1 2 45 |  |  | PA
IRONMONGERY | [26 empty] | PA
53 | MS-0024-0 |  | 0 | IRONMONGERY | SAMPLE | N/A | FIRE DOOR SEAL (INTUMESCENT STRIP) |  | FIRE DOOR SEAL 15X4mm INTUMESCENT STRIP (SAMPLE AS SUBMITTED FOR REV.0) | Pyroplex |  | Fire Rated Doors | NAM | MKM |  |  | 2017-01-25 | 2017-01-29 | 4 | B | 0 | B | Local authority compliance to be ensured. | 1 2 53
54 | MS-0023-0 |  | 0 | IRONMONGERY | SAMPLE | N/A | FIRE RATED EXPANDING FOAM |  | FIRE RATED EXPANDING FOAM | Tekapur /ETT |  | Fire Rated Doors | NAM | MKM |  |  | 2017-01-25 | 2017-01-29 | 4 | B | 0 | B | Attached test certificatefrom "Certifire is expired. Submit valid certificate. Attached ISO certificate is for a different manufacturer not relevant to submittal. | 1 2 54
55 | MS-0088-0 |  | 0 | PVC SEAL | SAMPLE | N/A | Rebate Seal |  | Hafele Star Tec PVC Rebate Seal Drak Brown Colour (Hafele Ref: 950.10.302) & Hafele Star Tec TPE Rebate Seal Drak Brown Colour (Hafele Ref: 950.10.312) | HAFELE |  | Normal Wooden Doors 950.10.302 & Main Entrance Doors 950.10.312 (Wherever Aplicable) | NAM | MKM |  |  | 2017-07-12 | 2017-07-12 | 0 | B | 0 | B | Color approved for 8th – 17th floor only (walnut finish) use ‘1’ hr Fire rated, Dark Brown Color, door seal from ‘HAFELE’ for all apartment doors (Internal / External). | 1 2 54
56 | MS-0123-0 |  | 0 | PVC SEAL | SAMPLE |  | Rebate Seal |  | Hafele Star Tec PVC Rebate Seal Drak Brown Colour (Hafele Ref: 950.10.312) (As per Sample) | HAFELE |  | 19th to 41th Floor Doors & Apartment 1601 | HHS | MKM |  |  | 2018-04-05 | 2018-04-29 | 24 | SS | 10 | SS | Color of rebate seal does not match with Macassal Ebony Veneer. Prefer to have darker color. | 1 2 54
57 | MS-0123-1 |  | 1 | PVC SEAL | SAMPLE | N/A | Rebate Seal |  | Hafele Star Tec PVC Rebate Seal Drak Brown Colour (Hafele Ref: 950.10.312) (As per Sample) | HAFELE |  | 19th to 41th Floor Doors & Apartment 1601 | HHS | MKM |  |  | 2018-05-03 | 2018-05-08 | 5 | B | 0 | B | Material approval is subject to Mock Up installation & our review of the same at site. | 1 2 54
58 | MS-0138-0 |  | 0 | IRONMONGERY |  |  | IRONMONGERY 1- Hardware Set Schedule 2- Door Schedule 3- Technical Data |  | Hafele Door Ironmongery - Enclose the Following: A- Hardware Sets B- Material Data Sheets C- Door Schedule D- Layout Key Plans Notes: 1- As discussed with Mr. Emmanuel, this submittal does not include any samples due to small QTY, Only hardware schedule, door schedule, key plans & Data sheet of each hardware. 2- This submittal does not include the samples of the Lever handle and Pull Handles which will follow by another Separate submittal later. | Hafele |  | 16th Floor Private Apartment Woodne Doors Harware | HHS | MKM |  |  | 2018-04-30 | 2018-05-17 | 17 | B | 3 | SS | Approved with comments. GLI should comply based on DGA attached comment. Update the rejected item & re-submit. | 1 2 54 |  |  | PA
59 | MS-0138-1 |  | 1 | IRONMONGERY |  | MKM-05Q-IDP-01-CI-0077 | IRONMONGERY 1- Hardware Set Schedule 2- Door Schedule 3- Technical Data |  | Hafele Door Ironmongery A- Hardware Sets (Updated), B- Material Data Sheets, C- Door Schedule, D- Layout Key Plans Notes: - Attached sample for the handle represent the finish will be applied for all the hardware finishes in Satin Brass finish ( alternative finish to match BR finish) - The pull handle and door plates will be custom made as per our approved shop drawing with BR finish (Gold leaf) as per our approved material | Hafele |  | 16th Floor Private Apartment Woodne Doors Harware | HHS | MKM |  |  | 2018-05-24 | 2018-05-28 | 4 | A | 0 | A | The handle sample submitted is approved. GLI should ensure that all ironmongery to be use will be Brass finish as commented by ID/DGA. | 1 2 54 |  |  | PA
60 |  |  | 0 | FOAM | SAMPLE | _ | JOINT FOAM |  | JOINT FOAM FIRE RESISTANT PLUS | [12 empty] | X |  | 1 2 57
61 |  |  | 0 | SEALANT | SAMPLE | _ | FIRE STOP SYSTEM |  | FIRE STOP SYSTEM: FLEXIBLE FIRE STOP SEALANT | [12 empty] | X |  | 1 2 58
FURNITURE HARDWARE | [26 empty] | PA
62 | MS-0043-0 |  | 0 | FURNITURE HARDWARE | SAMPLE | N/A | FURNITURE HARDWARE |  | FURNITURE HARDWARE AS PER ATTACHED LIST |  | Wordrobe & Furniture | Wordrobe & Furniture | NAM | MKM |  |  | 2017-02-20 | 2017-02-26 | 6 | A | 0 | SS | • ALL BLUM ACCESSORIES APPROVED, DOOR SOFT CLOSER MISSING. • ITEMS 5, 11, 12, 13, 14 PROVIDE BETTER OPTIONS MATCHING MOCK-UP. • ITEM 15-PROVIDE LOCATION OF USE- PROVIDE BETTER OPTION. | 1 2 60
63 | MS-0043-1 |  | 1 | FURNITURE HARDWARE | SAMPLE | N/A | FURNITURE HARDWARE |  | 1- Wardrobe Rail - 801.13.222 - Chrome 2- Rail End Support - 803.25.260 - Chrome 3- SOSS Hinges - 341.07.727 - Nickel Plated | Hafele | Wordrobe & Furniture | Wordrobe & Furniture | NAM | MKM |  |  | 2017-03-16 | 2017-03-21 | 5 | A | 0 | A | APPROVED | 1 2 60
64 | MS-0043-0 |  | 0 | FURNITURE HARDWARE | SAMPLE |  | DOUBLE BALL CATCH | [11 empty] | 43703 | FI | 43689 | FI |  | 1 2 60
65 | MS-0043-0 |  | 0 | WARDROBE FITTINGS | SAMPLE |  | CLIP TOP HINGE 110° ANGLE FULL OVERLAY | [9 empty] | 2017-02-20 | 2017-02-26 | 6 | A | 0 | FI |  | 1 2 61
66 | MS-0043-0 |  | 0 | WARDROBE FITTINGS | SAMPLE |  | CLIP TOP HINGE 110° ANGLE HALF OVERLAY | [9 empty] | 2017-02-20 | 2017-02-26 | 6 | A | 0 | FI
67 | MS-0043-0 |  | 0 | FURNITURE HARDWARE | SAMPLE |  | CLIP TOP HINGE 110° ANGLE INSET TYPE | [9 empty] | 2017-02-20 | 2017-02-26 | 6 | A | 0 | FI |  | 1 2 62
68 | MS-0043-0 |  | 0 | FURNITURE HARDWARE | SAMPLE |  | SOSS HINGE | [9 empty] | 2017-02-20 | 2017-02-26 | 6 | D | 0 | FI | BETTER PRODUCT REQUIRED | 1 2 63
69 | MS-0043-0 |  | 0 | FURNITURE HARDWARE | SAMPLE |  | FULL EXIT DRAWER RUNNER SOFT CLOSING 500MM | [9 empty] | 2017-02-20 | 2017-02-26 | 6 | A | 0 | FI |  | 1 2 64
70 | MS-0043-0 |  | 0 | FURNITURE HARDWARE | SAMPLE |  | FULL EXIT DRAWER RUNNER SOFT CLOSING 400MM | [9 empty] | 2017-02-20 | 2017-02-26 | 6 | A | 0 | FI |  | 1 2 65
71 | MS-0043-0 |  | 0 | FURNITURE HARDWARE | SAMPLE |  | FULL EXIT DRAWER RUNNER PUSH TO OPEN 20" | [9 empty] | 2017-02-20 | 2017-02-26 | 6 | A | 0 | FI |  | 1 2 66
72 | MS-0043-0 |  | 0 | FURNITURE HARDWARE | SAMPLE |  | DRAWER LOCKING DEVICE | [9 empty] | 2017-02-20 | 2017-02-26 | 6 | A | 0 | FI |  | 1 2 67
73 | MS-0043-0 |  | 0 | FURNITURE HARDWARE | SAMPLE |  | DRAWER TIP-ON SYSTEM | [9 empty] | 2017-02-20 | 2017-02-26 | 6 | A | 0 | FI |  | 1 2 67
74 | MS-0043-0 |  | 0 | FURNITURE HARDWARE | SAMPLE |  | MAGNETIC PUSH CATCH + STRIKING PLATE | [9 empty] | 2017-02-20 | 2017-02-26 | 6 | D | 0 | FI | REFER MOCK-UP (PHOTOS ATTACHED) | 1 2 68
75 | MS-0043-0 |  | 0 | FURNITURE HARDWARE | SAMPLE |  | ROUND TUBE STEEL HANGER | [9 empty] | 2017-02-20 | 2017-02-26 | 6 | D | 0 | FI | OVAL TUBE AS PER MOCK UP | 1 2 70
76 | MS-0043-0 |  | 0 | DOOR HARDWARE | SAMPLE |  | FLANGE BRACKET | [9 empty] | 2017-02-20 | 2017-02-26 | 6 | D | 0 | FI |  | 1 2 71
77 | MS-0043-0 |  | 0 | DOOR HARDWARE | SAMPLE |  | DRAWER LOCK | [9 empty] | 2017-02-20 | 2017-02-26 | 6 | D | 0 | FI | LOCATION OF USE. PROVIDE BETTER OPTION. | 1 2 72
78 | MS-0065-0 |  | 0 |  | SAMPLE | N/A | DRAWER RUNNER |  | DRAWER RUNNER SINGLE EXTENSION - 432.16.935 |  | Maid room Wardrobe & Work Desk Type 1 | Maid room Wardrobe & Work Desk Type 1 | NAM | MKM |  |  | 2017-03-16 | 2017-03-21 | 5 | A | 0 | A | APPROVED | 1 2 73
79 | MS-0067-0 |  | 0 |  | SAMPLE | N/A | Micro Switch |  | 820.22.110 - Built-In Switch Unit With Universal Push Button Switch |  | All Wardrobes | All Wardrobes | NAM | MKM |  |  | 2017-04-04 | 2017-04-05 | 1 | A | 0 | A | APPROVED | 1 2 73
80 |  |  | 0 | GLASS DOOR HARDWARE | SAMPLE |  | SHOWER DOOR HINGES | [14 empty] | FI | REFER TO SUBMITTAL NO: 0051 | 1 2 73
81 |  |  | 0 | GLASS DOOR HARDWARE | SAMPLE |  | SHOWER DOOR TRANSPARENT SEAL | [14 empty] | FI | REFER TO SUBMITTAL NO: 0051 | 1 2 74
82 | MS-0073-0 |  | 0 | FURNITURE HARDWARE | SAMPLE | N/A | Connecting fitting |  | Dometic Connecting fitting for Refrigerators door hafele ref : 568.16.020 colour guide : White and Rail : Black | Hafele | Mini Bar Fridge Cabinet @ Guest Rooms (Wherever Aplicable) | Mini Bar Fridge Cabinet @ Guest Rooms (Wherever Aplicable) | NAM | MKM |  |  | 2017-04-25 | 2017-04-26 | 1 | A | 0 | A | APPROVED | 1 2 73
83 | MS-0074-0 |  | 0 | FURNITURE HARDWARE | SAMPLE | N/A | magnetic push catch |  | Furniture Hardware : Lamp touch magnetic push catch (Long Stroke) Model ref: LAM120B colour brown size : A46mm x B7mm x C17mm | Lamp Sugatsune | GRMS Access Doors Guest Rooms (Wherever Applicable) | GRMS Access Doors Guest Rooms (Wherever Applicable) | NAM | MKM |  |  | 2017-04-25 | 2017-04-26 | 1 | A | 0 | A | APPROVED | 1 2 73
84 | MS-0075-0 |  | 0 | FURNITURE HARDWARE | SAMPLE | N/A | Drawer Lock |  | Furniture Hardware : Drawer Lock (Camlock) Ref : TGL507111 Nickel Plated | Amstrong | GRMS Access Doors Guest Rooms (Wherever Applicable) | GRMS Access Doors Guest Rooms (Wherever Applicable) | NAM | MKM |  |  | 2017-04-25 | 2017-04-26 | 1 | B | 0 | B | APPROVED WITH COMMENTS | 1 2 73
85 | MS-0076-0 |  | 0 | FURNITURE HARDWARE | SAMPLE | N/A | Push catch |  | Furniture Hardware : Ultimate Push catch model ref : SC5381BR Colour Brown, size : A57mm x B22mm x C18mm D14mm | Ultimate | Apartments & Guest Rooms work desk & cabinets (Wherever Applicable) | Apartments & Guest Rooms work desk & cabinets (Wherever Applicable) | NAM | MKM |  |  | 2017-04-25 | 2017-04-26 | 1 | A | 0 | A | APPROVED | 1 2 73
86 | MS-0084-0 |  | 0 | FURNITURE HARDWARE | SAMPLE | As per Mock Up | VENTILATION GRILL |  | VENTILATION GRILL: Ref# 575.24.900 - Aluminiun Profiled - Silver Color, size: 570mm x 57mm | Hafele | Mini Bar Guest Room & Pantry units at apartments | Mini Bar Guest Room & Pantry units at apartments | NAM | MKM |  |  | 2017-06-06 | 2017-06-15 | 9 | A | 0 | A | APPROVED | 1 2 73
87 | MS-0101-0 |  | 0 | FURNITURE HARDWARE | SAMPLE | N/A | Furniture Hardware: Glass Bracket |  | Furniture Hardware: Ultimate Glass Bracket Code: FO130202101 Chrome Finished (Sample from Specified Source) | Ulitimate | TV Unit Type-3 Glass Shelves Support @ Studio A in Level 8 to 17 | TV Unit Type-3 Glass Shelves Support @ Studio A in Level 8 to 17 | NAM | MKM |  |  | 2017-12-10 | 2017-12-10 | 0 | D | 0 | SS | As discussed & agreed in the meeting please submit another type of bracket. | 1 2 73 | AS PER HASSAN
88 | MS-0159-0 |  | 0 | DOOR HARDWARE | SAMPLE | SWA-601 |  |  | Bedside Table Knob: Hafele Steel Knob 133.50.678 Gold Champaigne Finish 9As per Sample) | Hafele | Apartments Master Bedroom Bedside Table | Guestrooms & Suite Table Drawer Knob | HHS | MKM |  |  | 2018-06-21 | 2018-06-26 | 5 | B | 0 | B | Sample piece is approved to provide original certificate upon its procurement. | 1 2 72
89 | MS-0160-0 |  | 0 | DOOR HARDWARE | Data Sheets |  |  |  | Bedside Table Drawer Knob: Kawajun Hardware PC-142-GL Pull and Knob Gold Plated Zinc Alloy (AS per Data Sheet - Specified Supplier Needs 2 Weeks to Arrange Sample) | Kawajun / Metallic Equipment | Guestrooms & Suite Table Drawer Knob | Guestrooms & Suite Table Drawer Knob | HHS | MKM |  |  | 2018-06-21 | 2018-06-24 | 3 | C | 0 | SS | Provide sample for our review & Confirmation. | 1 2 72
90 | MS-0160-1 |  | 1 | DOOR HARDWARE | SAMPLE | SWGS-600 |  |  | Bedside Table Drawer Knob: Kawajun Hardware PC-142-GL Pull and Knob Gold Plated Zinc Alloy (As per Sample) | Kawajun / Metallic Equipment | Guestrooms & Suite Table Drawer Knob | Guestrooms & Suite Table Drawer Knob | HHS | MKM |  |  | 2018-07-08 | 2018-07-12 | 4 | A | 0 | A | Sample piece is approved installation as per commented shop drawing. | 1 2 72
91 | MS-0163-0 |  | 0 | FURNITURE HARDWARE | SAMPLE | CI-0090-00 & Approved Mock Up |  |  | Push to Open Set for Shutters: BL956A1002SW - Blum Tip on for Door Silk WH Long Version BL956A1201SW - Blum Tip on Adapter BL9551008 - Blum Adhesive Plate for Tip on BL75B1550 - Blum Clip Top 107D Hinge Blumoton BL1736100 - Blum Clip M.Plate (As per Sample) | Blum | Junior Suite(New Dining Unit Shutter), Junior & GuestRooms Suites(Work Desk Shutters) | Junior Suite(New Dining Unit Shutter), Junior & GuestRooms Suites(Work Desk Shutters) | HHS | MKM |  |  | 2018-07-05 | 2018-07-10 | 5 | B | 0 | B | Sample Pieces are Approved Provide Mock-Up Sample for Our Review | 1 2 72
92 | MS-0165-0 |  | 0 | FURNITURE HARDWARE | SAMPLE |  |  |  | Hafele - Knob - Antique Brass - 118.06.116 | Hafele | Apartment - Work Desk Master Bedroom | Apartment - Work Desk Master Bedroom | HHS | MKM |  |  | 2018-07-05 | 2018-07-10 | 5 | C | 0 | SS | Provide actual physical sample for our review / approvals. | 1 2 72
93 | MS-0165-1 |  | 1 | FURNITURE HARDWARE | SAMPLE | SWA-600 |  |  | Furniture Hardware: Hafele - Knob : 118.06.116 - Antique Brass Finish (As per Sample) | Hafele | Apartment - Work Desk Master Bedroom | Apartment - Work Desk Master Bedroom | HHS | MKM |  |  | 2018-08-19 | 2018-08-26 | 7 | A | 0 | A | Sample piece is approved. All installation as per commented drawings. | 1 2 72
94 | MS-0167-0 |  | 0 | FURNITURE HARDWARE | SAMPLE | N/A |  |  | Furniture Handle: Simplex: 11.091.003X - Satin Brass Finish (As per Sample) | Simplex | 16th Floor Private Apartment @ Kitchen Pantyr Unit | 16th Floor Private Apartment @ Kitchen Pantyr Unit | HHS | MKM |  |  | 2018-07-31 | 2018-08-28 | 28 | A | 14 | A | Approved based on I.D/DGA confirmation -Email copy attached. | 1 2 72
95 | MS-0170-0 |  | 0 | FURNITURE HARDWARE | SAMPLE |  |  |  | Adjustable Shelf Pin Support - 282.01.701 Shelf Sleeve - 282.05.704 (As per Sample) | Hafele | Dining Unit @ Junior Suites Level 19th to 23rd | Dining Unit @ Junior Suites Level 19th to 23rd | HHS | MKM |  |  | 2018-08-13 | 2018-08-19 | 6 | C | 0 | SS | Too Fraige, need some stronger shelf supports. | 1 2 72
96 | MS-0170-1 |  | 1 | FURNITURE HARDWARE | SAMPLE | N/A |  |  | Expansion Shelf Support with Collar - 35XXB0900 Bolt with M4 thread for extractable bush - PRXMT040931 Options-01: Bianco White, Options-02: Nero Black (As per Sample) | Hafele | Dining Unit @ Junior Suites Level 19th to 23rd | Dining Unit @ Junior Suites Level 19th to 23rd | HHS | MKM |  |  | 2018-09-17 | 2018-10-08 | 21 | B | 7 | B | Black color sample approved for wooden shelf support. Contractor to provide mock up sample for our approvals. | 1 2 72
METAL | [26 empty] | PA
97 | MS-0007-00 |  | 0 | METAL | SAMPLE | MT 304 | POLISHED STAINLESS STEEL5X10 MM FOR LUGGAGE SHELVES |  | 1MM Thick Stainless Steel Mirror Finish (304 Grade) | YC INOX CO, LTD |  | Luggage Rack, Toilet Niche Frame | NAM | MKM |  |  | 2016-12-07 | 2016-12-07 | 0 | C | 0 | SS | Refer to email dated 07/12/16 Resubmit with sample boards, filled in check list & dividers | 1 2 76
98 | MS-0007-01 |  | 1 | METAL | SAMPLE | MT 304 | POLISHED STAINLESS STEEL5X10 MM FOR LUGGAGE SHELVES |  | 5MM THICK Stainless Steel Metal Inset Polished | YC INOX CO, LTD |  | Luggage Rack, Toilet Niche Frame | NAM | MKM |  |  | 2016-12-20 | 2017-01-08 | 19 | B | 5 | SS | 10X10mm THICK | 1 2 76
99 | MS-0007-02 |  | 2 | METAL | SAMPLE | MT 304 | POLISHED STAINLESS STEEL5X10 MM FOR LUGGAGE SHELVES |  | 10x10mm thick Stainless Steel Square Bar Grade-304 Metal Inset Satin Finished | YC INOX CO, LTD |  | Luggage Rack, Toilet Niche Frame | NAM | MKM |  |  | 2017-02-06 | 2017-02-12 | 6 | B | 0 | B | Rev-01 Comment complied. Both ends of inset steel need to be chanfered to prevent tearing of luggage. | 1 2 76
100 | MS-0025-00 |  | 0 | METAL | SAMPLE | N/A | POLISHED STAINLESS STEEL FOR TOILET NICHES CORNERS | Progress Profile | Proterminal Silver Anodised Aluminium Profile - PTAA10 | Progress Profile |  | Toilet Niches | NAM | MKM |  |  | 2017-01-25 | 2017-01-26 | 1 | D | 0 | SS | Please refer mockup. Profile to use must be "SS" with glossy chrome finish. Aluminium not acceptable. | 1 2 78
101 | MS-0025-01 |  | 1 | METAL | SAMPLE | RFI # 004 | POLISHED STAINLESS STEEL FOR TOILET NICHES CORNERS | Progress Profile | PROTERMINAL POLISHED CHROME ALUMINUM – PTBC10 | Progress Profile |  | Toilet Niches | NAM | MKM |  |  | 2017-03-02 | 2017-03-14 | 12 | D | 0 | SS | SUBMIT STAINLESS STEEL AS PER MOCK UP AND AS DISCUSSED WITH CAROLINE | 1 2 78
102 | MS-0025-02 |  | 2 | METAL | SAMPLE | RFI # 004 | POLISHED STAINLESS STEEL FOR TOILET NICHES CORNERS | Progress Profile | PROTERMINAL POLISHED CHROME ALUMINUM – PTOC10 | Progress Profile |  | Toilet Niches | NAM | MKM |  |  | 2017-03-21 | 2017-03-21 | 0 | D | 0 | SS | • While submitting revisions always attach previous comments (to be inserted right after the coversheet) • Follow previous revision comment, follow the mock-up and submit mirror finish stainless steel. • RFI-0004’s response provides the contact detail of dealer not the specification. | 1 2 78
103 | MS-0025-03 |  | 3 | METAL | SAMPLE | RFI # 004 | POLISHED STAINLESS STEEL FOR TOILET NICHES CORNERS | Progress Profile | PROTERMINAL POLISHED CHROME ALUMINUM – PTACM10 | Progress Profile |  | Toilet Niches | NAM | MKM |  |  | 2017-03-23 | 2017-03-27 | 4 | A | 0 | A | APPROVED | 1 2 78
104 | MS-0091-00 |  | 0 | METAL | SAMPLE |  | Metal Profile |  | PROJOLLY ECO - VINYL RESIN WHITE IVORY COLOR - REF# PJE 100106 | Progress Profile |  | Corner Beading at Maids Toilets | NAM | MKM |  |  | 2017-07-18 | 2017-07-19 | 1 | C | 0 | SS | FOR MAIDS TOILETS ONLY, SUBMIT SQUARE BREADING, SAME MATERIAL. | 1 2 78
105 | MS-0091-01 |  | 1 | METAL | SAMPLE | N/A | Metal Profile |  | PROJOLLY ECO - VINYL RESIN WHITE IVORY COLOR - REF# PJQ 100106 | Progress Profile |  | Corner Beading at Maids Toilets | NAM | MKM |  |  | 2017-07-23 | 2017-07-24 | 1 | B | 0 | B | * FOR MAID ROOM ONLY | 1 2 78
106 | MS-0087-00 |  | 0 | METAL | SAMPLE | N/A | MS ANGLE |  | MS ANGLE - (NATIONAL RED OXIDE PRIMER) | National Paint |  | Vanity Unit & WC Backwall | NAM | MKM |  |  | 2017-07-03 | 2017-07-04 | 1 | D | 0 | SS | • RED OXIDE PRIMER COATING NOT SUFFICIENT FOR CORROSION PROTECTION. • SUBMIT PROTECTIVE COATING COMPLYING TO TECHNICAL SPECIFICATION (REFER COMMENT IN MATERIAL INSPECTION MI-0049) • ALTERNATIVELY PROPOSE GI FRAME WORK. | 1 2 78 | AS PER HASSAN
107 | MS-0117-00 |  | 0 | METAL | SAMPLE |  | IMITATION GOLD LEAF - COLOUR 2.5 - BOX (BURNISHED BRASS) |  | PAINT FINISHED METAL: IMITATION GOLD LEAF - COLOUR 2.5 - BOX (BURNISHED BRASS) (As per Sample) | Decastelli / Giusto Manetti Battiloro | 16th Floor Private Apartment | 16th Floor Private Partment - Wall Panelling | NAM | MKM |  |  | 2018-02-07 | 2018-02-24 | 17 | C | 3 | SS | Colour application should match as per control sample. Gold paint finish burnish brass (Delabre Brass) | 1 2 78
108 | MS-0117-01 |  | 1 | METAL | SAMPLE | BR | IMITATION GOLD LEAF - COLOUR 2.5 - BOX (BURNISHED BRASS) |  | PAINT FINISHED METAL: IMITATION GOLD LEAF - COLOUR 2.5 - BOX (BURNISHED BRASS) (As per Sample) | Decastelli / Giusto Manetti Battiloro | 16th Floor Private Apartment | 16th Floor Private Partment - Wall Panelling | HHS | MKM |  |  | 2018-04-22 | 2018-04-29 | 7 | B | 0 | SS | Colour for the attached sample is good. But GLI should provide proper paint protection to avoid the peeling of paint. | 1 2 78
109 | MS-0117-02 |  | 2 | METAL | SAMPLE | BR | IMITATION GOLD LEAF - COLOUR 2.5 - BOX (BURNISHED BRASS) |  | PAINT FINISHED METAL: BURNISHED BRASS to match Control Sample received from MKM (As per Sample) | Decastelli / Giusto Manetti Battiloro | 16th Floor Private Apartment | 16th Floor Private Partment - Wall Panelling | HHS | MKM |  |  | 2018-09-17 | 2018-10-11 | 24 | B | 10 | B | The light color scratch should be more smaller & more random direction as per control sample. | 1 2 78
110 | MS-0124-00 |  | 0 | METAL | SAMPLE | WAPC-104 | Metal -AC Grill |  | Aluminium Fret Cut Design A/C Grill Frame Thickness: 12/20mm, Pattern Thickness: 6mm (Unfinished Sample to present the design only, Color WAPC-104 will be submitted separately) | Greenline Interiors | Atrium Wall Feature @ Apartments Atrium Corridor 8th Floor | Atrium Wall Feature @ Apartments Atrium Corridor 8th Floor | HHS | MKM |  |  | 2018-04-05 | 2018-04-29 | 24 | B | 10 | SS | Sample piece is approved, however its finishing to improve at joints, Provide fuill sample with right color. | 1 2 78
111 | MS-0124-01 |  | 1 | METAL | SAMPLE | WAPC-104 | Metal -AC Grill |  | Aluminium Fret Cut Design A/C Grill Frame Thickness: 12/20mm, Pattern Thickness: 6mm (Incorporation Previous Comments) | Greenline Interiors | Atrium Wall Feature @ Apartments Atrium Corridor 8th Floor | Atrium Wall Feature @ Apartments Atrium Corridor 8th Floor | HHS | MKM |  |  | 2018-07-11 | 2018-07-16 | 5 | C | 0 | SS | Color Finish to Match Control Sample Provided. | 1 2 78
112 | MS-0124-02 | ARK-0008 | 0 | METAL | SAMPLE | WAPC-104 | Metal -AC Grill |  | Aluminium Fret Cut Design A/C Grill Frame Thickness: 12/20mm, Pattern Thickness: 6mm (Incorporation Previous Comments) | Greenline Interiors | Atrium Wall Feature @ Apartments Atrium Corridor 8th Floor | Atrium Wall Feature @ Apartments Atrium Corridor 8th Floor | HHS | ARK |  |  | 2018-10-16 | 2018-10-25 | 9 | C | 0 | SS | Provide relevant documents inclusive of ID specs & its shop Drawings | 1 2 78 | AS PER HASSAN
113 | MS-0127-00 |  | 0 | METAL | SAMPLE | VM | Metal -Powder Coated |  | Metal (Powder Coating) Metal Aluminium- RAL 9005 (Black) (As per Sample) | Du Coats/Greenline |  | 16th Floor Private Apartment - Doors, Twin Bedroom Wardrobe, (Guest Restroom Mirror Frame), Living Room TV Cabinet | HHS | MKM |  |  | 2018-04-12 | 2018-04-29 | 17 | A | 3 | A | Approved as Specified from I.D. | 1 2 78 |  |  | PA
114 | MS-0128-00 |  | 0 | METAL | SAMPLE | MT1 | Metal -Powder Coated |  | Metal (Powder Coating) Metal Aluminium (Trim) - RAL 7006 | Du Coats/Greenline |  | 16th Floor Private Partment - Wall Panelling Bottom, Skirting & Top Shadow Gap Filler | HHS | MKM |  |  | 2018-04-12 | 2018-04-29 | 17 | A | 3 | A | Approved as Specified by I.D. RAL 7006 Beige Grey. | 1 2 78 |  |  | PA
115 | MS-0150-00 |  | 0 | METAL | SAMPLE | CI-0079_Rev.00 | Metal -Powder Coated |  | Metal Aluminum Flat Bar Powder Coated - Grey RAL 7024 (As per Sample) | Du Coats/Greenline |  | Apartment - Fridge Door Finger - Pull Gap in the Kitchen L-8 to L-17 | HHS | MKM |  |  | 2018-05-24 | 2018-05-29 | 5 | A | 0 | A | Sample piece is approved. Fixing design as per approved shop drawing. | 1 2 78 |  |  | PA
116 | MS-0151-00 |  | 0 | METAL | SAMPLE | BR | Brass metal finish to be used in replace of BR finish@ wet areas |  | Brushed Brass Finish Proposal to match BR Finish to use Only Where BR finish (Gold Leaf) is not feasable to use or apply, Please refer to below area of application. As per Sample) | Ultimate/Greenline | Private Apartment 1601 | Private Apartment 1601 - Metal Flooring divider strip, Glass shower channels, vanity mirror frame | HHS | MKM |  |  | 2018-05-24 | 2018-06-03 | 10 | B | 0 | B | Refer to the attached email from I.D/DGA, that the material submitted is approved for flooring profile divider only. | 1 2 78 |  |  | PA
117 | MS-0148-00 |  | 0 | METAL | SAMPLE |  | Metal- Dark Brass Finish |  | Metal: Dark Brass Finish | Classic Metal Coating LLC | Private Apartment 1601 | Private Apartment 1601 - Guest Rooms & Suites | HHS | MKM |  |  | 2018-05-28 | 2018-06-05 | 8 | C | 0 | SS | • Please submit private unit apartment separately from guest room & Suite • Location of use, material description are confusing & unacceptable. | 1 2 78 |  |  | PA
118 | MS-0148-01 |  | 1 | METAL | SAMPLE | SWGS - 111 & SWA - 111, WAPC - 104 | Metal- Dark Brass Finish |  | Metal: Dark Brass Finish | Classic Metal Coating LLC | Guest Rooms & Suites | Guest Rooms & Suites | HHS | MKM |  |  | 2018-06-04 | 2018-06-12 | 8 | B | 0 | B | Sample piece is approved. All installations to be in line with approved shop drawings. | 1 2 78 |  |  | PA
119 | MS-0173-00 | ARK-0003 | 0 | METAL | SAMPLE | WES-107 | Metal- Dark Brass Finish |  | Metal Dark Brass Finish - RN: 230518 (As per Technical Data) Note: Previously approved with MKM-05Q-IDP-01-MS-0148-01 | Classic Metal Coating LLC | 45th to 50th Floor Executive Suite - Joinery | 45th to 50th Floor Executive Suite - Joinery | HHS | ARK |  |  | 2018-09-26 | 2018-10-08 | 12 | C | 0 | SS | Contractor to provide attach ID spec/cut sheet along with their submittal along with its physical sample. | 1 2 78 |  |  | PA
120 | MS-0173-01 | ARK-0003 | 1 | METAL | SAMPLE | WES-107 WLC-101 | Metal- Dark Brass Finish |  | Metal Dark Brass Finish - RN: 230518 (As per Technical Data) Note: Previously approved with MKM-05Q-IDP-01-MS-0148-01 | Classic Metal Coating LLC | 45th to 50th Floor Executive Suite - Joinery | 45th to 50th Floor Executive Suite - Joinery | HHS | ARK |  |  | 2018-10-10 | 2018-10-22 | 12 | B | 0 | B | Contractor to follow same Material as approved earlier. Application as per approved shop drawing | 1 2 78 |  |  | PA
121 | MS-0183-00 | ARK-0014 | 0 | METAL | SAMPLE | WLC-101 | Metal- Dark Brass Finish |  | Metal Dark Brass Finish (Sample as previously approved with MKM-5Q-IDP-01-MS-0148-01 - Copy Attached) | Classic Metal Coating | Lift Car | Lift Car | LI | ARK |  |  | 2018-12-04 | 2018-12-22 | 18 | B | 4 | B | Sample piece approved earlier. All applications to be inline with ID Specs/Drawings. | 1 2 78 |  |  | PA
FABRIC / LEATHER UPHOLSTRY | [26 empty] | PA
122 | MS-0052-0 |  | 0 | FABRIC | SAMPLE | FB 210 | KIRBY APOLLO FR CLAY - KB 5035/05, 450gsm, 60%POLYESTER-40%PU, FIRE RETARDANT: BS5828 PART 1 IGNITION 0 CIGARETTE TEST AND 1 MATCH TEST |  | SYNTHETIC LEATHER ART T71A0603 COLOUR#R (AS PER SAMPLE) | Texomode |  | FABRIC FOR HEADBOARD, DRAWER AND CABINET FACE @ ALL ROOM TYPES | NAM | MKM |  |  | 2017-03-08 | 2017-03-13 | 5 | D | 0 | SS | Incomplete submittal, material don’t comply with specified fire retardant test certificate as per ID specification required. | 1 2 81
123 | MS-0052-1 |  | 1 | FABRIC | SAMPLE | FB 210 | KIRBY APOLLO FR CLAY - KB 5035/05, 450gsm, 60%POLYESTER-40%PU, FIRE RETARDANT: BS5828 PART 1 IGNITION 0 CIGARETTE TEST AND 1 MATCH TEST |  | SYNTHETIC LEATHER ART T71A0603 COLOUR#R (AS PER SAMPLE) | Texomode |  | FABRIC FOR HEADBOARD, DRAWER AND CABINET FACE @ ALL ROOM TYPES | NAM | MKM |  |  | 2017-05-29 | 2017-06-29 | 31 | D | 17 | SS | COLOR NOT MATCHING. OVERALL FINISH & LOOK NOT MATCHING. ALTERNATIVE SAMPLE REJECTED. | 1 2 81
124 | MS-0052-2 |  | 2 | FABRIC | SAMPLE | FB 210 | KIRBY APOLLO FR CLAY - KB 5035/05, 450gsm, 60%POLYESTER-40%PU, FIRE RETARDANT: BS5828 PART 1 IGNITION 0 CIGARETTE TEST AND 1 MATCH TEST |  | SYNTHETIC LEATHER ART T71A0603 COLOUR#R (AS PER SAMPLE) | Texomode |  | FABRIC FOR HEADBOARD, DRAWER AND CABINET FACE @ ALL ROOM TYPES | NAM | MKM |  |  | 2017-07-19 | 2017-07-20 | 1 | D | 0 | SS | • Previous comments not addressed. • Test certificate attached for alternative proposal is not related to the material proposed, nor is tested as per applicable standard. • Submit final product only, with test certificate equivalent to specified. • Refer comments inside. | 1 2 81
125 | MS-0052-4 |  | 4 | FABRIC | SAMPLE | FB 210 | KIRBY APOLLO FR CLAY - KB 5035/05, 450gsm, 60%POLYESTER-40%PU, FIRE RETARDANT: BS5828 PART 1 IGNITION 0 CIGARETTE TEST AND 1 MATCH TEST |  | (2 Options) Art ref: A17/2019, Width: 140cm, Composition: PU/PVC, FR Standard: BS 5852 Part1 | Warps & Wefts |  | FABRIC FOR HEADBOARD, DRAWER AND CABINET FACE @ ALL ROOM TYPES | NAM | MKM |  |  | 2017-09-28 | 2017-10-05 | 7 | D | 0 | SS | INCOMPLETE SUBMISSION. • SPECIFICATION NOT ATTACHED • PREVIOUS COMMENTS NOT ATTACHED. • PREVIOUS COMMENTS NOT ADDRESSED. • MANUFACTURER’S DATA SHEET NOT ATTACHED. • AS PREVIOUSLY MENTIONED SEVERAL TIMES SUPPLIER’S SELF-CERTIFICATION WILL NOT CONSIDERED AS A VALID CERTIFICATION. | 1 2 81
126 | MS-0052-5 |  | 5 | FABRIC | SAMPLE | FB 210 | KIRBY APOLLO FR CLAY - KB 5035/05, 450gsm, 60%POLYESTER-40%PU, FIRE RETARDANT: BS5828 PART 1 IGNITION 0 CIGARETTE TEST AND 1 MATCH TEST |  | (2 Options) Art ref: A17/2019, Width: 140cm, Composition: PU/PVC, FR Standard: BS 5852 Part1 | Warps & Wefts |  | FABRIC FOR HEADBOARD, DRAWER AND CABINET FACE @ ALL ROOM TYPES | NAM | MKM |  |  | 2017-11-28 | 2017-12-20 | 22 | D | 8 | SS | The material is not as per the requirement or specs. | 1 2 81 | As per Hassan
127 | MS-0017-00 |  | 0 | FOAM | SAMPLE | N/A | 40KG DENSITY FR FOAM PAD 20mm THICK |  | 20mm thick 40KG Density, Fire Retardent Polyurethene Foam Pad (PUF 40N - FR) | Three Star |  |  | NAM | MKM |  |  | 2017-01-02 | 2017-01-10 | 8 | B | 0 | B | Test Report required from local authority approved laboratory. | 1 2 86
128 | MS-0042-00 |  | 0 | FABRIC | SAMPLE | FB 232 | UPHOLSTERY FABRIC BNS 78923-26 WIDTH : 138 COMPOSITION : 100% POLYSTER IFR (SAMPLE AS SPECIFIED) |  | UPHOLSTERY FABRIC BNS 78923-26 WIDTH : 138 COMPOSITION : 100% POLYSTER IFR (SAMPLE AS SPECIFIED) | Atelier - Italy |  | FABRIC WALL PANELS / GUEST ROOM CORRIDORS (19TH - 41ST FLOOR) | NAM | MKM |  |  | 2017-02-20 | 2017-02-21 | 1 | B | 0 | B | LEVEL 19 TO 50 – GUESTROOM CORRIDORS. | 1 2 86
129 | MS-0102-00 |  | 0 | FABRIC | SAMPLE | F01 | Fabric: Jasper Col. 07 Latte | DEDAR | Fabric: Jasper Col. 07 Latte (Sample from Specified Source) | DEDAR |  | WALL CLADDING 1 - 216TH FLOOR APARTMENT | NAM | MKM |  |  | 2017-12-19 | 2018-01-31 | 43 | SS | 29 | SS | *No fire test certificate attached. *Material as per spec is correect. (Code is approved) *Submit with fire test certificate for approval. | 1 2 86
130 | MS-0102-01 |  | 1 | FABRIC | SAMPLE | F01 | Fabric: Jasper Col. 07 Latte | DEDAR | Fabric: Jasper Col. 07 Latte (Sample from Specified Source) | DEDAR |  | WALL CLADDING 1 - 216TH FLOOR APARTMENT | NAM | MKM |  |  | 2018-02-15 | 2018-02-24 | 9 | B | 0 | B | Aproved with Comments. FR certificate will be submitted during material inspection as per Dedar letter re: Prj#1252 dated 12 Feb 2018. | 1 2 86 |  |  | PA
131 | MS-0103-00 |  | 0 | FABRIC | SAMPLE | F02 | Fabric: Flushy Col. 108 Neve | DEDAR | Fabric: Flushy Col. 108 Neve (Sample from Specified Source) | DEDAR |  | WALL CLADDING 2 - 216TH FLOOR APARTMENT | NAM | MKM |  |  | 2017-12-19 | 2018-01-31 | 43 | SS | 29 | SS | *Code / Sample correct as per spec. *No fire test certificate attached, submit fire test certificates for approval. | 1 2 86 |  |  | PA
132 | MS-0103-01 |  | 1 | FABRIC | SAMPLE | F02 | Fabric: Flushy Col. 108 Neve | DEDAR | Fabric: Flushy Col. 108 Neve (Sample from Specified Source) | DEDAR |  | WALL CLADDING 2 - 216TH FLOOR APARTMENT | NAM | MKM |  |  | 2018-02-15 | 2018-02-24 | 9 | B | 0 | B | Aproved with Comments. FR certificate will be submitted during material inspection as per Dedar letter re: Prj#1252 dated 12 Feb 2018. | 1 2 86 |  |  | PA
133 | MS-0104-00 |  | 0 | FABRIC | SAMPLE | MEM | Fabric: Memory 143, Ref-1232 | DEDAR | Fabric: Memory 143, Ref-1232 (Sample from Specified Source) | DEDAR |  | TV Paneling & Behind Twin Beds - 16th Floor Apartment | NAM | MKM |  |  | 2017-12-19 | 2018-01-31 | 43 | A | 29 | A | Approved. | 1 2 86 |  |  | PA
134 | MS-0107-00 |  | 0 | FABRIC | SAMPLE | SWA-319F SWA-327F | Fabric: Cotton - Confetti - Book 125, SRL # 17, W=140cm |  | Fabric: Cotton - Confetti - Book 125, SRL # 17, W=140cm (To be treated with FR & SR, certificate upon final delivery) (As per Data Sheet) | York Trading / Al Sahara | Bed Base - Secondary (Twin & King) | Bed Base - Secondary (Twin & King) | NAM | MKM |  |  | 2018-01-18 | 2018-01-21 | 3 | B | 0 | B | Material is approved as procured from specified supplier. To submit all original certificates upon its procurement. | 1 2 86
135 | MS-0107-01 | ARK-0017-00 | 1 | FABRIC | SAMPLE | SWA-319F SWA-327F | Fabric: Cotton - Confetti - Book 125, SRL # 17, W=140cm |  | Fabric: option1: Cotton - Zen-Book # 223, SRL# 01 Option 2: Cotton - Zec - Book# 223, SRL# 07 (As per Sample) | York Trading | Bed Base - Secondary (Twin & King) | Bed Base - Secondary (Twin & King) | HS | MKM |  |  | 2019-07-18 | 2019-07-30 | 12 | A | 0 | A | Option - 1: Cotton - Zen - Book # 223, SRL # 01. Approved for 319/F & 327/F. | 1 2 86
136 | MS-0112-00 |  | 0 | LEATHER | SAMPLE | SWA-310F | Leather: Iman 72760, Col: 9920, Width: 140cm |  | Leather: Iman 72760, Col: 9920, Width: 140cm (As per Data Sheet) | Housles |  | Master Bedroom - Master Bedbase | NH | MKM |  |  | 2018-01-18 | 2018-01-21 | 3 | SS | 0 | SS | Material is approved as procured from specified supplier. Submit original certificates upon its procurement. | 1 2 103
137 | MS-0112-01 |  | 1 | LEATHER | SAMPLE | SWA-310F | Leather: Iman 72760, Col: 9920, Width: 140cm |  | Leather: Iman 72706, Col: 9920, Width: 140cm (As per Data Sheet) | Housles |  | Master Bedroom - Master Bedbase | NH | MKM |  |  | 2018-01-25 | 2018-01-28 | 3 | B | 0 | B | Material is Approved as procured from specified supplier. To submit Original Certificates upon its procurement. | 1 2 103
138 | MS-0113-00 |  | 0 | LEATHER | SAMPLE | SWA-309F | Bridgestone, Col-54, Width: 140cm (FR Inherent) |  | Leather: Bridstone, Col-52, Width: 140cm (FR Inherent) (As per Data Sheet) | Lugano Trading |  | Master Bedroom 901 - Head Board | NH | MKM |  |  | 2018-01-18 | 2018-01-21 | 3 | SS | 0 | SS | Please ensure correct material is procured as color codes don’t match. | 1 2 103
139 | MS-0113-01 |  | 1 | LEATHER | SAMPLE | SWA-309F | Bridgestone, Col-54, Width: 140cm (FR Inherent) |  | Leather: Bridgestone, Col-54, Width: 140cm (FR Inherent) (As per Data Sheet) | Lugano Trading |  | Master Bedroom 901 - Head Board | NH | MKM |  |  | 2018-01-25 | 2018-01-28 | 3 | B | 0 | B | Material is Approved as procured from specified supplier. To submit Original Certificates upon its procurement. | 1 2 103
140 | MS-0118-00 |  | 0 | LEATHER | SAMPLE | SWGS-300F | Ultimate Touch 155 Duck Egg |  | Leather: Ultimate Touch 155 Duck Egg (As per Data Sheet) | JAB |  | Mock Up Room (Guestrooms) & Suites - Head Board | NH | MKM |  |  | 2018-02-08 | 2018-02-13 | 5 | B | 0 | B | Material is approved as procured from specified supplier. Verify its right color. | 1 2 103
141 | MS-0157-00 |  | 0 | LEATHER | SAMPLE | SWA-318F SWA-326F | Faux Leather for Headboard |  | Leather: Faux Leather Headboard (As per Data Sheet) | Collezione Cesaro |  | SWA-318 Headboard 3BR Secondary Bedroom (King) SWA-326 Headboard 2BR & 3BR Secondary Bedroom (Twin) | HH | MKM |  |  | 2018-06-21 | 2018-06-26 | 5 | B | 0 | B | Material approved as procured from ID specified supplier & specs to provide original certificate upon its procurement. | 1 2 103
142 | MS-0161-00 |  | 0 | LEATHER | SAMPLE | RFI Ref:0113-00 | Faux Leather for Drawer |  | Faux Leather: OPTION 1: Collection: Wild West, Design: Tannery, Col. 12-Brindle OPTION 2: Collection: UV & FR Quality Synthetic Leather, Item Ref # H478 OPTION 3: Collection: UV & FR Quality Synthetic Leather, Item Ref # H477 (As per Sample) | Antic-Cuir/'Option-1: Silkland / Option-2&3: Al Reyami |  | Private Apartment 1601 Twin Dressing Room - Faux Leather for Inside Drawer | HH | MKM |  |  | 2018-06-27 | 2018-07-03 | 6 | A | 0 | A | Approved. Option 2 by I.D/DGA. | 1 2 103
143 | MS-0166-00 |  | 0 | LEATHER | SAMPLE |  | Faux Leather for Drawer |  | Faux Leather: Collection: UV & FR Quality Synthetic Leather, Item Ref # H478 | Al Reyami |  | Master Bedroom Faux Leather for Inside Drawer | HH | MKM |  |  | 2018-07-29 | 2018-10-08 | 71 | A | 57 | A | Approved as per I.D confirmation item Ref # H478. | 1 2 103
144 | MS-0164-00 |  | 0 | LEATHER | SAMPLE | SWGS-301F SWGS-316F | Leather for Bed Base |  | Leather: Leather Bed Base (As per Data Sheet) | Collezione Cesaro |  | SWGS-301 Bed Base (King Size) Junior & Guestroom Suite SWGS-316 Bed Base (Twin Size) Junior & Guest Room Suite | HH | MKM |  |  | 2018-06-27 | 2018-07-01 | 4 | B | 0 | B | Material is approved as from specified supplier & in line with ID specs. Provide original certificate upon its procurement. | 1 2 103
GYPSUM CEILINGS & PAINT | [26 empty] | PA
145 | MS-0005-00 |  | 0 | GYPSUM BOARD | SAMPLE | 09952 | STANDARD GYPSUM BOARD 12.5mm FOR FRY AREAS |  | Complete set of Knauf 12.5mm Thick Gypsum Board Material (Regular & MR) with Suspension System including Accessories and Fastening Devices | Knauf |  | Ceiling - Wherever Applicable | NAM | MKM |  |  | 2016-12-05 | 2016-12-07 | 2 | C | 0 | SS | Submit sample boards - 3 sets refer to email dated 07/12/16 | 1 2 92
145 | MS-0005-01 |  | 0 | GYPSUM BOARD | SAMPLE | 09952 | STANDARD GYPSUM BOARD 12.5mm FOR FRY AREAS |  | Complete set of Knauf 12.5mm Thick Gypsum Board Material (Regular & MR) with Suspension System including Accessories and Fastening Devices | Knauf |  | Ceiling - Wherever Applicable | NAM | MKM |  |  | 2017-01-02 | 2017-01-10 | 8 | A | 0 | A |  | 1 2 92
146 |  |  | 0 | GYPSUM BOARD | SAMPLE |  | MR GYPSUM BOARD 12.5mm FOR WET AREAS | [12 empty] | FI |  | FI | Refer to MS-0005 | 1 2 93
147 | MS-0011-00 |  | 0 | ACCESS PANEL | SAMPLE | 09952 | ACCESS PANEL |  | CEILING ACCESS PANEL 45x45 | BMG |  | Ceiling - Wherever Applicable | NAM | MKM |  |  | 2017-01-02 | 2017-01-10 | 8 | D | 0 | SS | -Submit gyproc or acceptable equivalent (Knauf etc) -Submitted Test report is for gypsum board only, from different manufacturer, different country of origin. Not Relevant. | 1 2 93
148 | MS-0011-01 |  | 0 | ACCESS PANEL | SAMPLE | 09952 | ACCESS PANEL |  | CEILING ACCESS PANEL 30X30 | Knauf |  | Ceiling - Wherever Applicable | NAM | MKM |  |  | 2017-01-25 | 2017-01-25 | 0 | A | 0 | A |  | 1 2 93
149 | MS-0095-00 |  | 0 | ACCESS PANEL | SAMPLE |  | ACCESS PANEL |  | Access Panels - Knauf (MR) 1 - Size: 800 x 1000mm 2 - Size: 900 x 1100mm | Knauf/Technocraft |  | 1 - (Area 1, 2 Bedroom, Studio A&B) Master Bathroom 8th, 9th 10th Floor & Apt 1102, 1103, 1104 2 - (Area - 3 Bedroom) Master Bathroom, 8th, 9th, 10 floor & Apt 1101 | NAM | MKM |  |  | 2017-08-17 | 2017-08-21 | 4 | D | 0 | SS | INCOMPLETE SUBMITTAL. MATERIAL PREVIOUSLY SUBMITTED AS MS-0011 (ATTACHED). MS-0011 REV-00 COMMENTS NOT COMPLIED. TECHNICAL SPECIFICATION COMPLIANCE NOT PROVIDED. | 1 2 93
150 | MS-0095-01 |  | 1 | ACCESS PANEL | SAMPLE |  | ACCESS PANEL |  | Access Panels - Knauf (MR) 1 - Size: 800 x 1000mm 2 - Size: 900 x 1100mm | Technocraft |  | 1 - (Area 1, 2 Bedroom, Studio A&B) Master Bathroom 8th, 9th 10th Floor & Apt 1102, 1103, 1104 2 - (Area - 3 Bedroom) Master Bathroom, 8th, 9th, 10 floor & Apt 1101 | NAM | MKM |  |  | 2017-08-30 | 2017-09-07 | 8 | C | 0 | SS | • SUBMIT JUSTIFICATION FOR ALTERNATIVE LETTER FROM APPROVED MANUFACTURER THAT MENTIONED SIZES ARE NOT AVAILABLE. • SUBMIT SAMPLE TO CHECK OPERATION | 1 2 93
151 | MS-0095-02 |  | 2 | ACCESS PANEL | SAMPLE | 09952 | ACCESS PANEL |  | Access Panels - Knauf (MR) 1 - Size: 800 x 1000mm 2 - Size: 900 x 1100mm | Technocraft |  | 1 - (Area 1, 2 Bedroom, Studio A&B) Master Bathroom 8th, 9th 10th Floor & Apt 1102, 1103, 1104 2 - (Area - 3 Bedroom) Master Bathroom, 8th, 9th, 10 floor & Apt 1101 | NAM | MKM |  |  | 2017-10-05 | 2017-10-12 | 7 | B | 0 | B | * ACCESS PANEL IS APPROVED AS PER ATTACHED SAMPLE. KEEP THE SAMPLE WITH MKM AS CONTROL SAMPLE. * GYPSUM BOARD SHOULD BE MR (MOIST RESISTANT) | 1 2 93
152 | MS-0041-0 |  | 0 | METAL | SAMPLE | N/A | Ceiling Edge Profile |  | Aluminium F Profile (Powder coated Mill finished) | TMI |  | Apt-Guest Room Corridor Ceiling | RK | MKM |  |  | 2017-02-09 | 2017-02-12 | 3 | B | 0 | B | Location drawing not attached. Assure it is for edge shadow gap. | 1 2 76
153 | MS-0006-00 |  | 0 | WALL PAINT | SAMPLE | PT 600 PT 601 PT 603 | BACKWALL AND CEILING FENOMASTIC PAINT, JOTUN S 0500N |  | Acrylic Emulsion Paint System including Primer & Stucco Colour Reference (RAL) sample to be submitted separately. | Jotun |  | Ceiling & Walls - Wherever Applicable | NAM | MKM |  |  | 2016-12-07 | 2016-12-28 | 21 | B | 7 | SS | - MANUFACTURER OF PRODUCT APPROVED, PROVIDE SAMPLE BOARDS FOR COLOR/TEXTURE CONFIRMATION. - CHECKLIST MISSING, BOQ, DRAWING MISSING. | 1 2 94 | As per Hassan
154 | MS-0046-00 |  | 0 | WALL PAINT | SAMPLE | PT-600 SWA-104 SWA-105 SWGS-104 SWGS-105 | Fenomastic Emulsion Paint |  | Fenomastic Emulsion Matt - S0500-N | Jotun |  | Ceiling & Walls - Guestroom Corridor | NAM | MKM |  |  | 2017-02-23 | 2017-03-06 | 11 | A | 0 | SS | APPROVED | 1 2 94
155 | MS-0046-01 |  | 1 | WALL PAINT | SAMPLE | SWA-104 SWA-105 | Fenomastic Emulsion Paint |  | Fenomastic Emulsion Matt - S0500-N (Subject to previous approval) | Jotun |  | Ceiling & Walls - Guestroom Corridor | HHS | MKM |  |  | 2018-06-28 | 2018-07-04 | 6 | A | 0 | A | Material is approved as confirmed earlier. | 1 2 94
156 | MS-0172-00 | ARK-0002 | 0 | WALL PAINT | SAMPLE | WES-104 WES-105 WES-104.1 WES-105.1 | Fenomastic Emulsion Paint |  | Paint: Fenomastic Emulsion Matt - S0500-N (As per Technical Data) Note: Previously approved with MKM-05Q-IDP-01-MS-0046-01 | Jotun |  | 45th to 50th Floor Executive Suite - Walls and Ceiling / Wall & Ceiling @ Bathroom | HHS | ARK |  |  | 2018-09-26 | 2018-10-08 | 12 | C | 0 | SS | Contractor to provide attach ID spec/cut sheet along with their submittal along with its physical sample. | 1 2 94
157 | MS-0172-01 | ARK-0002 | 1 | WALL PAINT | SAMPLE | WES-104 WES-105 WES-104.1 WES-105.1 | Fenomastic Emulsion Paint |  | Paint: Fenomastic Emulsion Matt - S0500-N (As per Technical Data) Note: Previously approved with MKM-05Q-IDP-01-MS-0046-01 | Jotun |  | 45th to 50th Floor Executive Suite - Walls and Ceiling / Wall & Ceiling @ Bathroom | HHS | ARK |  |  | 2018-10-10 | 2018-10-22 | 12 | B | 0 | B | Material is approved. Application procedure to be as per previous approved samples | 1 2 94
158 | MS-0047-00 |  | 0 | WALL PAINT | SAMPLE | PT-603, S/230/10 | Fenomastic Emulsion Paint |  | Fenomastic Emulsion Matt - S0502-G | Jotun |  | Ceiling - Standard Room and Executive Room | NAM | MKM |  |  | 2017-02-23 | 2017-03-06 | 11 | A | 0 | SS | APPROVED | 1 2 94 | As per Hassan
159 | MS-0048-00 |  | 0 | WALL PAINT | SAMPLE | PT-604, S/230/10 | Fenomastic Emulsion Paint |  | Fenomastic Emulsion Matt - S1000-N | Jotun |  | Wall - Standard Room and Executive Room | NAM | MKM |  |  | 2017-02-23 | 2017-03-06 | 11 | A | 0 | SS | APPROVED | 1 2 94 |  | As per Hassan
160 | MS-0050-00 |  | 0 | WALL PAINT | SAMPLE | PT 602 | PAINT FINISH MAMORINO - METALLIC EFFECT - PEGASUS COLOR-METALLIC TOP-COPPER BRONZE+SILVER |  | Decorative Paint Marmorino Venezia, Giallo Polished Plaster | Pegasus |  | Accent Wall to TV unit | NAM | MKM |  |  | 2017-02-23 | 2017-02-26 | 3 | A | 0 | SS | APPROVED | 1 2 95 |  | As per Hassan
161 | MS-0006-00 |  | 0 | WALL PAINT | SAMPLE | PT 603 | CEILING PAINT, FENOMASTIC, JOTUN S 0502G -04-A1/10-C1 | [12 empty] | FI |  | FI | Refer to MS-0006 | 1 2 96
162 | MS-0006-00 |  | 0 | WALL PAINT | SAMPLE | PT 604 | WALL PAINT, FENOMASTIC, JOTUN S 1000N-05 A6 | [12 empty] | FI |  | FI | Refer to MS-0006 | 1 2 97
163 | MS-0071-00 |  | 0 | WALL PAINT | SAMPLE | PT 603 | Fenomastic Matt Emulsion Paint color off white RAL#9010, Wall & Seiling. |  | Fenomastic Matt Emulsion Paint color off white RAL#9010, Wall & Seiling. |  | Walls & Seilings (wherever apppicable) |  | NAM | MKM |  |  | 2017-04-19 | 2017-04-24 | 5 | A | 0 | SS | APPROVED | 1 2 95 | As per Hassan
164 | MS-0093-00 |  | 0 | PAINT | SAMPLE | N/A | Jotun - Jotamastic Smart Pack |  | Jotun - Jotamastic Smart Pack |  | Steel Structure Vanity Unit |  | NAM | MKM |  |  | 2017-08-01 | 2017-08-08 | 7 | B | 0 | B | SUBMIT CONTROL SAMPLES COATED WITH SUBJECT PRODUCT – SAMPLE RECEIVED ON 07-08-17 | 1 2 95
165 | MS-0087A-00 |  | 0 | RAW MATERIAL | SAMPLE |  | NAILS |  | HILTI NAILS - X-CC U27 P8 | HILTI | Guest Room Ceiling and Corridor Ceiling Suspension |  | NAM | MKM |  |  | 2017-07-12 | 2017-07-12 | 0 | D | 0 | SS | NOT SUITABLE FOR SUBJECT PURPOSE | 1 2 95 | As per Hassan
166 | MS-0092-00 |  | 0 | GRG | SAMPLE |  | Gypsum Casting Elements (GRG) |  | Gypsum Casting Elements (GRG) | Golden Line | Corridor Atrium & Cove Light and Wherever Applicable |  | NAM | MKM |  |  | 2017-07-22 | 2017-07-24 | 2 | C | 0 | SS | • PRECAST GYPSUM CONCEPT APPROVED. • SUBMITTED ITEM IS NOT GRG (GLASS REINFORCED GYPSUM) AS GLASS FIBERS ARE NOT USED. • ARRANGE MEETING WITH TECHNICAL PERSON FOR MANUFACTURER. • METHOD STATEMENT TO BE SUBMITTED SEPARATELY. | 1 2 95
167 | MS-0092-01 |  | 1 | GRG | SAMPLE | N/A | Gypsum Casting Elements (GRG) |  | Precast Gypsum | Golden Line | Corridor Atrium & Cove Light |  | NAM | MKM |  |  | 2017-08-02 | 2017-08-08 | 6 | B | 0 | B | • DRAFT WARRANTY PERIOD CHANGED IN REV-01, NOT ACCEPTABLE, TO FOLLOW REV-00. • MATERIAL SPECIFICATION SHEET IS INCORRECT, SOURCE OF DATA NOT MENTIONED. • SAMPLE APPROVED, FIBER TO BE PLACED IN THE CENTER. • PARODIC TESTING REQUIRED | 1 2 95
168 | MS-0122-00 |  |  | Wall Finish | SAMPLE |  | Rendered Wall Finish |  | Rendered Wall Finish - Decorative Option 1 - Ref# P00411 Option 2 - Ref# P00412 | Al Zubaidi Modern Decorative | Apartments |  | NAM | MKM |  |  | 2018-04-05 | 2018-04-11 | 6 | D | 0 | SS | As per Client's instructions, specialist paint is now replaced by wall paper. Find attached revised ID specs. | 1 2 95
169 | MS-0122-01 |  |  | Wall Finish | SAMPLE | SWA-101 | Rendered Wall Finish |  | Premierwall Urban, Item Ref: PUR7344, Roll Size: 130cm x 35m | Goodrich Global | Apartments | TV Wall @ Living Room | HH | MKM |  |  | 2018-06-19 | 2018-06-24 | 5 | B | 0 | B | Material is approved as procured form specified supplier & in line with ID specs/Finishes. | 1 2 95
WALLCOVERING | [26 empty] | PA
170 | MS-0049-00 |  | 0 | WALL COVERING | SAMPLE | WP 605 | MURASPEC - UNION - CELESTE A2A33 |  | WALL COVERING: NEWMOR ART.REF.: PP NEW EX 02.17.01 COLOUR BEIGE (AS PER SAMPLE) | Newmor |  | BEDROOM AND LIVING ROOM (19TH TO 23RD FLOOR) | NH | MKM |  |  | 2017-02-27 | 2017-03-06 | 7 | D | 0 | SS | COLOR & PATTERN EFFECT NOT MATCHING TEAR RESISTANCE IS WEAK. | 1 2 99
171 | MS-0049-01 |  | 1 | WALL COVERING | SAMPLE | WP 605 | MURASPEC - UNION - CELESTE A2A33 |  | WALL COVERING: Art Ref- WQ10281C, Width: 137cm, Composition: Custom made Vinly Wallpaper in Paperback (AS PER SAMPLE) | Wall Quest / NGC Nafees |  | BEDROOM AND LIVING ROOM (19TH TO 23RD FLOOR) | NH | MKM |  |  | 2017-09-28 | 2017-11-06 | 39 | D | 25 | SS | USE ORIGINALLY SPECIFIED ITEM. FROM MURASPEC | 1 2 99 | As per Hassan
172 | MS-0061-00 |  | 0 | WALL COVERING | SAMPLE | WP 606 | MURASPEC - MUREK - NUREY 04A16, PAPER BACKED |  | WALL COVERING: NEWMOR ART.REF.: PP NEW EX 02.17.35 (AS PER SAMPLE) | Newmor |  | APARTMENTS - ACCENT WALL BEHIND HEADBOARDS | NH | MKM |  |  | 2017-03-19 | 2017-03-22 | 3 | D | 0 | SS | • TEXTURE, SHINE & TEAR RESISTANCE NOT MATCHING WITH SPECIFIED. • AS DISCUSSED WITH CAROLINE. | 1 2 100 | As per Hassan
173 | MS-0062-00 |  | 0 | WALL COVERING | SAMPLE | WP 607 | OMEXCO ETERNITY ET 2002, AGED BEIGE, MATT FINISH, 1mm THICK |  | WALL COVERING: NEWMOR ART.REF.: PP NEW 03.17.01 (AS PER SAMPLE) | Newmor |  | STD. ROOM & EXE.ROOM - HEADBOARD ACCENT WALL | NH | MKM |  |  | 2017-03-19 | 2017-03-22 | 3 | C | 0 | SS | • DESIGN OF PROPOSED PRODUCT IS MATCHING WITH SPECIFIED PRODUCT BUT LARGER SAMPLE AND LESS SHINING REQUIRED TO CONFIRM. • TEAR RESISTANCE IS LOWER THAN SPECIFIED. | 1 2 101
174 | MS-0062-01 |  | 1 | WALL COVERING | SAMPLE | WP 607 | OMEXCO ETERNITY ET 2002, AGED BEIGE, MATT FINISH, 1mm THICK |  | WALL COVERING: ACCENT-HEAD BOARD.REF.: OMEXCO - ETERNITY ET 202 (SAMPLE AS SPECIFIED ) | Newmor |  | STD. ROOM & EXE.ROOM - HEADBOARD ACCENT WALL | NH | MKM |  |  | 2017-04-10 | 2017-04-23 | 13 | C | 0 | SS | WP-607 IS TO BE REPLACED WITH WP-612 USED ON WALLS IN GUEST ROOM STANDARD / EXECUTIVE. | 1 2 101 | As per Hassan
175 | MS-0063-00 |  | 0 | WALL COVERING | SAMPLE | WP 612 | OMEXCO NV - HOR1114, BEIGE, ON NON WOVEN BACKING |  | WALL COVERING: NEWMOR ART.REF.: DP NEW UK 02.17.65A (AS PER SAMPLE) | Newmor |  | STD. ROOM & EXE.ROOM - BEDROOM & LIVING ROOM | NH | MKM |  |  | 2017-03-19 | 2017-03-22 | 3 | D | 0 | SS | • TEXTURE, SHINE NOT MATCHING. • MATERIAL QUALITY IS LOWER THAN SPECIFIED. • TEAR RESISTANCE IS LESS. | 1 2 102 | As per Hassan
176 | MS-0068-00 |  | 0 | WALL COVERING | SAMPLE | WP 614 | MURASPEC - CHANCERY - TESSAI 03A83 |  | WALL COVERING: MURASPEC - CHANCERY - TESSAI 03A83 (AS PER SAMPLE) | Muraspec |  | 8th to 17th Floor - TV Units | NH | MKM |  |  | 2017-04-09 | 2017-04-11 | 2 | A | 0 | SS |  | 1 2 103 | As per Hassan
177 | MS-0108-00 |  | 0 | WALL COVERING | SAMPLE | WP 620 | SQUISITO - ARTE NOCTIS - REF.38154, CREAM/BEIGE, NATURAL EFFECT |  | Wall Paper: Option 1: Prisma - Concorde KIP40470 - Width - 130cm Option 1: Prisma - Concorde KIP40471 - Width - 130cm (As per Sample) | Arte |  | Walls - Corridor 8 to 23 |  |  |  |  | 2018-01-21 | 2018-02-04 | 14 | C | 0 | SS | The material is not complied with the earlier comments. Corridors spec revised by WAI. MKM will issue new drawings & new specs for corridor wallpaper shortly. Submit wallpaper material as per new spec & details. | 1 2 104 | As per Hassan
178 | MS-0162-00 |  | 0 | WALL COVERING | SAMPLE | WAPC-108 | ARTE NOCTIS COLLECTION - MIRA - REFERENCE 38154 | SQUISITO | Item Ref: BNS 78923-26, FR Standards: CA117 (2 layered 260 cm) (Submitted material as per verbal agreement of higher management) | Cebu Fil-Veneer Corporation/Atelier-A |  | Wallpaper @ Corridor Walls / Corridor Walls at 8th – 17th floors | HH | MKM |  |  | 2018-06-25 | 2018-07-17 | 22 | A | 8 | A | As discussed with higher management, it is approved. Note; Should be same material as L-19 to L41 levels, but only change in the colored. | 1 2 104
179 | MS-0114-00 |  | 0 | WALL COVERING | SAMPLE | WP | Wall Paper: |  | Wall Paper: Veneto 2616.41, Width: 137cm (As per Sample) | Vescom | 16th Floor Apartment | Dressing Room @ Twin Bedroom Behind the Wardorbe |  |  |  |  | 2018-02-04 | 2018-02-24 | 20 | B | 6 | B | Aproved with comments. Make sure to comply with (FR) Fire Retardant. | 1 2 104 |  |  | PA
180 | MS-0109-00 |  | 0 | WALL COVERING | TECHNICAL DATA | SWA-109 | Wall Paper: |  | Wall Paper: J. Josephon, Bolta - Malta Linen, BVD-307, Width - 137cm (As per Data Sheet) | J. Josephson / BHS Trading |  | Secondary (Twin & King) 9801 the TV Wall | NH | MKM |  |  | 2018-01-18 | 2018-01-21 | 3 | B | 0 | B | Material is approved as procured from specified supplier. All original certificates upon its procurement. | 1 2 103
181 | MS-0110-00 |  | 0 | WALL COVERING | TECHNICAL DATA | SWA-107 | Wall Paper: |  | Wall Paper: J. Josephon, Bolta - Silk Road BVD-309 (As per Data Sheet) | J. Josephson / BHS Trading |  | Apartment 901 / Corridor Wall | NH | MKM |  |  | 2018-01-18 | 2018-01-21 | 3 | B | 0 | B | Material is approved as procured from specified supplier. Submit original certificates upon its procurement. | 1 2 103
182 | MS-0111-00 |  | 0 | WALL COVERING | TECHNICAL DATA | SWA-115 | Wall Paper: |  | Wall Paper: J. Josephon, Bolta - Fiddleback BVD-310 (As per Data Sheet) | J. Josephson / BHS Trading |  | Master Bedroom 901 / Behind the TV Wall | NH | MKM |  |  | 2018-01-18 | 2018-01-21 | 3 | B | 0 | B | Material is approved as procured from specified supplier. Submit original certificates upon its procurement. | 1 2 103
183 | MS-0119-00 |  | 0 | WALL COVERING | TECHNICAL DATA | SWGS-101 | Wall Paper: |  | Wallpaper: J-Josephson - Fiddleback Bolta - BVD 310 (As per Data Sheet) | J. Josephson / BHS Trading |  | Mock Up Room (Guestrooms) & Suites - Walls | NH | MKM |  |  | 2018-02-08 | 2018-02-13 | 5 | A | 0 | SS | Material is approved as procured from specified supplier. | 1 2 103 |  | AS PER HASSAN
184 | MS-0152-00 |  | 0 | WALL COVERING | TECHNICAL DATA | SWGS-115 | Wall Paper: |  | Wall Covering Premier Wall Vogue 6 - PV6343 Cavatina Silk - Incense (As per Data Sheet) | J. Josephson / Goodrich Global Trading LLC |  | Guestrooms & Suites - Bedroom | HH | MKM |  |  | 2018-06-07 | 2018-06-21 | 14 | B | 0 | B | Material I approved as procured from specified supplier & specs. Application as per ID drawings. | 1 2 103
185 | MS-0153-00 |  | 0 | WALL COVERING | TECHNICAL DATA | SWGS-101 | Wall Paper: |  | Wall Covering Premier Wall Vogue 6 - PV6343 Cavatina Silk - Cardamom (As per Data Sheet) | J. Josephson / Goodrich Global Trading LLC |  | Guestrooms & Suites - Bedroom | HH | MKM |  |  | 2018-06-07 | 2018-06-21 | 14 | B | 0 | B | Material is approved as procured from specified supplier & specs. Application as per ID drawings. | 1 2 103
186 | MS-0154-00 |  | 0 | WALL COVERING | TECHNICAL DATA | SWGS-110 | Wall Paper: |  | Wallpaper: J-Josephson - Bolta - Fiddleback - BVD 305 (As per Data Sheet) | J. Josephson / BHS Trading |  | Guestrooms & Suites - Living Room | HH | MKM |  |  | 2018-06-07 | 2018-06-21 | 14 | B | 0 | SS | Material is approved as procured from specified supplier & specs. Application as per ID drawings. | 1 2 103
187 | MS-0154-01 |  | 1 | WALL COVERING | SAMPLE | SWGS-110 | Wall Paper: |  | Wallpaper: J-Josephson - Bolta - BVD 305 (As per Sample) | J. Josephson / BHS Trading |  | Guestrooms & Suites - Living Room | HH | MKM |  |  | 2018-07-29 | 2018-08-06 | 8 | A | 0 | A | Sample approved for Bolta Li Ming - BVD 305. | 1 2 103
OTHERS | [26 empty] | PA
188 | MS-0149-00 |  | 0 | CARPET | SAMPLE | TAT | REP Col. 222 | Ruckstuhi carpet | Item Ref: REP, Col. 222, Composition: 48% Hair Yarn, 36.7% Pure New Wool, 15% PES, 0.3% Antistatic Roll Width: Approx. 400cm, 13’4” ft | Ruckstuhl Carpets |  | Private Apartment 1601 - Gym flooring | HHS | MKM |  |  | 2018-05-24 | 2018-06-03 | 10 | A | 0 | A | Based on the attached coordination email with I.D/DGA date 28 May 2018 & the attached Fire Testing documents, the material is approved. | 1 2 99 |  |  | PA
189 | MS-0147-00 |  | 0 | CORIAN | SAMPLE | N/A | Vanity Corian® DuPont top W1675xD530xH120mm Glacier White C01 with integerated Moode washbasin 700x400mm | Rexa, DuPont | Vanity Corian® DuPont top W1675xD530xH120mm Glacier White C01 with integerated Moode washbasin 700x400mm - Scatolato thick H 12cm (As per Sample) | Rexa |  | Private Apartment 1601 - Twin room bathroom vanity | HHS | MKM |  |  | 2018-05-01 | 2018-05-12 | 11 | A | 0 | A | A specified on DGA drawing. | 1 2 99 |  |  | PA
190 | MS-0169-00 |  | 0 | Underlay | SAMPLE | N/A |  |  | Carpet Underlay - Durafit 650 | Durafit |  | Gym | HH | MKM |  |  | 2018-08-13 | 2018-08-15 | 2 | B | 0 | B | Approved with Comment -Carpet underlay thickness should be adjusted to match the carpet & timber / wood strip surface levels. | 1 2 99 |  |  | PA
191 | MS-0171-00 | ARK-0001 | 0 |  | SAMPLE |  |  |  | Demista Heated Pads for Anti-Fog Mirrors (Adequete Sizes as per Contract Documents) | Demista - R & D Marketing |  | 16th Floor Private Apartment Master Bedroom & Twin Toilet | HH | MKM |  |  | 2018-09-23 | 2018-11-20 | 58 | B | 44 | B | Subject to final commissioning. | 1 2 99 |  |  | PA
[22 empty] | - |  | 1 2 107
|  |  |  | WAFI HOTEL COMPLEX AND MALL EXPANSION SUMMARY OF THE LOG FOR MATERIALS |  |  |  |  | NOS: | %
|  |  |  | TOTAL NO. OF MATERIALS SUBMITTED: |  |  |  |  | 0 | 0% | [6 empty] | 2016-12-05 |  | 994 | OD | 980 | OD
|  |  |  | TOTAL NO. OF MATERIALS TO BE SUBMITTED: |  |  |  |  | 0 | 100%
|  |  |  | BALANCE NO. OF MATERIALS TO BE SUBMITTED: |  |  |  |  | 0 | 0%
|  |  |  | APPROVED (A) |  |  |  |  | 0 | 0%
|  |  |  | APPROVED AS NOTED (B) |  |  |  |  | 0 | 0%
|  |  |  | RESUBMIT (C): |  |  |  |  | 0 | 0%
|  |  |  | REJECTED (D) |  |  |  |  | 0 | 0%
|  |  |  | INTERNAL REVIEW RETURN FOR CORRECTION (IR) |  |  |  |  | 0 | 0%
|  |  |  | ISSUED FOR REVIEW/APPROVAL (P) |  |  |  |  | 0 | 0%
|  |  |  | OVERDUE (OD) |  |  |  |  | 0 | 0%
|  |  |  | CANCELLED / NOT IN GLI SCOPE (X) |  |  |  |  | 0 | 0%
|  |  |  | FOR INFORMATION (FI) / NO ACTION |  |  |  |  | 0 | 0%
|  |  |  | ISSUED TO SITE, AWAITED ACKNOWLEDGEMENT COPY |  |  |  |  | 0 | 0%
Formulas:
Time taken to reply = IF([Date Commented]="",TODAY()-[Tracking],[Date Commented]-[Tracking])
STATUS = IF([Tracking]="",0,IF(((TODAY())-[Tracking])>14,"OD","P"))

## MS_LOG FF&E (hidden)
WAFI HOTEL COMPLEX AND MALL EXPANSION - PHASE 8, WAFI CITY - Plot No. 3153804, UMM HURAIR SECOND DUBAI (INTERIOR FITOUT WORKS)
FINISHES MATERIAL SCHEDULE & SUBMITTAL TRACKING LOG | [9 empty] | As of:- | 2016-11-13 | STATUS LEGEND
[12 empty] | A - Approved |  | P - Issued for Approval | [6 empty] | X - No Longer in Use/Not in Scope
[12 empty] | B - Approved as Noted |  | OD - Overdue | [6 empty] | FI - For Information only
[12 empty] | C - Resubmit |  | IR- Internal Review Return for Correction | [6 empty] | B/C- Approved as Noted / Resubmit
[12 empty] | D - Rejected |  | SS - Superseded by New Revision
Sr. No. | GLI Ref. No. | MKM | Rev. No: | Type of Material | Type of Submittal | Specs. Ref: | Material Description As Per Specification/ Contract Doc. | Manufacturer / Supplier | Proposed / Submitted Material | Manufacturer / Supplier | Location of Use | Area of Application | Initiator/ Follow-up By | Issued To | Planned Submission Start Date | Planned Submission Finish Date | Tracking
|  | Material Ref. | [14 empty] | Date Submitted | Date Commented | Time taken to reply | STATUS | No. of Days OverDue | Latest Status | Remarks
STONE FINISH
1 |  |  | 0 | MARBLE | SAMPLE | ST 008 | 20 mm Marroun Scurro Marble, polished, 100% natural. Cut to size | [14 empty] | 0 |  | 1 2 3
2 |  |  | 0 | MARBLE | SAMPLE | ST 009 | 20 mm Sina Beige, honed, 100% natural. Cut to size | [14 empty] | 0 |  | 1 2 4
3 |  |  | 0 | PORCELAIN TILE | SAMPLE | ST 010 | Argenta Ceramica - Spain, 11 mm, 450x900 mm, honed, Full body porcelain | [14 empty] | 0 |  | 1 2 5
4 |  |  | 0 | PORCELAIN TILE | SAMPLE | ST 011 | Fotiled TD 126008M, 11 mm, 600x600 mm, beige & honed, full body porcelain | [14 empty] | 0 |  | 1 2 6
5 |  |  | 0 | PORCELAIN TILE | SAMPLE | ST 011.1 | Fotiled TD 126008M, 11 mm, 120x600 mm, beige & honed, full body porcelain | [14 empty] | 0 |  | 1 2 7
6 |  |  | 0 | CERAMIC TILE | SAMPLE | ST 012 | RAK ceramics - Calixto flooring - Beige, 330x330 mm, 10 mm thick, Matt - non slip | [14 empty] | 0 |  | 1 2 8
7 |  |  | 0 | CERAMIC TILE | SAMPLE | ST 013 | RAK ceramics - Calixto white + beige, 250x330 mm, 12 mm thick, Glossy | [14 empty] | 0 |  | 1 2 9
8 |  |  | 0 | RECONSTITUTED STONE | SAMPLE | ST 016 | BFP stone - Nano glass, 20 mm thick, polished. Cut to size | [14 empty] | 0 |  | 1 2 10
9 |  |  |  | RECONSTITUTED STONE | SAMPLE | ST 016 | BFP stone - Nano glass, 10 mm thick, polished. Cut to size | [14 empty] | 0 |  | 1 2 11
10 |  |  | 0 | GRANITE | SAMPLE | ST 017 | Black absoluto, 20 mm (+20 mm for edge profile), polished, 100% natural stone | [14 empty] | 0 |  | 1 2 12
11 |  |  | 0 | MARBLE | SAMPLE | ST 034 | Fiore de pesco, 20 mm, polished, 100% natural | [14 empty] | 0 |  | 1 2 13
WOOD/VENEER & LACQUER FINISH
12 |  |  | 0 | WOOD | SAMPLE |  | SOLID MAHOGANY | [14 empty] | 0 |  | 1 2 26
13 |  |  | 0 | WOOD | SAMPLE |  | SOLID MERANTI | [14 empty] | 0 |  | 1 2 27
14 |  |  | 0 | WOOD | SAMPLE |  | SOLID BEACHWOOD | [14 empty] | 0 |  | 1 2 28
15 |  |  | 0 | VENEER | SAMPLE | TM 101 | Reconstituted Ebony Veneer - FF - 040-5902/3, 0.5-0.6mm, 25% GLOSSY | [14 empty] | 0 |  | 1 2 33
16 |  |  | 0 | VENEER | SAMPLE | TM 105 | Reconstituted OAK Veneer, BUSNELLI, R069/2 FP, 0.5-0.6mm, 25% GLOSSY | [14 empty] | 0 |  | 1 2 34
17 |  |  |  | VENEER | SAMPLE |  | KOTTO VENEER | [14 empty] | 0 |  | 1 2 35
18 |  |  |  | WOOD | SAMPLE |  | FRIT WOOD | [14 empty] | 0 |  | 1 2 36
GLASS & MIRROR
19 |  |  | 0 | MIRROR | SAMPLE | AW 701 | SILVER BACKING MIRROR FOR TV UNIT, 940X740 mm, 6mm THICK, CLEAR | [14 empty] | 0 |  | 1 2 40
20 | MS-0008-00 |  | 0 | MIRROR | SAMPLE | AW 703 | ANTIQUE BRONZE MIRROR, 6MM THICK |  | 6mm Thick Antique Mirror on Clear Glass (1) Ant 001, (2) Ant 002, (3) Ant 003, (4)- Ant 004 | Touch Of Glass |  | Standard Room & Executive Room |  |  |  |  | 2016-12-07 | 2016-12-07 | 0 | C | 0 | C | Resubmit it with (a) sample boards (b) checklist attached & (c ) Dividers | 1 2 41
21 |  |  | 0 | GLASS | SAMPLE | AW 704 | TOUGHENED CRYSTAL CLEAR GLASS - LOW IRON, 10MM THICK, TRANSAPRENT POLISHED, FOR SHOWER DOOR | [14 empty] | 0 |  | 1 2 42
22 |  |  | 0 | GLASS | SAMPLE | AW 706 | REFLECTIVE TEMPERED BACK PAINTED GLASS, MIRODEC-RAL 7006 COLOR, LOW IRON, CRYSTAL CLEAR, BEVELLED POLISHED EDGE | [14 empty] | 0 |  | 1 2 43
23 |  |  | 0 | ACRYLIC | SAMPLE | AR 103 | MILKY WHITE, 5-6 MM THICK, 22% TRANSPARENT | [14 empty] | 0 |  | 1 2 44
24 |  |  | 0 | GLASS | SAMPLE |  | 10MM THICK GLASS FASCIA FOR DRAWERS | [14 empty] | 0 |  | 1 2 45
FURNITURE HARDWARE
25 |  |  | 0 | FURNITURE HARDWARE | SAMPLE |  | DOUBLE BALL CATCH | [14 empty] | 0 |  | 1 2 60
26 |  |  | 0 | WARDROBE FITTINGS | SAMPLE |  | TIE RACK | [14 empty] | 0 |  | 1 2 61
27 |  |  | 0 | WARDROBE FITTINGS | SAMPLE |  | HANGING RAIL
28 |  |  | 0 | FURNITURE HARDWARE | SAMPLE |  | DRAWER RUNNER | [14 empty] | 0 |  | 1 2 62
29 |  |  | 0 | FURNITURE HARDWARE | SAMPLE |  | FLAP HINGE MARKANT | [14 empty] | 0 |  | 1 2 63
30 |  |  | 0 | FURNITURE HARDWARE | SAMPLE |  | CABINET HINGE 110° ANGLE FULL OVERLAY | [14 empty] | 0 |  | 1 2 64
31 |  |  | 0 | FURNITURE HARDWARE | SAMPLE |  | CABINET HINGE 110° ANGLE HALF OVERLAY | [14 empty] | 0 |  | 1 2 65
32 |  |  | 0 | FURNITURE HARDWARE | SAMPLE |  | CABINET HINGE 110° ANGLE INSET TYPE | [14 empty] | 0 |  | 1 2 66
33 |  |  | 0 | FURNITURE HARDWARE | SAMPLE |  | SOSS HINGE | [14 empty] | 0 |  | 1 2 67
34 |  |  | 0 | FURNITURE HARDWARE | SAMPLE |  | SOFT CLOSING SIDE MOUNTING DRAWER RUNNER LEFT AND RIGHT | [14 empty] | 0 |  | 1 2 68
35 |  |  | 0 | FURNITURE HARDWARE | SAMPLE |  | MAGNETIC PUSH CATCH | [14 empty] | 0 |  | 1 2 70
36 |  |  | 0 | FURNITURE HARDWARE | SAMPLE |  | CHEST LID HINGE | [14 empty] | 0 |  | 1 2 74
METAL
37 | MS-0007-00 |  | 0 | METAL | SAMPLE | MT 304 | POLISHED STAINLESS STEEL5X10 MM FOR LUGGAGE SHELVES |  | 1MM Thick Stainless Steel Mirror Finish (304 Grade) | YC INOX CO, LTD |  | Luggage Rack, Toilet Niche Frame |  |  |  |  | 2016-12-07 | 2016-12-07 | 0 | C | 0 | C | Refer to email dated 07/12/16 Resubmit with sample boards, filled in check list & dividers | 1 2 76
38 |  |  | 0 | METAL | SAMPLE | MT 305 | POWDER COATED METAL L-SHAPE PROFILE UNDER GLASS, BLACK RAL 7022, 30x20mm | [14 empty] | 0 |  | 1 2 77
39 | MS-0007-00 |  | 0 | METAL | SAMPLE |  | POLISHED STAINLESS STEEL FOR TOILET NICHES CORNERS | [12 empty] | FI |  | FI |  | 1 2 78
FABRIC / LEATHER UPHOLSTRY
40 |  |  | 0 | FABRIC | SAMPLE | FB 210 | KIRBY APOLLO FR CLAY - KB 5035/05, 450gsm, 60%POLYESTER-40%PU, |  | FIRE RETARDANT: BS5828 PART 1 IGNITION 0 CIGARETTE TEST AND 1 MATCH TEST | [12 empty] | 0 |  | 1 2 81
41 |  |  | 0 | FABRIC | SAMPLE | FB 232 | ATELIER A - BNS 78923-26, 100% POLYESTER INHERENT FR |  | FIRE RETARDANT: CAT 117 FOR 3 LAYERS | [12 empty] | 0 |  | 1 2 82
GYPSUM CEILINGS & PAINT
42 | MS-0005-00 |  | 0 | GYPSUM BOARD | SAMPLE |  | STANDARD GYPSUM BOARD 12.5mm FOR FRY AREAS |  | Complete set of Knauf 12.5mm Thick Gypsum Board Material (Regular & MR) with Suspension System including Accessories and Fastening Devices | Knauf |  | Ceiling - Wherever Applicable |  |  |  |  | 2016-12-05 | 2016-12-07 | 2 | C | 0 | C | Submit sample boards - 3 sets refer to email dated 07/12/16 | 1 2 92
43 |  |  | 0 | GYPSUM BOARD | SAMPLE |  | MR GYPSUM BOARD 12.5mm FOR WET AREAS | [12 empty] | FI |  | FI |  | 1 2 93
44 | MS-0011-00 |  | 0 | ACCESS PANEL | SAMPLE |  |  |  | CEILING ACCESS PANEL 60X60 | [12 empty] | 0 | ISSUED TO SITE ON 07/12/16 | 1 2 93
45 | MS-0006-00 |  | 0 | WALL PAINT | SAMPLE | PT 600 | BACKWALL AND CEILING FENOMASTIC PAINT, JOTUN S 0500N |  | Acrylic Emulsion Paint System including Primer & Stucco Colour Reference (RAL) sample to be submitted separately. | Jotun |  | Ceiling & Walls - Wherever Applicable |  |  |  |  | 2016-12-07 |  | 992 | OD | 978 | OD |  | 1 2 94
46 |  |  | 0 | WALL PAINT | SAMPLE | PT 602 | PAINT FINISH MAMORINO - METALLIC EFFECT - PEGASUS COLOR-METALLIC TOP-COPPER BRONZE+SILVER | [14 empty] | 0 |  | 1 2 95
47 | MS-0006-00 |  | 0 | WALL PAINT | SAMPLE | PT 603 | CEILING PAINT, FENOMASTIC, JOTUN S 0502G -04-A1/10-C1 | [12 empty] | FI |  | FI |  | 1 2 96
48 | MS-0006-00 |  | 0 | WALL PAINT | SAMPLE | PT 604 | WALL PAINT, FENOMASTIC, JOTUN S 1000N-05 A6 | [12 empty] | FI |  | FI |  | 1 2 97
WALLCOVERING
49 |  |  | 0 | WALL COVERING | SAMPLE | WP 605 | MURASPEC - UNION - CELESTE A2A33 | [14 empty] | 0 |  | 1 2 99
50 |  |  | 0 | WALL COVERING | SAMPLE | WP 606 | MURASPEC - MUREK - NUREY 04A16, PAPER BACKED | [14 empty] | 0 |  | 1 2 100
51 |  |  | 0 | WALL COVERING | SAMPLE | WP 607 | OMEXCO ETERNITY ET 2002, AGED BEIGE, MATT FINISH, 1mm THICK | [14 empty] | 0 |  | 1 2 101
52 |  |  | 0 | WALL COVERING | SAMPLE | WP 612 | OMEXCO NV - HOR1114, BEIGE, ON NON WOVEN BACKING | [14 empty] | 0 |  | 1 2 102
53 |  |  | 0 | WALL COVERING | SAMPLE | WP 614 | MURASPEC - CHANCERY - TESSAI 03A83 | [14 empty] | 0 |  | 1 2 103
54 |  |  | 0 | WALL COVERING | SAMPLE | WP 620 | SQUISITO - ARTE NOCTIS - REF.38154, CREAM/BEIGE, NATURAL EFFECT | [14 empty] | 0 |  | 1 2 104
[22 empty] | - |  | 1 2 107
|  |  |  | WAFI HOTEL COMPLEX AND MALL EXPANSION SUMMARY OF THE LOG FOR MATERIALS |  |  |  |  | NOS: | %
|  |  |  | TOTAL NO. OF MATERIALS SUBMITTED: |  |  |  |  | 0 | 0% | [6 empty] | 2016-12-05 |  | 994 | OD | 980 | OD
|  |  |  | TOTAL NO. OF MATERIALS TO BE SUBMITTED: |  |  |  |  | 0 | 100%
|  |  |  | BALANCE NO. OF MATERIALS TO BE SUBMITTED: |  |  |  |  | 0 | 0%
|  |  |  | APPROVED (A) |  |  |  |  | 0 | 0%
|  |  |  | APPROVED AS NOTED (B) |  |  |  |  | 0 | 0%
|  |  |  | RESUBMIT (C): |  |  |  |  | 0 | 0%
|  |  |  | REJECTED (D) |  |  |  |  | 0 | 0%
|  |  |  | INTERNAL REVIEW RETURN FOR CORRECTION (IR) |  |  |  |  | 0 | 0%
|  |  |  | ISSUED FOR REVIEW/APPROVAL (P) |  |  |  |  | 0 | 0%
|  |  |  | OVERDUE (OD) |  |  |  |  | 0 | 0%
|  |  |  | CANCELLED / NOT IN GLI SCOPE (X) |  |  |  |  | 0 | 0%
|  |  |  | FOR INFORMATION (FI) / NO ACTION |  |  |  |  | 0 | 0%
|  |  |  | ISSUED TO SITE, AWAITED ACKNOWLEDGEMENT COPY |  |  |  |  | 0 | 0%
Formulas:
Time taken to reply = IF([Date Commented]="",TODAY()-[Tracking],[Date Commented]-[Tracking])
STATUS = IF([Tracking]="",0,IF(((TODAY())-[Tracking])>14,"OD","P"))

## MS_LOG RAW (hidden)
WAFI HOTEL COMPLEX AND MALL EXPANSION - PHASE 8, WAFI CITY - Plot No. 3153804, UMM HURAIR SECOND DUBAI (INTERIOR FITOUT WORKS)
FINISHES MATERIAL SCHEDULE & SUBMITTAL TRACKING LOG | [9 empty] | As of:- | 2016-11-13 | STATUS LEGEND
[12 empty] | A - Approved |  | P - Issued for Approval | [6 empty] | X - No Longer in Use/Not in Scope
[12 empty] | B - Approved as Noted |  | OD - Overdue | [6 empty] | FI - For Information only
[12 empty] | C - Resubmit |  | IR- Internal Review Return for Correction | [6 empty] | B/C- Approved as Noted / Resubmit
[12 empty] | D - Rejected |  | SS - Superseded by New Revision
Sr. No. | GLI Ref. No. | MKM | Rev. No: | Type of Material | Type of Submittal | Specs. Ref: | Material Description As Per Specification/ Contract Doc. | Manufacturer / Supplier | Proposed / Submitted Material | Manufacturer / Supplier | Location of Use | Area of Application | Initiator/ Follow-up By | Issued To | Planned Submission Start Date | Planned Submission Finish Date | Tracking
|  | Material Ref. | [14 empty] | Date Submitted | Date Commented | Time taken to reply | STATUS | No. of Days OverDue | Latest Status | Remarks
STONE FINISH
1 |  |  | 0 | SEALER | TECHNICAL SHEET |  | 15 Gold - Acqua mix Inc. | [14 empty] | 0 |  | 1 2 14
2 |  |  | 0 | GROUT | TECHNICAL SHEET |  | Mapei-131-Vanilla | [14 empty] | 0 |  | 1 2 15
3 |  |  |  | GROUT | TECHNICAL SHEET |  | Keracolor-132-beige2000 | [14 empty] | 0 |  | 1 2 16
4 |  |  | 0 | ADHESIVE | TECHNICAL SHEET |  | Keraset grey - Mapei | [14 empty] | 0 |  | 1 2 17
WOOD/VENEER & LACQUER FINISH
5 |  |  | 0 | MDF | SAMPLE |  | 6mm THICK PLAIN MDF | [12 empty] | FI |  | FI |  | 1 2 19
6 |  |  | 0 | MDF | SAMPLE |  | 12mm THICK PLAIN MDF | [12 empty] | FI |  | FI |  | 1 2 20
7 | MS-0001-00 |  | 0 | MDF | SAMPLE | 09951 | 18mm THICK PLAIN MDF |  | Plain MDF - Adequate Thickness as per Contract Documents. (Sample Provided 12 & 18mm for Indicative Purpose) | Evergreen |  | Wherever Applicable |  |  |  |  | 2016-12-05 | 2016-12-07 | 2 | C | 0 | C | -MDF to comply with BSEN 622-1-2003 & 622-5-2009 '- Self Certificate by manufacturer is not acceptable. -Submit test report from DCL approved laboratory | 1 2 21
8 |  |  | 0 | MDF | SAMPLE |  | 30mm THICK PLAIN MDF | [12 empty] | FI |  | FI |  | 1 2 22
9 | MS-0002-00 |  | 0 | MDF | SAMPLE | 09951 | 18mm THICK MDF FR |  | High Moisture Resistant MDF - Adequate Thickness as per Contract Documents. (Sample provided is 18mm thick) | Evergreen |  | Wet Areas -Wherever Applicable |  |  |  |  | 2016-12-05 | 2016-12-07 | 2 | C | 0 | C | -MDF to comply with BSEN 622-1-2003 & 622-5-2009 -Submit test report from DCL approved laboratory | 1 2 23
10 |  |  | 0 | MDF | SAMPLE |  | 18mm MDF MR | [12 empty] | FI |  | FI |  | 1 2 24
11 |  |  | 0 | MDF | SAMPLE |  | 30mm MDF MR | [12 empty] | FI |  | FI |  | 1 2 25
12 | MS-0003-00 |  | 0 | PLYWOOD | SAMPLE | 09951-3 | PLYWOOD |  | Plywood - Adequate Thickness as per Contract Documents. (Sample Provided 12 & 18mm for Indicative Purpose) | Tridel Supreme |  | Central Panel Products- Singapore |  |  |  |  | 2016-12-05 | 2016-12-07 | 2 | C | 0 | C | -Provided data sheet and test certificate are contredictry each other -Manufacturer & origin different in data sheet & test report. -M/s. GLI to provide verifyable proof that material is confirming to specs (BS 1088) | 1 2 29
13 | MS-0004-00 |  | 0 | PLYWOOD | SAMPLE | 09951-3 | PLYWOOD: 18mm MARINE PLYWOOD |  | 18mm Thick Marine Plywood - Film Faced | Tridel Supreme |  | Wherever Applicable |  |  |  |  | 2016-12-05 | 2016-12-07 | 2 | C | 0 | C |  | 1 2 29
14 | MS-0009-00 |  | 0 | WOOD | SAMPLE |  | FIRE RATED DOOR CORE (60MIN FR) |  | 60min Fire Rated Door Core 54mm - Halspan 60 Optima (FD60) | Halspan |  | 60min Fire Rated Doors from L8 to L41 |  |  |  |  | 2016-12-07 | 2016-12-07 | 0 | C | 0 | C | Refer to email dated 07/12/16 Resubmit with sample boards, filled in check list & dividers | 1 2 30
15 | MS-0010-00 |  | 0 | WOOD | SAMPLE |  | NFR DOOR CORE 44mm |  | Non Fire Rated 44mm thick Solid Door Core - Linex France | LINEX |  | Non Fire Rated Doors from L8 to L41 |  |  |  |  | 2016-12-07 | 2016-12-07 | 0 | C | 0 | C | Refer to email dated 07/12/16 Resubmit with sample boards, filled in check list & dividers | 1 2 31
16 |  |  | 0 | WOOD | SAMPLE |  | FIRE RATED DOOR CORE (90MIN FR) | [14 empty] | 0 |  | 1 2 32
17 |  |  | 0 | LACQUER FINISH | TECHNICAL SHEET |  | LACQUER | [14 empty] | 0 |  | 1 2 37
18 |  |  | 0 | SEALANT | TECHNICAL SHEET |  | ACETOXY SILICONE | [14 empty] | 0 |  | 1 2 38
GLASS & MIRROR
19 |  |  | 0 | ADHESIVE | TECHNICAL SHEET |  | ADHESIVE FOR MIRROR | [14 empty] | 0 |  | 1 2 46
20 |  |  | 0 | GLASS | SAMPLE |  | STAINLESS STEEL U CHANNEL | [14 empty] | 0 |  | 1 2 47
21 |  |  | 0 | SEALANT | SAMPLE |  | SILICONE SEALANT | [14 empty] | 0 |  | 1 2 48
22 |  |  | 0 | SEALANT | SAMPLE |  | SILICONE SEALANT | [14 empty] | 0 |  | 1 2 49
23 |  |  | 0 | SEALANT | TECHNICAL SHEET |  | SEALANT | [14 empty] | 0 |  | 1 2 50
24 |  |  | 0 | GLASS | SAMPLE |  | WATER TIGHT SEALANT | [14 empty] | 0 |  | 1 2 51
IRONMONGERY
25 |  |  | 0 | IRONMONGERY | SAMPLE |  | FIRE DOOR SEAL (INTUMESCENT STRIP) |  | FIRE DOOR SEAL 15X4mm INTUMESCENT STRIP (SAMPLE AS SUBMITTED FOR REV.0) | [12 empty] | 0 |  | 1 2 53
26 |  |  | 0 | IRONMONGERY | SAMPLE |  | FIRE RATED EXPANDING FOAM |  | FIRE RATED EXPANDING FOAM | [12 empty] | 0 |  | 1 2 54
27 |  |  | 0 | INTUMESCENT PROTECTION KIT | SAMPLE | _ | INTUMESCENT PROTECTION KIT |  | INTUMESCENT PROTECTION KIT: 1mm THICK LORIENT INTUMESCENT PROTECTION KIT (A4 SHEET) (AS PER SAMPLE) | [12 empty] | 0 |  | 1 2 55
28 |  |  | 0 | ACOUSTIC CORNER SEAL | SAMPLE | _ | ACOUSTIC CORNER SEAL |  | ACOUSTIC CORNER SEAL: REDDIPLEX ACOUSTIC CORNER SEAL. R9946, COLOR BROWN. SIZE: 12X12MM WITH SELF ADHESIVE TAPE NOISE PROTECTION INDEX RW31db (AS PER SAMPLE) | [12 empty] | 0 |  | 1 2 56
29 |  |  | 0 | FOAM | SAMPLE | _ | JOINT FOAM |  | JOINT FOAM FIRE=RESISTANT PLUS | [12 empty] | 0 |  | 1 2 57
30 |  |  | 0 | SEALANT | SAMPLE | _ | FIRE STOP SYSTEM |  | FIRE STOP SYSTEM: FLEXIBLE FIRE STOP SEALANT | [12 empty] | 0 |  | 1 2 58
FURNITURE HARDWARE
31 |  |  | 0 | DOOR HARDWARE | SAMPLE |  | REBATE SEAL | [14 empty] | 0 |  | 1 2 71
32 |  |  | 0 | DOOR HARDWARE | SAMPLE |  | REBATE SEAL | [14 empty] | 0 |  | 1 2 72
33 |  |  | 0 | RUBBER SEAL | SAMPLE |  | SHOWER DOOR TRANSPARENT SEAL | [14 empty] | 0 |  | 1 2 73
METAL
34 |  |  | 0 | ADHESIVE | TECHNICAL SHEET | [16 empty] | 0 |  | 1 2 79
FABRIC / LEATHER UPHOLSTRY
35 |  |  | 0 | FOAM | TECHNICAL SHEET |  | FR DACRON 100gms |  | RAHA POLYESTER FIBER THERMOBONDED DACRON M7201 | [12 empty] | 0 |  | 1 2 83
36 |  |  | 0 | FOAM | TECHNICAL SHEET |  | 40KG DENSITY FR FOAM PAD 100mm THICK |  | 40KG DENSITY FLAME RETARDANT FOAM PAD 100mm THICK | [12 empty] | 0 |  | 1 2 84
37 |  |  | 0 | FOAM | TECHNICAL SHEET |  | 40KG DENSITY FR FOAM PAD 50mm THICK |  | 40KG DENSITY FLAME RETARDANT FOAM PAD 50mm THICK | [12 empty] | 0 |  | 1 2 85
38 |  |  | 0 | FOAM | TECHNICAL SHEET |  | 40KG DENSITY FR FOAM PAD 10mm THICK |  | 40KG DENSITY FLAME RETARDANT FOAM PAD 10mm THICK | [12 empty] | 0 |  | 1 2 86
39 |  |  | 0 | FOAM | TECHNICAL SHEET |  | 30KG DENSITY FR FOAM PAD 100mm THICK |  | 30KG DENSITY FLAME RETARDANT FOAM PAD 100mm THICK | [12 empty] | 0 |  | 1 2 87
40 |  |  | 0 | FOAM | TECHNICAL SHEET |  | 30KG DENSITY FR FOAM PAD 50mm THICK |  | 30KG DENSITY FLAME RETARDANT FOAM PAD 50mm THICK | [12 empty] | 0 |  | 1 2 88
41 |  |  | 0 | FOAM | TECHNICAL SHEET |  | 30KG DENSITY FR FOAM PAD 10mm THICK |  | 30KG DENSITY FLAME RETARDANT FOAM PAD 10mm THICK | [12 empty] | 0 |  | 1 2 89
42 |  |  | 0 | FOAM | TECHNICAL SHEET |  | 55KG DENSITY FR FOAM PAD 100mm THICK |  | 55KG DENSITY FLAME RETARDANT FOAM PAD 100mm THICK | [12 empty] | 0 |  | 1 2 90
WALLCOVERING
43 |  |  | 0 | ADHESIVE | TECHNICAL DATA |  | MC BOND WALL COVERING ADHESIVE READY MIXED | [14 empty] | 0 |  | 1 2 105
44 |  |  | 0 | PRIMER | TECHNICAL DATA |  | PRIMER | [14 empty] | 0 |  | 1 2 106
[22 empty] | - |  | 1 2 107
|  |  |  | WAFI HOTEL COMPLEX AND MALL EXPANSION SUMMARY OF THE LOG FOR MATERIALS |  |  |  |  | NOS: | %
|  |  |  | TOTAL NO. OF MATERIALS SUBMITTED: |  |  |  |  | 0 | 0% | [6 empty] | 2016-12-05 |  | 994 | OD | 980 | OD
|  |  |  | TOTAL NO. OF MATERIALS TO BE SUBMITTED: |  |  |  |  | 0 | 100%
|  |  |  | BALANCE NO. OF MATERIALS TO BE SUBMITTED: |  |  |  |  | 0 | 0%
|  |  |  | APPROVED (A) |  |  |  |  | 0 | 0%
|  |  |  | APPROVED AS NOTED (B) |  |  |  |  | 0 | 0%
|  |  |  | RESUBMIT (C): |  |  |  |  | 0 | 0%
|  |  |  | REJECTED (D) |  |  |  |  | 0 | 0%
|  |  |  | INTERNAL REVIEW RETURN FOR CORRECTION (IR) |  |  |  |  | 0 | 0%
|  |  |  | ISSUED FOR REVIEW/APPROVAL (P) |  |  |  |  | 0 | 0%
|  |  |  | OVERDUE (OD) |  |  |  |  | 0 | 0%
|  |  |  | CANCELLED / NOT IN GLI SCOPE (X) |  |  |  |  | 0 | 0%
|  |  |  | FOR INFORMATION (FI) / NO ACTION |  |  |  |  | 0 | 0%
|  |  |  | ISSUED TO SITE, AWAITED ACKNOWLEDGEMENT COPY |  |  |  |  | 0 | 0%
Formulas:
Time taken to reply = IF([Date Commented]="",TODAY()-[Tracking],[Date Commented]-[Tracking])
STATUS = IF([Tracking]="",0,IF(((TODAY())-[Tracking])>14,"OD","P"))