## 1252-WAFI
ABC COMPANY
REQUEST FOR INFORMATION TRACKING REGISTER
[11 empty] | As on: | 2019-08-26
PROJECT NAME: | [6 empty] | PROJECT NUMBERS |  |  |  |  | STATUS CODES
XYZ PROJECT CITY ABC (INTERIOR FITOUT PACKAGE) | [6 empty] | 5698 |  |  |  |  | A: Replied
P: Submitted - Not yet Replied (Less than 7 days)
OD: Overdue Submitted Not yet Replied (More than 7 Days)
GLI RFI No: | ARK Ref. No. | Rev. No.: | Subject | Ref. Doc / Attachment | Location | Description | Raised by | Issued To | Date Submitted | Date Received | Time Taken to Reply | Reply /Response | Status Code | Remarks | Line Adjust
0001 |  | 00 | Change of Wall Covering Codes | MKM-05Q-IDP-01-CI-0001 | Apartments & Guest rooms Wall Coverings | Further to the Client Instruction number MKM-05Q-IDP-01-CI-0001 in regards of the wall coverings changes, and today’s discussion at your offices in regards of the same, you are kindly requested to send us the revised wall finishes layouts for all floors at the earliest. | NAM | MKM | 2016-12-12 | 2016-12-13 | 1 | Refer to Client's Instruction: MKM-05Q-IDP-01-CI-0004 issued on 12th December 2016 for clarification on RFI subject. | A |  | 1 2 3
0002 |  | 00 | High kitchen counter | 05Q¦8F-17F¦DET¦0334 High kitchen counter rev.0 & rev.1 | High kitchen counter | Please clarify and provide details and specs for the materials: - Formica laminate type A - Formica laminate type B Both at the high kitchen counter stated previously as Timber + lacquer paint finish Also clarify the Nano glass 6mm thick in the drawings but 20 mm in the specifications. | NAM | MKM | 2016-12-14 | 2016-12-18 | 4 | Refer to 3D renders for finishes overall look Formica Grey colour "Battalon 0806" Formica White colour code "ICE White 0953" Formica to match veneer sample - to be submitted for ID approval. | A |  | 1 2 4
0003 |  | 00 | Pantry unit | 05Q¦8F¦DET¦0351 Pantry Unit (Tender documents reference) | Pantry unit | The auto cad drawings of the Pantry units are not received with the final IFC package. Please provide them in auto cad format. | NAM | MKM | 2016-12-14 | 2016-12-18 | 4 | Refer to attached in Cad & Pdf | A |  | 1 2 5
0004 |  | 00 | Stainless Steel Corner Angles | 05Q¦24F-41F¦DET¦0311 Bathroom details | All bathrooms with niches | In relation to the bathroom details and the mock-up room, the wall niche has a readymade stainless steel corner frame. Please provide the detail and the selection reference as per our discussion. | NAM | MKM | 2016-12-14 | 2016-12-15 | 1 | As per mockup Contractor to propose. Attached contact details (Progress Profile) | A |  | 1 2 6
0005 |  | 00 | Swivel TV Stand | 05Q¦8F-41F¦DET¦0319 Bathroom details | TV wall units | Please provide the details and specification for the swiveling TV stand at TV wall units. | NAM | MKM | 2016-12-14 | 2016-12-15 | 1 | Contractor to propose 180° | A |  | 1 2 7
0006 |  | 00 | AutoCAD Drawings for Corridors |  | Corridors | Please provide the AutoCAD IFC drawings of the corridors from floors 8 to 41 as they were not received with the final IFC package. | NAM | MKM | 2016-12-18 | 2017-01-18 | 31 | Please follow the floor wise IFC for corridor details. Separate drawings will not be required. Floorwise Ifc's attached for perusal. | A |  | 1 2 8
0007 |  | 00 | Wallpaper Schedule Confirmation |  | As per Wallpaper schedule | Find attached a schedule for the wallpaper references and location of uses, kindly approve and/or comment | NAM | MKM | 2016-12-18 | 2016-12-22 | 4 | Find Attached Comments, Locations to be as per IFC Drawings. | A |  | 1 2 9
0008 |  | 00 | Porcelain Skirting Dimensions | 05Q¦8F¦EL¦0107.10 | Apartments | Kindly confirm the height of 92mm for the porcelain skirting at the apartments as per the drawings. Note that the BOQ mentions a height of 120 mm and the specs not mentioning height. | NAM | MKM | 2016-12-18 | 2016-12-19 | 1 | Follow BOQ - 120mm | A |  | 1 2 10
0008 |  | 01 | Porcelain Skirting Dimensions | 05Q¦8F¦EL¦0107.10 | Apartments | As per commented drawings, wardrobe should have a Porcelain skirting of 120mm height as per RFI MKM-05Q-IDP-01-RFI-0008 reply. The same type of wardrobe is placed on carpet (1 Bedroom, 2 Bedrooms & 3 bedrooms units) where the skirting is wooden and 92 mm height as per attached drawing and related BOQ page. Please confirm the height of the skirting below wardrobes at different locations. | NAM | MKM | 2017-01-11 | 2017-01-11 | 0 | Follow the comments to drawings. Tile skirting to be chamger (3-4mm) | A |  | 1 2 10
0009 |  | 00 | Maid Toilet Floor tiles | 05Q-8F-FF-0107.44 | Apartment - Maid Toilet | Please note that Floor tile ST-012 - RAK Ceramics – Calixto flooring size 330x330 mm is available only in Gloss finish and not available in Matt finish as per the attached email communication from the Supplier. Therefore kindly advise how to proceed on this matter. | NAM | MKM | 2017-01-05 | 2017-01-13 | 8 | Request for alternative in same style and colour and size. | SS |  | 1 2 11
0009 |  | 01 | Maid Toilet Floor Tiles | 05Q-8F-FF-0107.44 | Apartment - Maid Toilet | Previously ST-012 Beige tile matt was going on the floors of Maid’s toilet, laundry and storage areas. Since the matt tile is not coming from RAK we sent an RFI for the floor tiles. Now as per the MS approval, you are advising us to go for the Beige glossy tiles on all the floors. Please confirm if this is correct and we can proceed for glossy tiles for all areas of ST-012 Maid’s bath, laundry & storage (which means RFI 0009 sent for ST-012 is not valid anymore). The size specified for the floors was 33 x 33 cm. The MS approval doesn’t tell anything about the size Previously combination of beige glossy and white glossy were going on the maid toilet walls and Glossy beige was going on the laundry & storage walls. As per the MS approval, you changed all walls to White glossy tiles. Please confirm to proceed. | NAM | MKM | 2017-01-11 | 2017-01-14 | 3 | Kindly Propose Alternative in Matt Finish. | A |  | 1 2 11
0009 |  | 02 | Maid Toilet, Maid room, Laundry room and store room floor Tiles | 05Q¦8F¦FF¦0107.44 | Apartments: Floor and wall tiles for maid room, maid toilets, laundry rooms & storage | Following your reply to RFI-0009 please select from these 4 alternatives for the floor tile for the above mentioned areas (Physical samples included with submittal): - A04RRICA-IVO-MOU - A04R4001-LBE-MOU - A04RZSPC-WHO-MOU - AO4R1074-IVO-MOU Also submitted the previously selected colors for your reference | NAM | MKM | 2017-01-25 | 2017-01-26 | 1 | A04RZSPC – WHO –MOU Approved sample. | A |  | 1 2 11
0010 |  | 00 | Façade Drawings |  | False ceiling – all apartments | Please provide the shop drawings of the Glass façade to enable us to prepare the interface detail between gypsum ceiling and façade mullions. | NAM | MKM | 2017-01-09 | 2017-01-09 | 0 | Attached digital copies of façade drawings (Autocad Drawings & Commented Drawings PDF) | A |  | 1 2 12
0011 |  | 00 | Guest Toilet Tiles | 05Q¦8F-17F¦DET¦0305.1 | Apartments: Flooring for maid room, maid toilets, laundry rooms & storage | Please confirm the tile selection for the floors and walls of the Apartments guest toilets mentioned as ST 010 on the drawings - 450x900 mm Argenta porcelain tiles with pre-incisions – and advice about the location of Argenta Sina beige 60x30 cm and 60x60 cm. | NAM | MKM | 2017-01-11 | 2017-01-11 | 0 | Argenta: 60x60cm is for floor & 30x60cm for walls as per elevation. For Guest Toilet: 45x90only for bathroom. | A |  | 1 2 13
0012 |  | 00 | Antique Mirror | 05Q¦8F-41F¦DET¦0331 | Guest rooms - Wardrobes | As per Material Submittal MKM-05Q-IDP-01-MS-008, Antique mirror to be placed only at Junior suite. Please specify the mirror finish for all other areas, and clarify the specifications of mirror AW702 | NAM | MKM | 2017-01-15 | 2017-02-14 | 30 | Refer attached specification sheet & sample photos. Samples available at MKM office, M/s GLI may take it for reference but to be returned. | A |  | 1 2 14
0013 |  | 00 | TV and bracket dimensions and specifications | 05Q¦8F-41F¦DET¦0316 | TV units - All rooms | Please provide the exact TV dimensions along with support bracket specifications and sample to have it detailed with the TV units – Note that the physical sample is required to make sure that it will be possible to install and remove the TV once the unit is completed. | NAM | MKM | 2017-01-15 | 2017-02-12 | 28 | Distribution of television unit 1230.6 x718.4 x 64.0 (Attached data sheet) bracket dimension as per mockup. | A |  | 1 2 15
0013 |  | 01 | TV and bracket dimensions and specifications | 05Q¦8F-41F¦DET¦0316 | TV units - All rooms | Further to the RFI-0013-00 reply dated 12/02/2017 mentioning TV size 1230.6 x 718.4 x 64.0 mm, note that commented drawings submittal MKM-05Q-IDP-01-DS-040 Rev. 01 for the TV mirror frame is mentioning a different size of 1242 x 716 x 31 mm. Please clarify which one is final and if 1 TV type and size will be used for all rooms. | NAM | MKM | 2017-07-02 | 2017-07-04 | 2 | Refer to the recent correspondence dated May 23, 2017 with the approved TV size. | A |  | 1 2 15
0014 |  | 00 | Kitchen appliances and Sanitary fixtures and appliances | 05Q¦8F-17F¦DET¦0303.1 | Kitchens ¬and Bathrooms in all rooms | Please provide the complete specifications for all the kitchen appliances and fittings, in addition to the sanitary fixtures and bathrooms/toilets accessories and appliances. | NAM | MKM | 2017-01-17 | 2017-02-14 | 28 | Kitchen appliances specifications attached (10 pages) Bathroom / toilet accessories specification officially transmitted via MKM-05Q-IDP-01-TM-0010 cover sheet attached. | A |  | 1 2 16
0015 |  | 00 | Studio B Floors 9 to 17 – TV unit detail drawings | 05Q¦9F-13F¦GA¦0108.11 | TV unit – Floor 9 to 17 | Please provide the TV unit detail drawings for the Studio unit B from floor 9 to 17 | NAM | MKM | 2017-01-24 | 2017-03-09 | 44 | FOLLOW RFI-0013 NO SEPARATE TV SPEC FOR STUDIO-B | A |  | 1 2 17
0016 |  | 00 | [9 empty] | Not yet issued | 0 |  | 1 2 18
0017 |  | 00 | Apartments – Laundry Room cabinets | 05Q¦9F-13F¦GA¦0108.31 | Apartments – Laundry rooms | Please provide the detail drawings for the Laundry room cabinets in all apartments | NAM | MKM | 2017-02-09 | 2017-02-13 | 4 | Refer to the attached - Email will follow | A |  | 1 2 19
0018 |  | 00 | Bathrooms & Guest Toilets Flushing Cistern | 05Q¦8F-17F¦DET¦306 | Apartments & Guest rooms – Bathrooms and Guest toilets | You are kindly requested to provide the latest specifications for the flushing cistern to be used in all bathrooms, as per previous discussions, the attached in the received transmittal MKM-05Q-IDP-01-TM-Greenline-0010 on Feb. 01 is not applicable and a different selection will be proposed. | NAM | MKM | 2017-02-13 | 2017-02-14 | 1 | Find attached technical data sheet and photo. Physical sample available at MKM office. | A |  | 1 2 20
0019 |  | 00 | Ironmongery details | 05Q¦8F-17F¦DET¦314, 05Q¦8F¦DET¦302.1 | Apartments, Guest rooms and lift lobbies | Please provide the ironmongery specifications for the following wood doors: - Maid room door WD3b at 2 & 3 bedroom apartments floors 8 to 17 (concealed hinge) - Lift lobby double door WD11 floors 19 to 41 (Butt hinge) - Interconnecting door WD12 floors 24 to 41 (handles on both sides, double sided cylinder) | NAM | MKM | 2017-02-13 | 2017-03-27 | 42 | • Maids room doors WD3a & WD3b to have concealed hinges , refer attached data sheet for SOSS hinges (3 Hinges per door), other hardware’s to remain same, extract from hardware schedule attached. • Lift Lobby double door to have floor spring to enable 180 degree opening and will be fire alarm integrated, hardware details shall be issued by April 1st week. • No change for interconnecting door WD12 hardware, contractor to follow issued hardware schedule, attached herewith for reference. | A |  | 1 2 21
0020 |  | 00 | Kitchen high counter | 05Q¦8F-17F¦DET¦314, 05Q¦8F¦DET¦302.1 | Studio A & B - Apartments | This is to confirm that the comment related to shifting the high kitchen counter 50 mm mentioned on drawing number 1252-MKM-05Q-IDP-01-DWG-301 of submittal MKM-05Q-IDP-01-DS-0019 is not valid anymore and will be cancelled. | NAM | MKM | 2017-02-13 | 2017-02-13 | 0 | Yes, confirmed. The comment is not valid | A |  | 1 2 22
0021 |  | 00 | Sink specifications | 05Q¦8F-17F¦DET¦334, 05Q¦8F-17F¦DET¦362 | Apartments – high counter & laundry room | Please provide the selection and technical specifications for the following items: - High counter built in sink and mixer (apartments) - Laundry room sink and mixer (apartments) | NAM | MKM | 2017-02-19 | 2017-02-21 | 2 | REFER TO TRANSMITTAL MKM-05Q-IDP-01-TM-GREENLINE-0012 DATED 20/02/17 ALSO ATTACHED FOR EASY REFERENCE. | A |  | 1 2 22
0022 |  | 00 | Electrical Hub | 05Q¦24F-36F¦DET¦0324 | All apartments and Guest rooms | Please provide the technical data sheets for the electrical hub to be inserted in all work desks as per the attached drawing | NAM | MKM | 2017-02-19 | 2017-02-21 | 2 | REFER ATTACHED SPECIFICATION SHEETS FOR HUB AND FRAME COVER. | A |  | 1 2 22
0023 |  | 00 | MEP Services Clash with ID Design |  | 8th Floor – Apartment No. 801, 803, 804, 806, 808 & 809 | Reference to the above subject; please be informed that some of the MEP services located at apartment’s no. 801, 803, 804, 806, 808 & 809 are clashing with the ID design hence with the specified FCL as shown in the attached photos and drawing where the existing AC duct height is +3000 and the FCL also is +3000 MM in addition to other clashes, please be noted that at least we need 75 mm clear gap for the suspended ceiling system. Kindly advise… | NAM | MKM | 2017-02-19 | 2017-02-22 | 3 | DUE TO SITE STRUCTURAL LEVEL CONSTRAINT ON LEVEL 8, THE REVISED CEILING LEVELS ARE MASKED IN RED. | A |  | 1 2 22
0023 |  | 01 | MEP Services Clash with ID Design |  | 8th Floor – Apartment No. 801, 803, 804, 806, 808 & 809 | Reference to your reply on the previous revision, please find attached marked plan showing the updated achievable FCL for the affected area as per the last modification done by the MEP contractor since the progress for MEP 1st fix still on going. Please confirm the mentioned heights… | NAM | MKM | 2017-03-04 | 2017-03-06 | 2 | CONFIRMED THE FCL HEIGHT AT 8TH FLOOR ONLY AS PER THE ATTACHED MARKED PLAN. | A |  | 1 2 22
0024 |  | 00 | High Counter Location @ Apartments 801 & 806 |  | 8th Floor – Apartment No. 801 & 806 | Reference to the above subject; please be informed that the location of the “High Counter” @ App. 801 & 806 is conflicting with the “Maids Room Door” WD-3A hence is conflicting with ID drawings. Please refer to the attached photos / marked plan and advise accordingly… | NAM | MKM | 2017-02-19 | 2017-02-21 | 2 | MAIN CONTRACTOR WILL CUT THE ‘NIB’ AND LONG DIMENSION TO 200MM. REFER MARK-UP ON THE ATTACHED PHOTOS HIGHLIGHTED IN YELLOW. | A |  | 1 2 22
0025 |  | 00 | Additional Bulkhead Above TV Unit – Client’s General Comment |  | 8 to 17 Floor – 1, 2 & 3 Bedroom Apartments | Reference to the client’s general comment on GLI’s shop drawings pertaining to add additional bulkhead above the T.V unit as per the attached commented drawing, please be informed that this comment is not applicable /achievable due to MEP height issues. Please refer to the attached marked plan and advise accordingly. | NAM | MKM | 2017-02-21 | 2017-02-23 | 2 | KINDLY REVIEW SITE CONDITION, INDIRECT LIGHT (ROPE) IS ONLY ON ONE SECTION (INDICATED IN RED) AND NOT ON ALL WALL-TV UNIT. WE BELIEVE THAT IT CAN BE EXECUTED – PROCEED ACCORDINGLY W/ WORKS. | A |  | 1 2 27
0025 |  | 01 | Additional Bulkhead Above TV Unit – Client’s General Comment |  | 8 to 17 Floor – 1, 2 & 3 Bedroom Apartments | Reference to your reply on the previous revision regarding the unachievable cove light above the living room T.V unit; kindly be informed that the site condition has been reviewed and the height issue (clashes) with the MEP services still existing, please refer to the enclosed photos and advise accordingly… | NAM | MKM | 2017-03-04 | 2017-03-06 | 2 | NOTED- COVE LIGHT IN THAT PARTICULAR AREA “TV UNIT” IS 1,2,3 BEDROOM UNITS TO BE CANCELLED. (ONLY LEVEL 8) | A |  | 1 2 27
0026 |  | 00 | Width of tiles Joints | 05Q¦8F¦WF¦0107.35 | All Apartments | Please confirm the required width for the joints of the following tiles types: - ST-010: 450x900mm Argenta Full Body Porcelain Tile at Bathrooms walls and floors - ST-010.1: 600x600mm Argenta Full Body Porcelain Tile at guest toilets floors - ST-010.2: 600x300mm Argenta Full Body Porcelain Tile at guest toilets walls - ST-011: 600x600mm Porcelain Tile "Fotiles TD126008M" for living/kitchen/corridor - ST-011.1: 600x120mm porcelain skirting "Fotiles TD126008M" for living/kitchen/corridor - ST-012: 330x330mm RAK Ceramic Tile A04RZSPC-WH0-MOU for Laundry/Maid room/maid toilet floors - ST-013: 250x330mm RAK Ceramic Tile CALIXTO "A50RCALX-WH0.G0U" for Laundry/maid toilet walls | NAM | MKM | 2017-02-27 | 2017-03-09 | 10 | FOLLOW MOCK UP AS DISCUSSED IN PROGRESS MEETING FOR ST-012 & ST-013- FOLLOW 2MM GROUT LINES. | A |  | 1 2 27
0026 |  | 01 | Width of tiles Joints | 05Q¦8F¦WF¦0107.35 | All Apartments | Note that the reply on RFI-0026-00 dated March 09,2017 does not provide sufficient and clear information for the grout size of the following tiles types: - ST-010.1: 600x600mm Argenta Full Body Porcelain Tile at guest toilets floors - ST-010.2: 600x300mm Argenta Full Body Porcelain Tile at guest toilets walls - ST-011: 600x600mm Porcelain Tile "Fotiles TD126008M" for living/kitchen/corridor - ST-011.1: 600x120mm porcelain skirting "Fotiles TD126008M" for living/kitchen/corridor You are kindly requested to provide the above information by type. | NAM | MKM | 2017-03-21 | 2017-03-27 | 6 | Follow 2mm grout size for all the above tiles types’ i.e for ST-010.1, ST-010.2, ST-011 & ST-011.1 | A |  | 1 2 27
0027 |  | 00 | Joinery Drawer runner | 05Q¦8F-41F¦DET¦334 | All units | You are kindly requested to confirm that the drawer runners will remain bottom fixing type as per the approved sample for the following items: - Wardrobes - Pantry units - Kitchen high counter - TV units - Work desks at Guest rooms And will be replaced by side fixing type at the following units: - Work desks at apartments - All night stands Hardware schedule is attached for your reference | NAM | MKM | 2017-03-07 | 2017-03-08 | 1 | We would like to see sample of side runner soft close prior to approval on replacement. | A |  | 1 2 27
0027 |  | 01 | Joinery Drawer runner | 05Q¦8F-41F¦DET¦334 | All units | You are kindly requested to confirm that the drawer runners will be replaced by side fixing type at the following units: - Work desks type 1 at Studio A and B - Wardrobe at maid rooms at 3 bedroom and 2 bedroom apartments. Revised hardware schedule is attached for your reference | NAM | MKM | 2017-03-21 | 2017-03-27 | 6 | FOLLOW MATERIAL SUBMITTAL APPROVED ‘MS-0065 (ATTACHED) | A |  | 1 2 27
0028 |  | 00 | Back Sofa Unit at 3 Bedroom apartment | 05Q¦8F¦GA¦0107.41 | All Apartments | This is to confirm if the Back sofa unit at 3 bedroom apartments from floors 8 to 13 is a loose item, otherwise please provide the detail drawing for this item in order to prepare the shop drawings. | NAM | MKM | 2017-03-21 | 2017-03-22 | 1 | Back sofa table not in scope, it is loose item if included in quote, to be omitted. | A |  | 1 2 27
0029 |  | 00 | Installed Cistern At Apartment 802 clashing with ID drawings | 1252¦MKM¦05Q¦IDP¦01¦DWG¦0409 | Apartment 802 | Please be informed that the existing installed cistern unit @ Bathroom - Apartment 802 has 160 MM depth from the adjacent wall which is clashing with the ID drawings and approved SD consequently. Please refer to the attached photo and advise accordingly. | NAM | MKM | 2017-03-27 | 2017-03-28 | 1 | PROCEED AS PER SITE CONDITIONS | A |  | 1 2 27
0030 |  | 00 | Mini bar fridge | 05Q¦8-41F¦DET¦0331 | Guest rooms – 19th to 41st floor | Please provide the technical data of the mini bar fridge including dimensions. | NAM | MKM | 2017-03-27 | 2017-03-30 | 3 | REFER ATTACHED SPECIFICATION FOLLOW MOCK-UP FOR DIMENSIONS. | A |  | 1 2 27
0031 |  | 00 | MEP Clashes with the Specified FCL @ 8th Floor Corridor | 1252¦MKM¦05Q¦IDP¦01¦DWG¦0712 | 8th Floor corridor | Please be informed that the existing MEP elements installed at the ceiling of 8th Floor Corridor Area are clashing with the specified FCL as shown on the attached photos. Moreover; please find attached the achievable FCL marked on the pertinent plan for your kind review and confirmation. | NAM | MKM | 2017-03-27 | 2017-03-30 | 3 | • AS DISCUSSED IN THE PROGRESS MEETING ON 28TH MARCH 2017 CO-ORDINATE IN THE SITE AND PROCEED WITH THE MOCK-UP WORKS AS INSTRUCTED VIA CLIENT’S INSTRUCTION-0013. TAKE FROM THE MOCK UP. AS DISCUSSED FOLLOW THE CEILING LEVELS ARE +2550MM & +2400MM. | A |  | 1 2 27
0032 |  | 00 | Corridor details at Floor 16 | 1252¦MKM¦05Q¦IDP¦01¦DWG¦0713 | 16th Floor corridor | As per your instruction and comments on corridor drawing 1252-MKM-05Q-IDP-01-DWG-713 stating that the entrance of the excluded apartment at floor 16 has changed, please send us the latest drawings to incorporate in ours. | NAM | MKM | 2017-03-29 | 2017-03-30 | 1 | DRAWINGS ATTACHED IN CAD & PDF | A |  | 1 2 27
0033 |  | 00 | Lipping color for approved Formica material | 05Q¦8-17F¦DET 334 | Apartments - kitchens | Following your approval for the Formica material submittals MS-0036-02 & MS-0037-02, kindly advice on the color and details of the lipping for the materials. | NAM | MKM | 2017-03-29 | 2017-03-30 | 1 | PVC LIPPING 2MM THICK, COLOR TO MATCH THE APPROVED FORMICA SAMPLES. SUBMIT 300X300MM MOCK-UP SAMPLE FOR FINAL APPROVAL. | A |  | 1 2 27
0034 |  | 00 | MDF and Plywood specifications |  | All floors - Joinery | Please provide the technical specifications for the MDF, MR MDF and the plywood to be able to provide the compliance statement as per the requirements and to avoid another rejection for these materials due to compliance or required standards. | NAM | MKM | 2017-03-30 | 2017-04-04 | 5 | REFER TO THE ATTACHED COMMENTS SHEET | A |  | 1 2 27
0035 |  | 00 | WC Backwall structural work | 05Q¦8F-17F¦DET¦306.1 | All Bathrooms and guest toilets | In relation to the above mentioned subject, please note that our Scope is limited to the Supply & Install Finishes only (i.e. Supply & Install Stone Ledge & Wall Tile only), hence kindly advise the party who shall be responsible to arrange the Structure to receive the finishes in WC Cistern wall to enable us to coordinate accordingly | NAM | MKM | 2017-03-30 | 2017-04-02 | 3 | Already in GLI scope, refer GLI’s approved shop drawings for toilets and Mock-up. Example DWG-0402 Detail 4, DWG-403 detail 6 | A |  | 1 2 27
0036 |  | 00 | Furniture interface with building elevation | 05Q¦8F-17F¦DET¦322.1 | Living rooms & bedrooms of apartments | Following reply to RFI 0036-00 and the new proposed dimensions for the TV units at 1,2 & 3 bedroom apartments, we would like to propose another option as per the attached drawing for the following reasons: - To cover the inclined structural columns with Gypsum board + structure to avoid finished wood cutting on site for better end result. - To center the TV unit as per the drawing with 2 equal size mirrors from both sides - To unify the dimensions every 2 floors to keep the TV centered with sitting area. Kindly advice if we can proceed accordingly. Note that the attached drawing dimensions are for the apartment 901 in process for mock-up | NAM | MKM | 2017-03-30 | 2017-04-05 | 6 | REFER TO THE EMAIL FOR CAD & PDF SK001 & SK002. PROCEED WITH WORKS | A |  | 1 2 27
0036 |  | 01 | Furniture interface with building elevation | 1252-MKM-05Q-IDP-01-DWG-0332-1 | 1, 2 & 3 bedroom apartments | Please advise on the sizes of the units and the interface with building as shown in the attached sections taking into consideration the following: - Building reducing size approximately 14 cm per floor from 8th to 17th floor - Column inside the apartments is at the same angle of the glass façade - If concrete finish to be kept on columns, then the site dimensions may differ by few centimeters between rooms at the same floor which is hectic for production and creates a gap between columns and vertical items (fillers discussed to be avoided) - Production of different dimensions for each floor separately preferred to be avoided | NAM | MKM | 2017-05-02 | 2017-05-08 | 6 | APPROVED AS SUGGESTED & PROPOSED | A |  | 1 2 27
0037 |  | 00 | Main entrance door WD1 | All floors – Apartments & guest rooms doors | 1252¦MKM¦05Q¦IDP¦01¦DWG¦501-02 sheet 1/3 | In regards of the main entrance door WD1, note the following: - The selected concealed door retainer type SC1941 Eurolever does not fit. - As per site conditions, the result will be: Clear opening (frame to frame) is 908mm and clear access with door open is 865mm. Kindly advice about the above to proceed with door details | NAM | MKM | 2017-04-06 | 2017-04-09 | 3 | PROCEED WITH WORKS AS PER THE DETAILS IN YOUR SHOP DRAWING – 501-REV-01 AND COMPLY WITH AUTHORITY REQUIREMENTS. | A |  | 1 2 34
0038 |  | 00 | Wardrobe type 8 site dimensions | 1252¦MKM¦05Q¦IDP¦01¦DWG¦357 sheet 1/2 | Apartments 806 & 1006 | Please note that, reference to site dimension at 3 bedroom apartment (# 0806 & 1006), There is not enough space to accommodate wardrobe type -8. Our approved wardrobe unit depth is 580mm which we can accommodate in all other areas except the Rm # 0806 (2 units) & 1006 (1 unit) where we have structural depth is only 545mm & 558mm. | NAM | MKM | 2017-04-06 | 2017-04-11 | 5 | PROCEED WITH APPROVED DRAWING - 580MM | A |  | 1 2 34
0039 |  | 00 | Twin headboard unit site dimensions | 1252¦MKM¦05Q¦IDP¦01¦DWG¦341 Rev.2 | Apartments 806 & 1006 | According the site dimensions for twin headboard unit type 2 at Level – 08_ 3 bedroom apartment (RM # 0801 & 0806), there is not enough space to accommodate the headboard. The approved width of headboard is 4600mm and available space is 4505mm & 4515mm excluding the curtain/Beam Space. Kindly advise. | NAM | MKM | 2017-04-06 | 2017-04-13 | 7 | Only for Level-8. 1. Reduce all Bedside table 50mm . 2.Reduce gap between beds 100mm, so overall size to be 4350mm. | A |  | 1 2 34
0040 |  | 00 | MEP Clashes with the Specified FCL @ 8th Floor apartments 803 & 804 | 1252¦MKM¦05Q¦IDP¦01¦DWG¦0148 | Maid rooms – Apartments 803 & 804 | Please be informed that the existing MEP elements installed at the ceiling of 8th Floor maid rooms of the 2 bedroom apartments 803 & 804 are clashing with the specified FCL (+2700mm FFL) as shown on the attached photos. Moreover; please find attached the achievable FCL marked on the pertinent plan for your kind review and confirmation. | NAM | MKM | 2017-04-06 | 2017-04-13 | 7 | Proceed with works as per the details given in the mail from MKM dated 11th Aril 2017. The mail copy and markup drawing is attached for your reference. Ceiling height in maid rooms at 803 and 804 will be +2500mm instead of +2700mm Please note that this changes is applicable at 8th Floor only. | A |  | 1 2 34
0041 |  | 00 | WC ledge alignment with structures | 05Q¦9F-13F¦DET¦309 | Bathrooms at Studio B Floor 9 & 10 | Please be informed that by extending the WC ledge to 200 mm, there will be no alignment with the structural wall at bathrooms of Studio B 907, 910, 1007, 1010 as shown in the attached sketches. The same applies for the vanity unit type 2 at studio B No. 1007. Note that the same may apply on other levels once we have site dimensions. | NAM | MKM | 2017-04-12 | 2017-04-16 | 4 | Proceed as per site conditions, Maxmimum 185cm from finish wall. | A |  | 1 2 34
0042 |  | 00 | Kitchen pantries direction | 1252-MKM-05Q-IDP-01-DWG-0302 | Apartments – All units | Please confirm the direction of the pantry units at all apartments, note that the detail drawings showing the fridge from the open side of the kitchen and approved general floor plan not matching. | NAM | MKM | 2017-04-17 | 2017-04-19 | 2 | FOLLOW THE BLOWUP LAYOUT OF THE UNIT, POWER FOR FRIDGE IS ALREADY ALLOCATED CANNOT BE SHIFTED COMMENTS ATTACHED. | A |  | 1 2 34
0043 |  | 00 | Wood skirting at Glass elevation | 1252-MKM-05Q-IDP-01-DWG-0368 – 1/3 – R1 | Apartments – wood skirting at windows | Following the shop drawing approval DS-0057-1 in regards of the skirting detail and the comment to have it 120mm under the window, note that the intersection at the corner with the other wall wood skirting will be as per the attached sketch. Please confirm approval. | NAM | MKM | 2017-04-17 | 2017-04-19 | 2 | PROCEED WITH WORKS AS PER THE SKETCH | A |  | 1 2 34
0044 |  | 00 | Corridor balustrade detail | 1252-MKM-05Q-IDP-01-DWG-712 | Corridors ceiling – 8th to 17th Floor | Please provide the balustrade fixing detail at the corridors as per the commented drawing 1252-MKM-05Q-IDP-01-DWG-0712 drawing submission SD-0059-0 in order to complete our gypsum ceiling details. | NAM | MKM | 2017-04-17 | 2017-04-19 | 2 | REFER TO THE ATTACHED SKETCH MKM-05Q-IDP-1-SK-001 | A |  | 1 2 34
0045 |  | 00 | Lock for DB and GRMS access doors | 05Q-8-41F-DET-0332-1 | Wardrobes – All floors | Please confirm if a lock is required and approved for the GRMS and DB access doors. Note that it is mentioned on the IFC drawings but not installed on the mock up. | NAM | MKM | 2017-04-17 | 2017-04-19 | 2 | GRMS DOOR REQUIRES LOCK- NOTE THAT IT WAS INSTALLED ON THE MOCKUP & GLI REMOVED. L-19 TO 41. | A |  | 1 2 34
0046 |  | 00 | Fret cut Screen Color | 05Q-19-23F-DET-0328 | Headboards – Junior suites | Following comments on Material submittal MS-0066-01 in regards of Junior suites headboards fret cut screen, please specify the replacement color to use. | NAM | MKM | 2017-04-30 | 2017-05-02 | 2 | PAINT FINISH AS ON SAMPLE IS APPROVED, NO REQUIREMENT FOR ALTERNATIVE. | A |  | 1 2 38
0047 |  | 00 | Bulkhead detail above pantry unit | 1252-MKM-05Q-IDP-01-DWG-0601 | Kitchens – 1,2,3 bedrooms apartments | Reference to FCL height changes confirmed through an RFI no. 0023-01 where the ceiling height has been dropped down from +2700 to +2400 @ Kitchen area, Kindly confirm the Bulkhead Details above Pantry Unit @ 1,2,3 Bedrooms Apartments. | NAM | MKM | 2017-04-30 | 2017-05-02 | 2 | BULKHEAD IS TO BE DIVIDED IN 2 EQUAL STEPPING DETAILS | A |  | 1 2 39
0048 |  | 00 | Shadow gap at TV unit type 2&4 | 1252-MKM-05Q-IDP-01-DWG-0332-01 | Apartments 1,2&3 bedrooms – TV units | Kindly clarify if the “F” shadow gap angle is required for the TV unit (Type 2 & 4) where we have the PT-602 Paint finish for the termination between the said unit and ceiling at 1,2,3 Bedrooms Apartments. | NAM | MKM | 2017-04-30 | 2017-05-02 | 2 | TO ADVICE THE MIN. AVAILABLE “F” CHANNEL FOR SHADOW GAP (MAX 10MM) & TO VERIFY W/ PAINT APPLICATORS THE DETAIL OF HOW TO TERMINATE THE PAINT EDGE | A |  | 1 2 40
0049 |  | 00 | Wall paneling at floor 16 | 1252-MKM-05Q-IDP-01-DWG-713 | Corridor – Floor 16 | Kindly clarify the intersection detail of the wall paneling at the corner of apartment 1601 | NAM | MKM | 2017-04-30 | 2017-05-02 | 2 | WILL SEND A REQUEST TO REVISE THE OPENING LOCATION, SHIFTING THE DOOR 400MM AS MARKED – IN ORDER TO ACCOMMODATE ALL THE DETAILS AROUND. | A
0050 |  | 00 | Tile slope towards drainage |  | Showers- all Bathrooms | Reference to our several progress meetings and site walk; Kindly be informed that item 10.5.9 “Tiles Method Statement” cannot be provided since the existing screed does not respect the mentioned slope percentage ( 2:100 ) taking in consideration tile’s big size dimensions | NAM | MKM | 2017-04-30 | 2017-05-02 | 2 | DISCUSSED IN PROGRESS MEETING ON 2 MAY 2017, SLOPE REQUIRED TOWARDS DRAIN IN ALL TOILETS. WHERE EVER SLOPE CANNOT ACHIEVED DUE TO SCREED DEFECTS NEED TO BE OFFICIALLY REPORTED TO MKM WHICH WILL BE FORWARDED TO MAIN CONTRACTOR FOR RECTIFICATION WITH DUE CONSIDERATION FOR RESULTING IMPACT. | A
0051 |  | 00 | Vertical groove on bulkhead |  | Ceiling bulkheads – All apartments | Reference to your instruction to proceed with a vertical shadow gap between gypsum bulkhead and plaster finish, please refer to the attached photos and advise to proceed accordingly. | NAM | MKM | 2017-05-01 | 2017-05-02 | 1 | NOT REQUIRED IN THIS LOCATION. | A |  | 1 2 41
0052 |  | 00 | DB panels at floors 8 to 17 | 05Q¦8F¦GA¦0107-1 | Apartments – 1, 2 & 3 bedroom apartments | Please clarify the finish at the highlighted areas (DB panel) in the attached plan for floors 8 to 17 | NAM | MKM | 2017-05-02 | 2017-05-30 | 28 | TO FOLLOW THE SAME CONCEPT CABINET DB/GRMS IN STUDIO A&B: SHUTTERS ONLY, NO SHELVING NO STORAGE BELOW SUBMIT SKETCH/DRAWING FOR APPROVAL AS PER SITE CONDITION. | A |  | 1 2 41
0053 |  | 00 | CEILING & CURTAIN BULKHEAD DETAILS FOR MAID’s ROOM | 1252-MKM-05Q-IDP-01-DWG-0165-REV-1 | MAID ROOMS – 2,3 Bedrooms apartment | Reference to the highlighted areas on the attached drawings and furthermore the attached photos, Kindly provide us the ceiling and curtain bulkhead details at maid rooms (2&3 Bedrooms apartments). | NAM | MKM | 2017-05-07 | 2017-05-18 | 11 | Ceiling recess details for roller bland attached. | A |  | 1 2 41
0054 |  | 00 | False ceiling detail at 9 to 17 floor apartments | 1252-MKM-05Q-IDP-01-DWG-0171-REV-1 MKM-05Q-IDP-01-TM-Greenline-00016 | 1,2 &3 Bedrooms apartment floors 9 to 17 | Reference to M/s MKM’s transmittal no. DT-MKM-05Q-IDP-01-TM-Greenline-00016 dated April 18,2017, where the FCL height was dropped down in several locations. Kindly please provide us the new ceiling’s design / Sections as highlighted on the attached drawings to implement those changes in our SD. | NAM | MKM | 2017-05-08 | 2017-05-22 | 14 | REFER TO THE ATTACHED (3) BLOW UP PLANS FOR UNITS 1 BEDROOM, 2 BEDROOM & 3 BEDROOM | A |  | 1 2 41
0054 |  | 01 | False ceiling detail at 9 to 17 floor apartments | 1252-MKM-05Q-IDP-01-DWG-0171-REV-1 MKM-05Q-IDP-01-TM-Greenline-00016 | 1,2 &3 Bedrooms apartment floors 9 to 17 | Following your reply to RFI-0054 note that the Maid room ceiling is not correct and requires clarification for the levels and the AC supply. | NAM | MKM | 2017-05-25 | 2017-05-29 | 4 | Maid’s bedroom ceiling is 2700mm for the 2BR unit & 2400/2700 mm for the 3BR units | A |  | 1 2 41
0055 |  | 00 | KITCHEN Unit and High Counter Inside Finish |  |  | Kindly advice if the laminate finish inside of the cabinets of the pantry unit and the high counter as highlighted in the attached drawings can be melamine matching color for technical and time consuming reasons, and also clarify the color for the following areas: - The carcass of the unit - The type 1 Formica drawers and cabinets - The type 2 laminate drawers and cabinets - The type 3 Formica drawers and cabinets | NAM | MKM | 2017-05-10 | 2017-05-18 | 8 | All cabinet (carcess + drawers + under counter cabinet are in grey laminate (Formica). All drawer in white (F) laminate, Fascia of door shutters or drawers as previously approved. | A |  | 1 2 41
0056 |  | 00 | Additional support for work desks | 1252-MKM-05Q-IDP-01-DWG-0323 | Work desks – 1, 2 & 3 bedroom apartments – floors 8 to 17 | Kindly advice if an additional support can be provided for the work desks type: 2-2A-2B-2C-3-3A-5-5A. If yes, please confirm the location of the support | NAM | MKM | 2017-05-22 | 2017-05-24 | 2 | • Incomplete reference, IFC drawing and commented shop drawing not attached. • Contractor to provide sufficient support for the safe service life of the work desk complying with the design intend as per issued IFC drawings. • Steel sections for support bracket to be box sections and not ‘L’ angle sections. | A |  | 1 2 41
0057 |  | 00 | Access Panel 808-809 |  | Apartments 808-809 | Further to your comments on DS-0005-01; please be informed that the required design for the Access Panel cannot be achieved due to MEP clashes. Please refer to RFI no. 0023-01 for your reference and advise accordingly. | NAM | MKM | 2017-05-18 | 2017-05-22 | 4 | THE RAISED RFI IS NOT CLEAR, KINDLY RESEND W/ SUPPORTED DOCUMENTS | A |  | 1 2 41
0057 |  | 01 | Access Panel 808-809 |  | Apartments 808-809 | Further to your comments on DS-0005-01, please be informed that required design for access panel cannot be achieved due to MEP clashes. Please refer to RFI no. 0023-01 for your reference and advise. | NAM | MKM | 2017-05-23 | 2017-05-23 | 0 | Refer to sketch to dwg (A3 paper) | A |  | 1 2 41
0058 |  | 00 | Laundry room door WD3 | 05Q¦8F¦DET¦0302.7 1252-MKM-05Q-IDP-01-DWG-0602_R1 1252-MKM-05Q-IDP-01-DWG-0504_R1_BEDROOM DOOR (WD3) | Laundry room at Studio A, Studio B, 2 bedrooms & 3 bedrooms apartments – 8 to 41st floor | In relation to the above mentioned subject, note that the laundry room wood door is same as the bedroom door type WD3, although it was approved in a different drawing 1252-MKM-05Q-IDP-01-DWG-0602_R1_FLOORING TYPICAL DETAIL to have a 10mm raised threshold for the same area. Kindly advice if the detail should follow the previously approved WD2 for the bathroom with the threshold below the frame or simply below the door leaf. | NAM | MKM | 2017-05-25 | 2017-05-29 | 4 | Threshold to be raised by 10mm if it plays a separation between dry/wet zone. Yes, implement to threshold between corridor/pantry bedroom/bathroom. | A |  | 1 2 41
0059 |  | 00 | Wood door WD3 frame detail | 1252-MKM-05Q-IDP-01-DWG-0504_R1_BEDROOM DOOR (WD3) 1252-MKM-05Q-IDP-01-DWG-0502_R3_BATHROOM DOOR (WD2) | Wood doors – All apartments | Please advise if the approved door detail WD3 drawing 1252-MKM-05Q-IDP-01-DWG-0504 should follow the recently approved detail and sample of door frame WD2. | NAM | MKM | 2017-05-25 | 2017-05-29 | 4 | Keep WD2 & WD3 as drawn | A |  | 1 2 41
0060 |  | 00 | Glass schedule | 1252-MKM-05Q-IDP-01-DWG-332 | All | Further to the comments received on the shop drawings and our discussions, please find attached a schedule for the glass/mirror distribution for your approval. Note that item labeled as “grey mirror” is considered new material and sample will be submitted for approval. | NAM | MKM | 2017-05-28 | 2017-05-30 | 2 | Refer to comments attached to the RFI documents | A |  | 1 2 41
0060 |  | 01 | Glass schedule | 1252-MKM-05Q-IDP-01-DWG-331 |  | Further to your reply to RFI-0060-00, note that the schedule at page 2 mentions that item W-701 not available at 19 to 23 floor wall units while drawing of TV unit type 1 page 5 mentions clearly that the unit has both AW-701 & AW-702. | NAM | MKM | 2017-06-03 | 2017-06-06 | 3 | Please refer to the previous comments clearly specified type for each and every area – if further classification would be required. If needed update glass schedule for sign off. | A |  | 1 2 41
0061 |  | 00 | PVC lipping at kitchen pantry unit and high counter | 1252-MKM-05Q-IDP-01-DWG-304 | All | Please confirm that the front part of the kitchen pantry and the high counter as highlighted on the attached drawing is in PVC lipping as per the approved sample MS-0081 | NAM | MKM | 2017-05-28 | 2017-05-30 | 2 | Agree, matching color PVC as lipping to be provided – advice if a working-mock up could be seen. | A |  | 1 2 41
0062 |  | 00 | Bathroom door frame size | 1252-MKM-05Q-IDP-01-DWG-502 R3 | All bathrooms | Further to our site measurements we noticed that the bathroom door thickness varies between 145 to 155 mm including wall finishes, for that, we proposed the attached sketch as a development to the previously approved WD2 for your approval. | NAM | MKM | 2017-05-31 | 2017-06-04 | 4 | • The attached sketch is not acceptable. • As discussed follow the site conditions for 8th floor. • M/S GLI make sure that all door frame thickness should be uniform for the 9th and above floors and M/S GLI should notify to MKM if any difference in plaster thickness of more than 5 to 10mm before proceeding to tiling works. • MKM will instruct M/S AFGC to rectify the same. | A |  | 1 2 41
0063 |  | 00 | Wardrobe finger pull | 1252-MKM-05Q-IDP-01-DWG-351 | All wardrobes | Please confirm replacing the approved finger pull detail for all wardrobes to match the existing at the mock-up room as per the attached detail. | NAM | MKM | 2017-06-06 | 2017-06-15 | 9 | APPROVED AS PROPOSED IN SKETCH AND AS IN MOCK UP ROOM. | A |  | 1 2 41
0064 |  | 00 | Pantry unit elevation details | 1252-MKM-05Q-IDP-01-DWG-305 | All wardrobes | Further to our discussion in regards to the pantry units, please find attached the proposed detail drawing for your approval. | NAM | MKM | 2017-06-11 | 2017-06-12 | 1 | Incomplete RFI, revise and resubmit old & new drawings, Highlighted changes, correct narative. | A |  | 1 2 41
0064 |  | 01 | Pantry unit elevation details | 1252-MKM-05Q-IDP-01-DWG-305 | All wardrobes | In regards to the pantry units details for all apartments, and following MKM inspection of item at GLI factory, please confirm the attached revised detail drawing with the following changes: - Under counter drawers and cabinet doors are extended to cover the vertical partitions - Vertical partition separating tall unit from counter unit is reduced from 60 mm to 30 mm - Revised dimensions due to the above changes. | NAM | MKM | 2017-06-17 | 2017-06-18 | 1 | REFER TO THE ATTACHED COMMENTS – DWG 305-REV-4 | A |  | 1 2 41
0065 |  | 00 | Work desks length | 1252-MKM-05Q-IDP-01-DWG-323A-R2 | Work desks – 1,2&3 bedroom apartments | In regards of the work desks type 2, 2A, 2B, 3, 3A, 5 & 5A, it is logistically not possible to take the unit in 1 piece inside the rooms due to the narrow corridors and turns. For that we propose a joint as per the attached detail and a leg at the drawer level as per previous discussions to help in stability of the unit. | NAM | MKM | 2017-06-12 | 2017-06-18 | 6 | REFER TO SKETCH ON BACK PAGE | A |  | 1 2 41
0066 |  | 00 | 8th Floor access panels | MKM-05Q-IDP-01-TM-Greenline-0018_Approved RCP 8th Floor Drawing | Access panels apartments 801 & 806 | In regards of the received transmittal “MKM-05Q-IDP-01-TM-Greenline-0018_Approved RCP 8th Floor Drawing” , note that all access panels of unit 801 and 806 are shown as double line, please clarify if these access panels are at the same level of the ceiling (except for the master bathroom approved previously) or they should follow the same mock-up detail of 2 steps up. | NAM | MKM | 2017-06-21 | 2017-06-28 | 7 | DOUBLE LINE REQUIRED FOR MASTER BATHROOM + KITCHEN PANTRY (WHERE INDICATED) ONLY. | A |  | 1 2 41
0067 |  | 00 | Wall panel detail at corner shaft door 8 to 17 | 1252-MKM-05Q-IDP-01-DWG-0710-R2_CORRIDOR WALL PANELING LAYOUT | Corridors – 8 to 17th floors | Note that the wall paneling detail at the 8 to 17th floor corridor is clashing with the corner shaft metal door. Please advise a solution for the metal door to allow for both doors (metal and wood) to open at 90 degrees. | NAM | MKM | 2017-06-21 | 2017-07-03 | 12 | proceed with work-DWG-0710/2/2/R1 | A |  | 1 2 41
0068 |  | 00 | 0068-00_Misalignement between corner wall and curtain box at Maid rooms of 2 bedroom units | 05Q¦9F-13F¦RCP¦0148¦R1 | Ceiling at maid room – 2 bedroom apartments 003 & 004 | All 2 bedroom apartments from floor 9 to 17 have misalignment between the corner wall and the curtain box at maid rooms as per the attached pictures. If this is not accepted to remain please advise a solution for the alignment. | NAM | MKM | 2017-07-09 | 2017-07-09 | 0 | • THE DESCRIPTION & ATTACHMENT IS CONTRADICTORY (LOCATIONS). SO THE RFI REJECTED. RESUBMIT WITH CORRECT LOCATIONS. | A |  | 1 2 41
0068 |  | 01 | Misalignement between corner wall and curtain box at bedroom 1 of 2 bedroom apartments | 05Q¦9F-13F¦RCP¦0148¦R1 | Ceiling at maid room – 2 bedroom apartments 003 & 004 | All 2 bedroom apartments from floor 9 to 17 have misalignment between the corner wall and the curtain box at bedroom 1 as per the attached pictures. If this is not accepted to remain please advise a solution for the alignment. | NAM | MKM | 2017-07-20 | 2017-08-01 | 12 | • PROCEED TO FIX THE CURTAIN BULK HEAD, WHERE THE OFFSET IS LESS THAN 25MM. • BLOCK WALL OFFSET MORE THAN 25MM WILL BE RECTIFIED BY MAIN CONTRACTOR. | A |  | 1 2 41
0069 |  | 00 | Headdboard location | 1252-MKM-05Q-IDP- 01-DWG-0101 | All apartments bedrooms – 8 to 17th floor | Please clarify the location of the headboard in all rooms. Note that we can follow one of the two options: - Fixed dimension from the adjacent wall - Center of the wall behind the headboard | NAM | MKM | 2017-07-11 | 2017-07-13 | 2 | CONTRACTOR TO CHECK THE SECTIONAL BUILDING DRAWINGS TO VERIFY THE BED’S HEAD BOARD CENTER LINE IN EACH FLOOR (8TH TO 17TH). WE BELIEVED THE DIMENSION REFERENCE TO FOLLOW IS FROM THE BATHROOM BLOCK WORK. EITHER DECREASING OR INCREASING THE DIMENSION IN EACH FLOOR. BUT CONTRACTOR TO VERIFY. | A |  | 1 2 41
0070 |  | 00 | Maid’s and store skirting detail | 1252-MKM-05Q-IDP- 01-DWG-0368 1/3 | Maid room & Stores – All apartments – 8 to 17th floor | Please be informed that the approved details of the Skirting of the Maids Room & Store (RAK Ceramic) is not applicable since it is RED Body and chamfering 45 degrees cannot be applied; Therefore we propose proceeding without any chamfering . | NAM | MKM | 2017-07-13 | 2017-07-16 | 3 | • PLEASE PROCEED WITHOUT ANY CHAMBERING AS INSTRUCTED DURING SITE WALK ON 9TH JULY 2017. • PROVIDE MOCK UP AND GET APPROVED BEFORE PROCEED WITH WORKS. | A |  | 1 2 41
0071 |  | 00 | WC Marble Ledge | 1252-MKM-05Q-IDP- 01-DWG-0403 | All bathrooms , WC ledges | We propose to have the WC Ledge into 2 Pcs with a joint. Our concern that when we apply the cutting for the Push Plate it will be broken if we will go with 1 full piece as per SD. Please confirm the location of the joint if approved either to be on the center of WC wall or Center of the Push Plate. | NAM | MKM | 2017-07-13 | 2017-07-19 | 6 | • M/S GLI ALREADY HAD A COMMUNICATION WITH M/S STONE FACTORY • PLEASE FIND THE ATTACHED DRAWINGS SHOWING THE LOCATION OF THE JOINT FOR DIFFERENT TYPES OF TOILETS – MARBLE LEDGE CUTTING JOINT. • PROVIDE REINFORCEMENT FOR MARBLE AT PUSH PLATE AREA. • PLEASE FOLLOW THE ATTACHED DRAWINGS FOR THE LOCATIONS OF MARBLE JOINTS. | A |  | 1 2 41
0072 |  | 00 | Store shaft steel door SD-25 | 1252-MKM-05Q-IDP- 01-DWG-0101 | All store rooms – 8 to 41st floor | Further to the attached highlighted drawing ; we require the details of the Laundry/Store Shaft's steel Door SD-25 to proceed with the tiling works | NAM | MKM | 2017-07-20 | 2017-07-22 | 2 | PLEASE FIND THE ATTACHED DETAILS OF SHAFT STEEL DOOR SD-25 | A |  | 1 2 41
0073 |  | 00 | Corridor wall paneling detail | All corridors – 8 to 41st floor | 1252-MKM-05Q-IDP- 01-DWG-0710 | For MEP purposes, the decorative wood column at the corridor has to shifted to provide 28 mm clear space behind it as per the attached sketch. Please confirm to proceed accordingly. | NAM | MKM | 2017-07-20 | 2017-07-22 | 2 | • APPROVED THE PROPOSAL. • PROCEED THE WORKS AS PER THE PROPOSAL. | A |  | 1 2 41
0074 |  | 00 | Dry wall joint @ 1 bedroom apartments | 1252-MKM-05Q-IDP- 01-DWG-0134 | 1 Bedroom apartments – 8 to 17th floor | Please advise if a joint is required at the additional dry wall at the 1 bedroom apartments between 2 different materials as per the attached pictures | NAM | MKM | 2017-08-02 | 2017-08-02 | 0 | THE ADDITIONAL CLADDING TO BE CANCELLED. REFER TO ATTACHED | A |  | 1 2 41
0075 |  | 00 | Laundry room wall finishes @ 1 bedroom | 1252-MKM-05Q-IDP- 01-DWG-0134 | 1 Bedroom apartments – 8 to 17th floor | Please refer to the attached approved drawings showing Laundry Wall Finish @ Apartments 8 & 9 to be tile finish, Please note that there is no door & Door frame to be installed at the entrance, hence tiles edges at the entrance will be visible and the bathroom door frame will be increased. Hence we recommend to have tile on the laundry cabinet back wall only. | NAM | MKM | 2017-08-02 | 2017-08-02 | 0 | NO TILES TO WALLS EXCEPT BACK WALL OF COUNTER, REFER TO ATTACHED. | A |  | 1 2 41
0076 |  | 00 | Fret cut screen paint color | 1252-MKM-05Q-IDP- 01-DWG-0344 | Headboards – Junior suites | Reference to material submittal MS-0066 in regards of the fret cut screen for the Junior suites headboards and the niches, and the comment “Paint on fret cut screen is yet to be approved”, please confirm the paint color to be aplied | NAM | MKM | 2017-08-14 | 2017-08-16 | 2 | FRET CUT PATTERN WITH PAINT WAS SUBMITTED AS MS-066 REV-01 AND THE PAINT COLOR ON THE SAMPLE US APPROVED – KINDLY RESUBMIT ALL CODE FOR PAINT/ACRYLIC ETC, AS ALL COMPLIED UNDER ONE DOCUMENT/DRAWING. | A |  | 1 2 41
0077 |  | 00 | One Bedroom suite B toilet column | 1252-MKM-05Q-IDP- 01-DWG-0366 | 1 Bedroom suite B – Guest toilet – Floors 19 to 23 | Reference to the drawing nbr 1252-MKM-05Q-IDP- 01-DWG-0366 and the attached sketch showing that the corner column at the mentioned toilet is smaller than the WC backwall ledge. Note that this wall should be flush to the cistern ledge = 185 mm as previously approved. Kindly give instructions to the main contractor to rectify to 185 mm or advice about an alternative solution. | NAM | MKM | 2017-08-23 | 2017-08-26 | 3 | PLEASE PROCEED WITH ATTACHED DRAWING AS HIGHLIGHTED (CEMENT BOARD BACKING) & FLUSH WITH CISTERN LEDGE. | A |  | 1 2 41
0078 |  | 00 | One Bedroom suite A – TV unit finishes | 1252-MKM-05Q-IDP- 01-DWG-0331 | 1 Bedroom suite A – TV unit – Floors 19 to 23 | Reference to the drawing nbr 1252-MKM-05Q-IDP- 01-DWG-0331 in regards of the TV unit type 1 at the 1 bedroom suite type A – please clarify the missing finishes as per the highlighted attached drawings | NAM | MKM | 2017-08-26 | 2017-08-28 | 2 | REFER TO COMMENTS ATTACHED. 1- MIRROR FOR MINI BAR IS CODE 702 (ARTIC BRONZE MIRROR) 2- MIRROR NEAR TV UNIT IS GREY MIRROR CODE 701. 3- FINISH OF MINI BAR IS VENEER (VISUAL ATTACHED) | A |  | 1 2 41
0079 |  | 00 | Maid bathroom glass shelves | 1252-MKM-05Q-IDP- 01-DWG-0401 | 3 bedroom apartments – Maid bathrooms | Reference to the drawing nbr 1252-MKM-05Q-IDP- 01-DWG-0401 in regards of the 3 bedroom apartment maid’s bathroom – please clarify the specification of the glass shelves to be fixed in the highlighted niche, in addition to the quantity of shelves and/or distance between each other | NAM | MKM | 2017-09-14 | 2017-09-19 | 5 | ADD 2 SHELVES IN 18MM WHITE MELAMINE, PVC EDGE LIPING, W=600MM. W/SHELF SUPPORT SUITABLE | A |  | 1 2 41
0080 |  | 00 | Access card reader location | 1252-MKM-05Q-IDP- 01-DWG-0710 | Corridor – 10 to 17th floor | Reference to the drawing nbr 1252-MKM-05Q-IDP- 01-DWG-0710 in regards of the Corridor wall paneling details and the drawing submittal SD-0059-R1 – please note that the highlighted comment “increase to 200mm for levels 10 and above & 300mm for levels 8 and 9” is not applicable on site since the card reader containment is installed at 200mm to center (picture attached) and it will clash with the door panel. Since the production of all panels for floors 8 to 17 has started, we urge you to give instruction to the MEP contractor to modify as per your comment. | NAM | MKM | 2017-09-14 | 2017-09-19 | 5 | PROCEED WITH 300MM WIDTH PANEL SAME AS 8&9 FLOORS, FOR L10 TO L17 | A |  | 1 2 41
0081 |  | 00 | Main entrance door at 16th Floor private apartment |  | 16th Floor Private Apartment | Reference to the ID drawing nbr 0-0A in relation to the main entrance door of the private apartment of the 16th floor, please confirm if it will be a pivot door as per the ID drawings or a hinged door to follow the other apartments detail from the corridor side. | NAM | MKM | 2017-10-19 | 2017-10-30 | 11 | DOOR WILL OPERATE ON HINGED TYPE TO FOLLOW SAME IRONMONGERY SPECS & CD REQUIREMENTS IN TERM OF FIRE STRIP, ETC. PREPARE SHOP DRAWING FOR MKM APPROVAL (AS THE PROPOSED DETAIL IS NOT SUITABLE FOR LOCAL AUTHORITIES REQUIREMENTS). | A |  | 1 2 41
0082 |  | 00 | Fabrics selection at 16th Floor private apartment |  | 16th Floor Private Apartment | Reference to the above mentioned subject, please specify the selection of the fabrics F01 & F02 as mentioned in the ID drawings | NAM | MKM | 2017-10-19 | 2017-10-30 | 11 | • F01 = JASOER COL.1 ROC – BY DEDAR • F02 = PLUSHY COL. 108 NEVE – BY DEDAR | A |  | 1 2 41
0083 |  | 00 | Kitchen details at 16th Floor private apartment |  | 16th Floor Private Apartment | Reference to the above mentioned subject, Kindly provide the ID drawings for the kitchen to include: - Pantry unit details - Appliances specifications - Kitchen wall finishes | NAM | MKM | 2017-10-19 | 2017-10-30 | 11 | • PREPARE ELEVATION FOR REVIEW – SAME DESIGN AS FOR APARTMENT 8-17 LVL. • APPLIANCES ALL SAME AS FOR APARTMENT EXCEPT | A |  | 1 2 41
0083 |  | 01 | Kitchen details at 16th Floor private apartment |  | 16th Floor Private Apartment | Reference to the above mentioned subject, and following our discussion in this regard, the design of the kitchen should come from the designer because of the following: - Previous design kept on hold due to design change issues. - The other apartment’s pantry unit does not include the sink and the dish washer which are located in the high counter. For that, we cannot propose a design that didn’t exist before and require your assistance in this | NAM | MKM | 2017-12-26 | 2018-01-31 | 36 | REFER TO THE ATTACHED KITCHEN DESIGN CI-0071 FOR YOUR INFORMATION & REFERENCE. | A |  | 1 2 41
0083 |  | 02 | Kitchen details at 16th Floor private apartment |  | 16th Floor private apartment | Reference to the above mentioned subject; kindly provide the specification for sink which was not included in the transmittal # MKM-05Q-IDP-01-TM-Greenline-0065 for to coordinate with shop drawing. | HHS | MKM | 2018-04-15 | 2018-12-04 | 233 | As discussed by Stone Factory with the Client, his response is to decide later on the kitchen sink. Nevertheless, Stone Factory suggested to leave the counter top MDF backing unopen for kitchen sink area & it will be cut further to Client confirmation. | A |  | 1 2 41
0084 |  | 00 | Master bedroom structure wall | 1252-MKM-05Q-IDP-01-DWG-176 | 3 bedroom apartments – Floors 14 to 17 | Reference to the above mentioned subject and approved shop drawings submittals reference DS-0012-01 & DS-0018-0, please confirm if the approved wood structure wall located behind the headboard at the master bedroom of the 3 bedroom apartment has to be changed to follow the same detail as the same location of 9 to 13th floors. | NAM | MKM | 2017-10-19 | 2017-10-22 | 3 | Yes, Proceed accordingly. Same as 9 to 13th floor. | A |  | 1 2 41
0085 |  | 00 | Doors hardware sets at 16th Floor private apartment | ID drawing 2-3A | 16th Floor Private Apartment | In regards of the private apartment at the 16th floor, please provide the ironmongery selection for all door types. | NAM | MKM | 2017-10-19 | 2017-11-06 | 18 | REFER TO THE ATTACHED BRAND-MODEL & FINISH OF ALL INTERNAL DOOR HANDLES | A |  | 1 2 41
0085 |  | 01 | Doors hardware sets at 16th Floor private apartment | ID drawing 2-3A | 16th Floor Private Apartment | In regards of the private apartment at the 16th floor, please provide the ironmongery schedule for all doors. Note that reply to RFI-0085-0 did not include the ironmongery and as per our last meeting we discussed replacing the SOSS hinge and requested the sliding system details | NAM | MKM | 2017-12-26 | 2018-01-31 | 36 | REFER TO THE ATTACHED IRONMONGERY SCHEDULE FOR YOUR ABOVE QUERY. | A |  | 1 2 41
0086 |  | 00 | Entrance doors at 16th Floor private apartment | ID drawing 2-3A | 16th Floor Private Apartment | In relation to the above mentioned subject kindly confirm the following: - Main entrance door: 60 min Fire rated door with card access panel - Back entrance door (kitchenette): NFR, detail to follow other apartments entrance doors but without card access panel. | NAM | MKM | 2017-10-19 | 2017-10-30 | 11 | CONFIRMED | A |  | 1 2 41
0087 |  | 00 | TV unit type 3 Finishes | 1252-MKM-05Q-IDP-01-DWG-0333 | Studio A & B | In relation to the above mentioned subject kindly confirm the following finishes: - Illuminated acrylic: to follow approved material MS-0015 (approved for vanities) or MS-0066 (approved for headboard fret cut screen)? - SS strip: as per approved MS-0007 (for luggage rack) but different dimensions? - Glass AW-703 as per previous communication is black back painted glass, shelves to follow or preferred clear glass? | NAM | MKM | 2017-10-26 | 2017-11-06 | 11 | 1- MILKY WHITE ACRYLIC FOR BACK PANEL. 2- SAME MATERIAL – PROFILE SAME ONLY LENGTH TO BE ADJUSTED AS PER WARDROBE WIDTH. 3- CLEAR GLASS – AS CRYSTAL / LOW IRON TYPE | A |  | 1 2 41
0088 |  | 00 | Corridor wallpaper 8 to 17th Floor | 1252-MKM-05Q-IDP-01-DWG-713-02 | Corridors 8 to 17th floor | In relation to the above mentioned subject note the following comments: - The approved shop drawings SDS-0059-R2 do not show joints on wallpaper - Mock up corridor wallpaper has joints as per the attached pictures - Access panels should be provided for electrical access, therefore at least 1 joint should be provided - Specified wallpaper has a width of 85 cm, and as per previous email from Nagham awaiting your confirmation, we suggest using the fabric of the guest rooms corridors which has a width of 135 cm Please clarify either to use joints for the wallpaper panels or not, and the width of panels related to selection of material. | NAM | MKM | 2017-10-31 | 2017-11-06 | 6 | a- CONTRACTOR TO SHOW NECESSARY JOINTS. b- YES, AGREED & THE JOINT BEEN SUGGESTED & APPROVED FOR ACCESS PANEL. c- REFER TO RESPONSE (B) d- NO ALTERNATIVE IS APPROVED – ONLY SPECIFIED ON USE SPECIFIED WALL PAPER | A |  | 1 2 41
0089 |  | 00 | 16th floor private apartment entrance walls | 1252-MKM-05Q-IDP-01-DWG-713-03 | 16th Floor private apartment entrance | In relation to the above mentioned subject note that the final received IFC dimensions don’t match with the approved corridor shop drawings as per the attached highlighted drawings in terms of wall length and door location. Also note that as per RFI-0049, service door should be shifted 400 mm from the wall and is a left hand side door. Please confirm | NAM | MKM | 2017-11-16 | 2017-12-12 | 26 | REFER TO YOUR ABOVE QUERRY, FIND ATTACHED UPDATED BLOCK WORK OF LEVEL 16 FOR YOUR REFERENCE. DOORSHIFTED 400MM, DOOR SWING REVISED, SLIDING DOOR WALL TO BE SINGLE WALL ONLY | A |  | 1 2 41
0090 |  | 00 | Coffee table veneer | 1252-MKM-05Q-IDP-01-DWG-375-R1 | Coffee tables – all rooms | In relation to the above mentioned subject note that the approved shop drawing 1252-MKM-05Q-IDP-01-DWG-0375 R1 and the approved sample are showing the top veneer in 4 directions, for that we suggest to have it in 3 directions as per the attached pictures to match with the 3 legs of the table. Kindly advice | NAM | MKM | 2017-11-16 | 2017-11-23 | 7 | AGREE – APPROVED ASAP = PLEASE SUBMIT UNIT SCHEDULE FOR SIZES & DIM VERIFICATION. | A |  | 1 2 41
0091 |  | 00 | Wallpaper location at revised 901 | 1252-MKM-05Q-IDP-01-DWG-170-R2 | Wallpapers @ TV walls – Apartment 901 | In relation to the above mentioned subject please find attached the specifications cut sheets and the plans highlighted with the location of wallpapers for your comments and approval. Moreover, the elevations at the workdesks are required to clarify the location of the desks, mirrors and TV. | NAM | MKM | 2018-01-07 | 2018-01-08 | 1 | WALL PAPER MATERIAL & LOCATIONS MARKED IN DRAWING ARE APPROVED. FIND ATTACHED COLORED ELEVATIONS FOR SECONDARY ROOMS. | A |  | 1 2 41
0092 |  | 00 | 16th Floor Electrical Drawings | 1252-MKM-05Q-IDP-01-DS-0069 | Private Apartment 901 | In relation to the 16th floor private apartment and following your comments on the shop drawings to show the electrical points, please provide the MEP details in plans and elevations to be able incorporate these details. | NAM | MKM | 2018-01-18 | 2018-02-06 | 19 | REFER TRANSMITTAL MKM-05Q-IDP-01-TM-GREENLINE-0063 AS A REPLY TO THE ABOVE QUERY | A |  | 1 2 41
0093 |  | 00 | 16th floor apartment kitchen wall finishes | 1252-MKM-05Q-IDP-01-PA-103-00 | 16th Floor Private Apartment Kitchen | In relation to the above mentioned subject please provide the wall finishes specification and detail, including the detail at the corner and termination with doors. | NAM | MKM | 2018-02-14 | 2018-03-10 | 24 | *Refer to I.D / DGA attached drawing & specification *Door termination detail for the shaft should be similar to the shaft door detail between Apartment 1605 & Apt.-1606. | A |  | 1 2 41
0093 |  | 01 | 16th floor apartment kitchen wall finishes | MKM-05Q-IDP-01-RFI-0093-00 | 16th Floor Private Apartment Kitchen | With reference to the reply for RFI # 0093-00, Please confirm the scope of work for shaft door at inside the 1601 apartment’s kitchen. Whether it is GLI scope of work, please furnish the details of same in order to prepare the shop drawing and variation for approval. | NAM | MKM | 2018-04-04 | 2018-04-09 | 5 | Refer to your above querry, the interior door will be GLI scope & the shaft door will be done by Naffco. Details will be as discussed & agreed during meeting yesterday (08 April 2018). | A |  | 1 2 41
0094 |  | 00 | 16th floor master bedroom round stone corner | 1252-MKM-05Q-IDP-01-PA-103-00 | 16th Floor Private Apartment master bedroom | Reference to the above mentioned subject, note that the master bedroom corridor has a round stone as per the attached. Kindly confirm if we can cancel the round corner as per the proposed or keep it round but change the stone finish to a different material that works better with curves. | NAM | MKM | 2018-02-14 | 2018-02-21 | 7 | THE ABOVE QUERY SHOULD BE AS PER I.D. DESIGN APPROVED BY CLIENTS. MATERIAL CANNOT BE REPLACE NCR CANELING THE ROUND CORNER IS NOT ALLOWED. CONTRACTOR / GLI SHOULD PROVIDE THE BEST SOLUTION TO COMPLY WITH THE APPROVED DESIGN. | A |  | 1 2 41
0094 |  | 01 | 16th floor master bedroom round stone corner | 05Q-16F-BL-0172-4 | 16th Floor Master Bedroom Round Stone Corner | Reference to the above mentioned subject, and your comments on RFI-0094-00, note that there is discrepancy between blockwork (round corner) and ID latest drawings (No curves), please advise which one to follow | NAM | MKM | 2018-03-15 | 2018-03-19 | 4 | With regards to your above query, follow as per site condition. | A |  | 1 2 41
0095 |  | 00 | 16th floor Lacquered Wood LW1 | 1252-MKM-05Q-IDP-01-PA-103-00 | 16th Floor Private Apartment master bedroom | Reference to the above mentioned subject, and to your reply to the related Material submittal MS-0097, your comment states that the used code NCS S 1505-Y70R is approved therefore the reply is not clear why it is rejected and what to modify for resubmission. Moreover, we noticed in the 3Dviews that the LW1 in the master bedroom is glossy. Please clarify to submit accordingly. | NAM | MKM | 2018-02-14 | 2018-02-21 | 7 | BASED ON THE ATTACHED MATERIAL DOCUMENT IT IS NOTED 'SUBMIT BIGGER SAMPLE' IN ORDER FOR US TO CLARIFY YOUR ABOVE QUERY. | A |  | 1 2 41
0096 |  | 00 | Handicapped Toilet Door (WD-13) | 1252-MKM-05Q-IDP-01-DWG-0507-00 | 16th Floor Private Apartment master bedroom | Reference to the above mentioned subject, Please note the following issues for handicapped toilet Door (WD-13) and advise. 1. According to the approved shop drawing (SDS # 025-00 Dwg # 1252-MKM-05Q-IDP-01-DWG-0507-00), the clear access opening is 915mm and structural opening is 1080mm. According to the existing site structural opening (1036mm) the mentioned clear opening is not achievable and which would be reduced to 871mm. 2. Threshold Level is same as bathroom floor finish and bedroom floor finish (Carpet). So this may allow water to flow into the bedroom carpet area unless to provide a raised threshold with ramped edge. Please advise. | NAM | MKM | 2018-03-18 | 2018-03-19 | 1 | 1. 915mm clear width is the minimum requirements as per code, therfore Al Faraa should follow the required structural opening as per design. 2. Threshold for handicap toilet should raise 4mm high. | A |  | 1 2 41
0096 |  | 01 | Handicapped Toilet Door (WD-13) & entrance door (WD-01) | 24th to 29rd Floor Handicapped Guest Rooms. | 16th Floor Private Apartment master bedroom | Following the weekly meeting held on 27/03/2018 and the discussion in regards of the handicapped rooms doors, please confirm the final structural opening of the main entrance door and bathroom door of all handicapped rooms floors 24 to 29 in addition to the threshold dimensions | NAM | MKM | 2018-03-27 | 2018-04-01 | 5 | The structural opening for handicapped rooms doors will be 1100mm (Entrance & Bathroom Door).L-24 to L-29 Please ignore the previous RFI reply RFI-0096 dated 18/03/2018 | A |  | 1 2 41
0097 |  | 00 | Fret cut design at Studio A&B TV unit | 418-WAPD-7-408-00 | TV unit at Studio A & B - Apartments | Reference to the above mentioned subject and following the material submittal MS-0120 in this regards, kindly issue the new material specifications along with its design. | NAM | MKM | 2018-03-27 | 2018-04-11 | 15 | New design is under process & shall be issued shortly. | A |  | 1 2 41
0098 |  | 00 | 8th Floor corridor new design – GLI scope | CI-0078 | Corridor at 8th floor | Reference to the above mentioned subject and the received CI-0078 dated Feb. 13, 2018, please clarify the scope of work of GLI at the atrium since the new design includes structural wall, marble cladding & metal fret works. | NAM | MKM | 2018-03-27 | 2018-04-07 | 11 | L-8 Structural wall & metal fret works at exhaust enclosure is under GLI Scope & marble cladding will be by M/S Stone Factory directly under MKM. L-9 to L-17 Balustrade marble coping will be same as before under GLI scope of works. | A |  | 1 2 41
0099 |  | 00 | 8th to 17Th Floors Pantry Unit Filler Panel |  | Corridor at 8th to 17th floors | Based on our “ Weekly Progress Meeting” discussions dated March 27, 2018 regarding pantry units Type 2/2A & Type 3/3A revised shop drawings, which were rejected due to designer’s comments “ Filler Size is not acceptable” kindly be informed that the said units were already produced completely based on the last approved shop drawings and design . GLI to produce the upper extension parts, cove light panel and change shutters & drawers face based on the New revised design and 901 approved IR. Please clarify your comment and advise accordingly how to proceed further. Pantry Units Type 2/2A are for 1 Bedroom with Total 20 Sets ( 10 Each) Pantry Units Type 3/3A are for 2 Bedrooms Apartments with Total 20 Sets ( 10 Each) | NAM | MKM | 2018-03-29 | 2018-07-05 | 98 | We definitely do not recommend by filler pieces of 200mm or either side, where we loose a lot of storage space. To be finalized by MKM. MKM, principally approved for 1 bedroom apartment pantry units only. The price has to be discussed and agreed follow the WAI drawing 418-WAPKD-7-401-00. | A |  | 1 2 41
0100 |  | 00 | 19th to 23Rd Floors Junior Suite Elevations | MKM-05Q-IDP-01-TM-Greenline-0075 | 19th to 23rd floors Junior Suites | Please furnish the following elevations drawing as indicated in 19th to 23rd Floors Junior Suites furniture plans which are received through transmittal # MKM-05Q-IDP-01-TM-Greenline-0075. 1. Dwg # WJS1-7-300-00 2. Dwg # WJS2-7-300-00 3. Dwg # WJS3-7-300-00 | NAM | MKM | 2018-03-29 | 2018-04-17 | 19 | As per latest site walk comments, the bulkhead on the blockwall will removed. Hence there will not be any changes on this elevation from the previous design. | A |  | 1 2 41
0101 |  | 00 | Twin Guest Rooms Gypsum Beam Clashing | MKM-05Q-IDP-01-TM-Greenline-0075 | 24th to 41st floors Twin Guest Rooms | With reference to attached RCP ID drawing for Twin Guest Room at L24 to 41 floors, Please note, the gypsum beam (@ +2400 Level) is terminating on headboard veneer panel. See the following two options to avoid the beam clashing with Headboard panel. Option - 1 ) Gypsum Beams to be not from Wall to Wall ( i.e 500 MM Away from each wall) Option - 2) Headboard to be shifted 250 MM From Bathroom Wall. Please advise… | NAM | MKM | 2018-04-01 | 2018-04-11 | 10 | As per latest Clients instructions, buck heads are now cancelled @ guestrooms. Hence headboard remain unchanged. | A |  | 1 2 41
0102 |  | 00 | Apt # 1601_ Master Bathroom Shower Floor Finish. | 16008-2.2 | 1601- Private Apartment | With reference to above mentioned subject, there is a discrepancy noted in ID drawing (Dwg # 16008-2.2_Floor Finishes Layout). According the layout the Master bathroom shower area floor finish is mentioned as Stone GR1 while the stone finish specification provided as GR2 in the same drawing instead of GR1. Please confirm to use code GR1 for it. | HHS | MKM | 2018-04-12 | 2018-04-15 | 3 | Refer to attached DGA email dated 13 April 2018 for the confirmation of your above query. (GR1 is correct). | A |  | 1 2 41
0103 |  | 00 | Apt # 1601_ Main Entrance door Structural opening. | DS-0079-00 | 1601- Private Apartment | Regarding the main Entrance door structural opening, the existing height as per site condition is 2118mm from FFL, As per the revised drawing # 4-0 rev 01 section # SY-10 attached, it should be increased to 2400mm +AFFL in order to maximize the door height to +2300mm as requested by designer email received via our shop drawings reply DS-0079-00 attached. Please confirm. | HHS | MKM | 2018-04-16 |  | 497 | Cancelled (Called Back by Engr. Ramzi) |  |  | 1 2 41
0103 |  | 00 | Apt # 1601_ Main Entrance door Structural opening. | Email, 3D & DGW-4-1 REV 01 | 1601- Private Apartment | Regarding the main Entrance door structural opening, the existing height as per site condition is 2370mm from FFL, However as per DGA revised drawing # 4-1 rev 01 section # SY-10 attached, it should be clear +2400mm AFFL. Refer attached DGA render without comments for you refernce. Please advise. | HHS | MKM | 2018-05-15 | 2018-05-17 | 2 | Regarding the above query, 2370mm SOS door HT opeing is fixed as per the attached CI-0049, since DGA did not consider any technical fixation detail, please refer toi attached MKM proposed skecth for the solution to this issue. | A |  | 1 2 41
0104 |  | 00 | Apt # 1601_ Entrance Area Apartment Corridor Wall Finish. | MKM-05Q-IDP-01-DS-0059 REV.02 & 16008-41rev1 | 1601- Private Apartment | With reference to above mentioned subject and as per attached approved shop drawing the wall finish at 16th floor corridor entire area is wall pepper with wooden frame. According the new design drawing ( Dwg 16008-41rev1) received through TR # 077, the corridor area wall finish mentioned in section SY-10 as Stone finish( RTR ) Please confirm the finish for this area since the wall cladding and wooden frame is produced as per approved shop drawing Please advise. | HHS | MKM | 2018-04-17 | 2018-04-18 | 1 | Based on the latest DGA drawing, the highlighted on the attached dwg. Is RTR marble finish. Please provide evidence of wall cladding manufactured for this area. | A |  | 1 2 41
0105 |  | 00 | Apt # 1601_ Main Entrance door Handle and locks | Dwg 0-0 A rev 1, sketch & Email | 1601- Private Apartment | Query #1 - The current door design, when using pull handle with Vingcard lock, it is not feasible, kindly refer to Assa Abloy’s email attached which is self-explanatory, Therefore we suggest you the following two options Option 1- Using Vingcard lock with lever handle Option 2- Using pull handle with a surface mounted magnetic lock should be supplied by MKM hardware or MEP contractor Query #2 - Door security guard retainer cannot be used because it clashes with the applique trims design 15x10mm in BR finish as shown attached sketch, please advise if it not applicable to this door | HHS | MKM | 2018-04-24 | 2018-05-19 | 25 | Q#1- For 1601, all doors hardware will be supplied by GLI except for access control system for main door & kitchen door Ving Card, as discussed & agreed with several meeting. Q#2- Not required, refer to the attached ASSA Abloy access control system. Q#1- Option 2 - The main door will be pull handle with surface mounted magnetic lock should be supplied by MKM/Ving Cara/ASS Abloy. | A |  | 1 2 41
0105 |  | 01 | Apt # 1601_ Main Entrance door Handle and locks | Dwg 0-0 A rev 1, sketch & Email | 1601- Private Apartment | Reference to the same RFI Rev 00 reply & attached email, please advise on the following: 1. There is no mechanical lock is required from our side, please confirm 2. Please provide the magnetic lock exact model, technical details & physical sample 3. Please confirm the magnetic lock is certified with BS standard to use in fire rated wooden doors 60min | HHS | MKM | 2018-05-29 | 2018-06-03 | 5 | Please find attached mail reply from M/s. Ass Abloy. Hopes all your querries clarified. | A |  | 1 2 41
0105 |  | 02 | Apt # 1601_ Main Entrance door Handle and locks | Email | 1601- Private Apartment | Reference to the same RFI Rev 00 reply & attached email, please advise on the following: 1. There is no mechanical lock is required from our side, please confirm 2. Please provide the magnetic lock exact model, technical details & physical sample 3. Please confirm the magnetic lock is certified with BS standard to use in fire rated wooden doors 60min | HHS | MKM | 2018-07-31 |  | 391 |  | OD |  | 1 2 41
0106 |  | 00 | Apt # 1601_ Main Entrance door Strips and MM Specification | Dwg 0-0 A rev 1 & sketch | 1601- Private Apartment | Query 1: Kindly provide the specification of finish code MM finish Query 2: As per attached ID drawing attached, the highlighted applique metal strips design in BR and MM finish are not permitted on the fire doors as per attached fire report & the same are very close to the door edges which will impact negatively to the fire performance. Therefore, we propose to use wood finished to match the specified finish, refer attached sketch, please confirm | HHS | MKM | 2018-04-24 | 2018-05-05 | 11 | MM stand for VM black varnished metal (a typing error according to DGA) A per DGA email it is confirmed to substitute BR & VM metlas for main door with solid wood finish to match the equivalent metal finish. Refer to attached DGA email. | A |  | 1 2 41
0107 |  | 00 | 19th – 41st Floor Lift Lobby Door (WD-11) |  | 19th – 41st Floor Lift Lobby door WD-11 | Query 1: As per M/s Silvershore hardware set schedule for Door WD11, the specified door closer type does not comply with the designer’s comment on our shop drawing # 0509 rev 0 attached to increase the door opening angle to 180 degree, Therefore Kindly provide the correct door closer model & physical sample that can be used with the current approved door design attached Shop drawing # 0509 rev 3 with opening angle 170 degree Query 2: as highlighted on attached drawings #0509 rev 03, the marble installation is not ready at site and we require to the marble cladding thickness in order to start our door frame mass production for all levels from 19th to 41st floors, Kindly advise | HHS | MKM | 2018-05-02 | 2018-06-20 | 49 | Refer attached comment sheet for RFI response. | A |  | 1 2 41
0108 |  | 00 | Structural Width Opening for WD2b in Relation with Small Bathroom Vanity & Wardrobe | Sketch | 19th – 41st Floor Lift Lobby door WD-11 | As per the meeting with MKM on 05-May-2018 for the mentioned above subject, we need site modification in order to achieve 800mm clear frame width opening. Refer attached sketch. Please advise. | HHS | MKM | 2018-05-16 | 2018-05-23 | 7 | Refer to your above query, we prefered Greenline proposal to remove the NIB MKM will issue C.I to Ark to clarify the NIB. | A |  | 1 2 41
0109 |  | 00 | Corridors Atrium Stepped-Bulkheads Termination at Level 18 | Level 8 (Level 9 Slab Soffit) | CI-0078-00; Dwgs 418-WAPCD-7-401- & 200 00 | Please refer to the attached highlighted drawings along with photos showing site conditions of step bulkheads at Atrium 1, 2 & 3. Please advise the termination detail of the said bulkheads and confirm if it should terminate to feature wall. | HHS | MKM | 2018-05-20 | 2018-05-28 | 8 | I.D step Bulkhead ceiling detail to continue up to the Core Wall. | A |  | 1 2 41
0110 |  | 00 | Interconnecting door WD12 @ 24th to 41st Floor | MKM-05Q-IDP-01-DS-0042 rev.01, 1252-MKM-05Q-IDP-01-DWG-0508_REV-01, UAE Fire code (2 pages) | 24th to 41st Floors - Guest Rooms. | Reference to the above mentioned door, we observed that the hardware provided by MKM / Silvershore does NOT include door closers for the concerned doors According to UAE Fire Code attached, it mentioned in Clause 20.5 “Fire doors used to protect the means of egress shall be self-closing or automatic-closing. “ Normally any fire door required to be kept closed (self-closing) to restrict the spread of fire from one fire compartment to the next. If, in this situation, the door is kept open, then main function of the fire door is rendered useless. Please advise urgently | HHS | MKM | 2018-05-23 | 2018-07-11 | 49 | We recommend to have door closers for these doors. However final confirmation from Main Contractor in line with ID requirements. *Find attached confirmation from M/s Ark for door closer not reuired for the interconnecting doors. | A |  | 1 2 41
0111 |  | 00 | Material Specification Codes | Material Cover Pages as per attached list | Guestrooms | Reference to the attached the approved materials cover pages with old codes (MKM Codes), we require you confirmation each below listed codes can be used for the new WA codes instead of the old codes. 1. SWGS-102 & SWGS-103 Walnut wood & veneer, please confirm using our approved material TM101 submittal ref. MS-0026-0 attached. 2. SWGS-104 & SWGS-105 Paint, please confirm using our approved material PT600 submittal ref. MS-0046-0 attached. 3. SWGS-112 Statuario Marble, please confirm using our approved material SWA-112 submittal ref. MS-0105-0 attached. 4. SWGS-113 Clear Glass, please confirm using our approved material AW-704 submittal ref. MS-0014-1 attached. 5. SWGS-315F Twin Headboard Fabric, please confirm using our approved material SWGS-300F submittal ref. MS-0118-0 attached. | HHS | MKM | 2018-05-28 | 2018-05-29 | 1 | Confirmed provide shop drawings using new ID specs. | A |  | 1 2 41
0112 |  | 00 | Guestrooms & Junior Suites Full IFC set | MKM-05Q-IDP-STDROOM-MOCKUP-MOM-001 | 19th to 41st Floors | Reference to the attached MOM ref. MKM-05Q-IDP-STDROOM-MOCKUP-MOM-001 dated 08th May 2018 point # 7, we received in MKM-05Q-IDP-01-CI-0090-00 only the Furniture Layouts & one elevation for standard king room type 1) which insufficient for our engineering process and for our commercial department to be clear about the changes It was agreed with our GLI’s Project Manager that MKM /WA will provide a complete set of IFC that can supersede all related previous transmittals and client instructions to avoid confusion, therefore it should include the following: 1- Full set of drawings (all trades of Layouts, elevations & Joinery details) 2- Full set updated specification | HHS | MKM | 2018-05-23 | 2018-06-12 | 20 | Complete set was issued to MKM on 17/05/2018, However ther are more changes as per new instructions, need to review & re-issued them accordingly. | A |  | 1 2 41
0113 |  | 00 | Missing Specification | DWG – 16008-64 | Private Apartment 1601 Twin Dressing Room | Kindly provide the missing specification as per attached for Leather at drawer and “SC” glass shelf | HHS | MKM | 2018-05-23 | 2018-05-27 | 4 | With regards to your above query, kindly refer to attached email by DGA for your information and reference. | A |  | 1 2 41
0114 |  | 00 | 1601 Kitchen HPL finishes | email | Private Apartment 1601 Kitchen Unit | reference to attached email conversation with MKM and DGA, it was agreed due a minimum QTY issue, DGA accepted to substitute the Formica Beige oak Approved MS# 0135 with Natural Walnut W01, please confirm the same for our record | HHS | MKM | 2018-05-24 | 2018-05-27 | 3 | Based on the attached email by Duccio Grassi Architects, it is agreed to substituteFormica Beige Oak to W01 with natural Walnut. | A |  | 1 2 41
0115 |  | 00 | Twin room Small Bathroom vanity | Email & DWG 5-1 rev 02 | Private Apartment 1601 | Query # 1, DGA specified washbasin size 700x420mm, please refer to the attached specified supplier’s email and advise if it is ok to follow washbasin size 580x310mm Query # 2, Please provide the cutout sizes and approved details for the mixers, traps & towel bar for our coordination and to arrange the holes | HHS | MKM | 2018-05-28 | 2018-06-03 | 6 | Q#1 - Refer to the attached updated drawings by DGA. Q#2 - Refer to attached detail fixation & specs. Provided by I.D/DGA. | A |  | 1 2 41
0116 |  | 00 | Junior Suite Dining Unit SWGS-107 Glass specification | 418-WJSD-7-402-00 & Spec sheet SWGS-107 | Junior Suite 19th to 23rd Floors | Reference to the revised specification attached for SWGS-107 grey tinted etched, it was cancelled (omitted), while it is still applicable to the dining unit as per attached WA drawings, please advise | HHS | MKM | 2018-05-29 | 2018-06-12 | 14 | Item was Omited for wall paneling, however I shall remain on these unit. | A |  | 1 2 41
0117 |  | 00 | Wall finishes demarcation | WA Guestrooms and junior suites Furniture layouts 100 series | Guestrooms and Junior Suite 19th to 41st Floors | Reference to client instruction CI-0090-00, available only one elevation for standard king room, therefore please confirm the wall paper and wall paint finishes as per attached layouts as marked in colors on WA furniture layouts attached | HHS | MKM | 2018-05-29 | 2018-06-12 | 14 | Confirmed. All finishes to be as per attached marked up drawings. | A |  | 1 2 41
0118 |  | 00 | Junior Suite Type 1 & 1A Dining Unit Size | 418-WJS1-7-100-00 rev 2, 418-WJS1A-7-100-00 rev 1 & 418-WJSD-7-402-00 rev 0 | Junior Suite Type 1 & 1A, 19th to 23rd Floors | Query # 1 Reference to the revised furniture layouts received via CI-0090-00, we did a quick check for the highest floor level 23rd (worst case) and observed that the 2500mm width dining unit cannot be fit within the recess between the two concrete columns, please advise how to proceed. Query #2 The reference in furniture layouts for the dining unit mentioned is 418-WJSD-7-401-00 which is incorrect because it refers to the nightstand table drawings as per attached, the only dining unit detail drawings available with us is 418-WJSD-7-402-00 rev 00 attached, please confirm this is the right reference to use | HHS | MKM | 2018-06-11 | 2018-06-20 | 9 | 1. As discussed, we shall have 2 series of dining unit with the same concept design. Provide your SDS accordingly. 2. Confirmed typing error. | A |  | 1 2 41
0119 |  | 00 | Material Approval King Headboard Fabric SWGS-300F | Material Cover Pages MS-0018-00 | Guestrooms & Junior suites L19 to L41 | Reference to the attached the approved materials was submitted and approved for the mock up only & Since the mock up was recently approved, please confirm to proceed with the same typically for all Guestrooms & Junior suites L19 to L41 | HHS | MKM | 2018-06-11 | 2018-06-20 | 9 | Confirmed to proceed with its procurement. Provide original certificates. | A |  | 1 2 41
0120 |  | 00 | Material Specification Codes | Material Cover Pages as per attached list | Apartments 8th to 17th Floor | Reference to the attached the approved materials cover pages with old codes (MKM Codes), we require your confirmation for the below listed codes which can be used for the new (WA codes) instead of the old codes. 1. SWA-102 & SWA-103 Walnut veneer, Please confirm using our approved material TM105 submittal ref. MS-0045-00 2. SWA-104 & SWA-105 Paint, Please confirm using our approved material PT600 submittal ref. MS-0046-00 3. SWA-114 Clear Glass, Please confirm using our approved material submittal ref. MS-0014-01 4. SWA-116 White Laminate, Please confirm using our approved material submittal MS-0036-02 5. SWA-117 Grey Laminate, Please confirm using our approved material submittal MS-0037-02 6. SWA-118 Reconstituted Stone, Please confirm using our approved material ST016 submittal MS-0055-00 7. SWA-119 Black Absolute Granite, Please confirm using our approved material ST017 submittal ref. MS-0056-00 | HHS | MKM | 2018-06-10 | 2018-06-20 | 10 | We have not issued old specs, hence cannot comment on the same. Contractor to follow new issued ID specs details. | A |  | 1 2 41
0121 |  | 00 | LED Strip Profile @ Joinery items | Attached drawings and specification data sheets | Apartments, Junior Suites & Guestrooms (8th to 41st Floor) | Reference to the attached WA ID specification and drawings, please provide the latest approved LED strip profile technical data and physical sample for our reference in mass production | HHS | MKM | 2018-06-11 | 2018-08-12 | 62 | LED light PL1 will be used in all locations. -The physical sample attached with the RFI for your reference. | A |  | 1 2 41
0122 |  | 00 | Junior Suite TV Wall Unit SWGS-106 Glass specification | 418-WJSD-7-404-00 & Spec sheet SWGS-106 | Junior Suite 19th to 23rd Floors | Reference to the revised specification attached for SWGS-106 grey tinted Mirror, it was cancelled (omitted), while it is still applicable to the TV wall unit as per attached WA drawings, please advise | HHS | MKM | 2018-06-11 | 2018-06-21 | 10 | To be retained. Kindly make your material submittal accordingly. | A |  | 1 2 41
0123 |  | 00 | Desk type 4 @ Junior Suite 1 & 1A | 418-WSKGD-7-402-00, 418-WJS1-7-100-00, 418-WJS1A-7-100-00 | Junior Suite 1 & 1A @ 19th to 23rd Floors | Reference to the desk type 4 drawings which is used for Junior suites and guestrooms, we observed at the Junior suite type 1 & 1A rooms, there is no Media Hub at all in the room and even on the other unit Please advise if the Media Hub is required, If yes, please issue another desk type detail can be followed for this case (let’s call it Type 4A) and show it location and related details | HHS | MKM | 2018-06-17 | 2018-06-21 | 4 | Media Hub is read as clearly shown in our power plan. Marked in attached dwg. Provide your SDS accordingly. | A |  | 1 2 41
0124 |  | 00 | Apartment Full IFC set issues | CI-0094-00 | 8th to 17th Floors | Reference to the IFC set received recently via attached client instruction CI-0094-rev 00, we observed the following: 1- IFC set include some old drawings which may lead to a confusion such as Secondary bedrooms headboards, night stand & working desk details..etc 2- IFC set does not include the floor Key plan layouts for level 8th 3- IFC set does not include the individual layouts for level 8th and 14th to 17th floor Therefore, we request WA to issue a revision of this Client instruction with the final drawings to follow, please advise | HHS | MKM | 2018-06-17 | 2018-06-21 | 4 | 1. Kindly Omit all Dwg's for secondary rooms, included by mistake. 2. Provided to MKM on 18/06/2018 | A |  | 1 2 41
0125 |  | 00 | Desk type 5 & 5A @ 2BR rooms #003& 004 | 418-WAP2B-7-100, 418-WAP2B-7-101, 418-WAP2B-7-100, 418-WAPD-7-409-00, GLI Production Drawings (2 sheets), Sketch 001 | 2BR rooms #003& 004 @ 8th to 17th Floors (Apartments) | Reference to attached WA layouts, WA shows the desk tapered as shown below snap shot and requested to use existing manufactured desk unit which is straight as shown on our drawings attached Tapered Kindly refer to our site survey attached sketch #1 and confirm to instruct the main contractor to modify the site condition of the adjacent wall and maintain the requirement of 610mm min depth as shown to accommodate the desk and archway architrave | HHS | MKM | 2018-06-20 | 2018-06-26 | 6 | To install straight desks as already produced. Site works to be prepared accordingly. | A |  | 1 2 41
0126 |  | 00 | Final Approved RCP Combined MEP Coordination drawings | CI-0094-00 | 8th to 17th Floors (Apartments) | Reference to the recent IFC set received recently via attached client instruction CI-0094-rev 00, we require to the Updated & Approved RCP Combined MEP Coordination drawings for the coordination purpose with our RCP ceiling shop drawings (HVAC, lighting, fire alarm, Firefighting, …etc) Notes: 1- Combined RCP coordination drawings should reflect all visible and seen MEP services on the false ceiling, preferred to remove all unseen services above ceiling to avoid confusion, please also include an updated MEP legend to follow 2- GLI will reflect the final location, size and number of access panels which only approved with WA (designer) & MKM 3- Any additional access panels are required in additional to our contract drawings are subject to cost impact (variation) to our scope | HHS | MKM | 2018-06-20 |  | 432 | Issued to Site on 19-06-2018 | OD |  | 1 2 41
0127 |  | 00 | 2 Bedroom Room # 803 & 804 – Secondary Twin Room Desk details | 05Q-8F-GA-107.31-0, 418-WAPKP-7-100-00, 418-WAP2B-7-100, 418-WAP2B-7-101 | 8th Floor 2 Bedroom Room # 803 & 804 | As per our RFI 0124 rev 0, we highlighted that we do not have updated drawings for level 08 in general, we are not sure of which detail type to follow for the Desk unit in the above mentioned area because each type of drawing below shows in different detail or shape of desk • MKM old drawings 05Q-8F-GA-107.31-0 shows desk type3 • WA key plan layout 418-WAPKP-7-100-00 shows with two dresser desk (No detail) • WA layouts 418-WAP2B-7-100 & 418-WAP2B-7-101 in upper typical level 9th to 13th & 14th to 17th shows desk type 5 Please advise. | HHS | MKM | 2018-06-20 | 2018-06-26 | 6 | For secondary guestrooms, old desks as produced are to be installed. Please discuss it not clear 8th floor drawings issued by WAI | A |  | 1 2 41
0128 |  | 00 | 2BR & 3BR Maid's Room Furniture | SWA-334, SWA-335 & SWA-336 specs data sheets | 8th to 17th Floors 2 Bedrooms & 3 Bedrooms maid’s room | Reference to attached WA specification, please advise if MKM wants to add the below listed items in GLI scope: SWA-334, Maids Room Bed SWA-335, Maids Room Bedside Table SWA-336, Maids Room Chest of Drawers Please confirm. | HHS | MKM | 2018-06-27 | 2018-07-04 | 7 | Confirmed, all items to be under GLI scope. Provide one Mock Up for each item before mass production. | A |  | 1 2 41
0128 |  | 01 | 2BR & 3BR Maid's Room Furniture |  | 8th to 17th Floors 2 Bedrooms & 3 Bedrooms maid’s room | Reference to WA/MKM reply on our RFI rev 0, please provide WA ID design drawings for the below listed items in order to proceed our shop drawings : SWA-334, Maids Room Bed SWA-335, Maids Room Bedside Table SWA-336, Maids Room Chest of Drawers | HHS | MKM | 2018-07-22 | 2018-08-05 | 14 | Pls. develop dwgs. Based on spec cutshift & sizes. | A |  | 1 2 41
0128 |  | 02 | 2BR & 3BR Maid's Room Furniture |  | 8th to 17th Floors 2 Bedrooms & 3 Bedrooms maid’s room | Reference to attached email & WA/MKM reply on our RFI rev 1 , please provide WA ID design drawings for the below listed items in order to proceed our shop drawings : SWA-334, Maids Room Bed SWA-335, Maids Room Bedside Table SWA-336, Maids Room Chest of Drawers | HHS | MKM | 2018-08-07 | 2018-08-29 | 22 | There is no changes for these items from the original MKM design. Please follow MKM original design for the above items. | A |  | 1 2 41
0129 |  | 00 | Wall finishes demarcation | WA Apartment Furniture layouts 100 series | Apartments 8th to 17th Floors (Except 1601 apartment) | Query # 01: Reference to client instruction CI-0094-00, please confirm the wall paper and wall paint finishes as per attached layouts as marked in colors on WA furniture layouts attached Query # 02: Reference to attached specification SWA-109 wall covering at Secondary king and twin rooms, it is not applicable on the existing approved mock up Apartment # 090, please confirm this specification no more in use | HHS | MKM | 2018-07-02 | 2018-07-09 | 7 | 1. Comments on Drawings 2. This wallpaper to be on the headboard wall in both secondary rooms. | A |  | 1 2 41
0130 |  | 00 | TV Size | DWG 6-3 & 6-2, 3 Sketches, Transmittal TM-0063 | 1601 Private Apartment Gym and Twin Bedroom | Query # 01: Regarding TV #1&2 highlighted attached in two location (@ GYM between the two mirrors and Twin Bedroom), Please confirm to follow same TV size and specifications received via RFI-013-00 which used of the other Apartments 8th to 17th floors. Please confirm in order to proceed the production Query # 02: Regarding TV #3TV # 1 @ GYM corner column highlighted attached, we recommend to use 40” TV maximum size, Please confirm this final TV Size O/A WxH size and provide TV specification. | HHS | MKM | 2018-07-17 | 2018-07-22 | 5 | #01. Submit Shop Dwg. For the 65" TV consider the frame sizes & bracing for DGA approval. #02. Corner column TV is a provision TV oulet only as reuested by Client. | A |  | 1 2 41
0131 |  | 00 | Apartment Entrance Door Threshold | CI-0094-00 Sketch 1 | Apartment 8th to 17th Floors | Reference to the latest WA drawing set received recently via attached client instruction CI-0094 shows marble threshold at Entrance Door. Refer attached sketch for your confirmation on detail & finishes. NOTE: Please note that Entrance Doors are already produced with 5mm undercut gap. | HHS | MKM | 2018-07-18 | 2018-07-19 | 1 | Please follow GLI's approved shop drawing 1252-MKM-05Q-IDP-01-DWG-0602_Rev.01 approved on 21/05/2018 & works habe been executed on site. The approval sheet &^drawings are attached for your reference. | A |  | 1 2 41
0132 |  | 00 | Secondary Bedrooms Headboard Leather Pattern | Revised Shop Drawings – 1252-MKM-05Q-IDP-01-DWG-0342-1/1-REV03,1252-MKM-05Q-IDP-01-DWG-0340-2/2-REV03,1252-MKM-05Q-IDP-01-DWG-0341-1/1-REV04, 1252-MKM-05Q-IDP-01-DWG-0343-1/1-REV03 | Apartment 8th to 17th Floors | Reference to our discussion with Mr. Sanjay (WA)on 18th July , we made a minor modifications on our shop drawings as clouded attached to benefit of using the existing headboard wood material and achieve WA desired scale for the leather pattern. Please confirm to proceed | HHS | MKM | 2018-07-22 | 2018-07-25 | 3 | To be review @ Mock Up room: Pattern to be removable type for maintenance. | A |  | 1 2 41
0133 |  | 00 | Missing wall @ Master Bedroom | DWG – 6-0 & 7-1 | Private Apartment 1601 - Master Bedroom | Please note that we observed the attached highlighted wall which will receive marble RTR finish are not executed yet at site by Al Faraa, please advise as the similar wall between studio & Dining is already done at site | HHS | MKM | 2018-07-22 | 2018-07-25 | 3 | Based on DGA drawing No. 0-0A detail B07, no block work required by I.D GLI to proceed accordingly as per I.D design/detail. Find attached detail drawing. | A |  | 1 2 41
0134 |  | 00 | BR Metal finish control sample | BR Finish (Metal Burnished Brass) | 1601 Private apartment wall metal trims | Reference to the attached email & several reminders to obtain the revised control sample of BR metal finish, please provide the control sample at the earliest in order to avoid hindering our production. Note: Due to change in Specification of the metal finish, please note that it may has a potential of cost and time impact & will be advise in due course | HHS | MKM | 2018-07-31 |  | 391 |  | OD |  | 1 2 41
0135 |  | 00 | 8th – 17th Corridor Skirting Joint | DS-0059_6 (DWG-713-1/3_04 & DWG-713-2/3_04) & DS-0059_9(DWG-713-3/3_06) | 8th – 17th Corridor | Based on the approved Drawing Submittal DS-0059_6 & DS-0059_9 for the 8th – 17th Corridor Elevations, M/S Stone factory prepared the isolated detail drawing for the skirting joints (staggered joint) as per our work shop with M/S WA on 26th of June, 2018. Please review & confirm. | HHS | MKM | 2018-08-07 | 2018-08-28 | 21 | ID: Confirmed, kindly prepare work sample for our review & approvals prior to its bucj construction. | A |  | 1 2 41
0136 |  | 00 | TV Size @ TV Wall Studio A | 418-WAPD-7-408-00, 1252-MKM-05Q-IDP-01-DWG-0333-1/1-Rev4 | 8th – 17th Studio A | Reference to the attached email for the TV size, we noticed it will not fit in the TV unit as per WA and our approved shop drawing attached, please advise | HHS | MKM | 2018-08-08 | 2018-08-09 | 1 | Increase the width of the TV frame 100mm. Hence the width of the TV frame will be 1300mm (Please check the content on the instead of 1200mm drawing. | A |  | 1 2 41
0137 |  | 00 | Strip Light Physical sample (Final / Approved) | Specifications as per DGA Drawings (DWG#s 3-0, 5-0, 5-1, 6-0A, 6-1A, 6-2, 6-4 & 7-0A) & CI-0060 Light Specs | 1601 Private Apartment (Living TV unit, Cove Ceiling, Twin & Master Dresser, Gym Mirrors, Master Bedroom Shelves and Master & Twin Bathroom Vanity Mirrors) | Reference to attached Client Instruction ref. CI-0060 enclosed the specification of the strip light dimensions (Viabizzuno, size 32x30mm) while on the attached DGA drawings the size is mentioned 13x8mm, Please confirm and provide the final / approved strip light (By Other) dimension, specification & physical sample to follow in our production | HHS | MKM | 2018-08-14 | 2018-08-18 | 4 | Follow RFI-0121 12/08/18 (Sample Provided) | A |  | 1 2 41
0138 |  | 00 | 8th Floor 1 Bedroom Handicapped Power layout | 1252-MKM-05Q-IDP-01-DWG-0135 | 8th Floor 1 Bedroom Handicapped (Room Nos. 0808 & 0809) | Reference to attached rejected drawing for (Power plan) below location can you please provide the latest Power Plan with all the special requirements for handicapped room to incorporate it with our shop drawing. | HHS | MKM | 2018-08-14 | 2018-08-26 | 12 | Please Ref. Dwg. # 418-WAP-1BB-7-120-00 issued via CI-0094 Rev.01 dated 25th June 2018. | A |  | 1 2 41
0139 |  | 00 | 19th – 41st Aluminum Flashing / Skirting Support Detail | Photos (2 Nos.), ID drawing # EL-0110.10-0, GLI shop drawing # 0602-1, WA key Furniture plans 418-WJSKP-7-104 to 110 (7 sheets) | 19th – 41st Floors | Reference to attached key plan layouts for 19th to 41st floors attached, the clouded two side elevations have a high Alum flashing which is not matching the ID Elevation drawing # EL-0110.10-0 or the approved detail “I” & “J” of drawing # 0602 attached which is shown 150mm high only, please provide the right detail to be followed for the high Aluminum Flashing / Skirting support. | HHS | MKM | 2018-08-16 | 2018-09-02 | 17 | I.D: Find comments on attached dwrg. WAF-TA-ALL-AAB-AF-EXT-SD-18611 Rev.02. | A |  | 1 2 41
0140 |  | 00 | Vanity Mirror Anti-Fog | 1601 Private Apartment (Master & Twin Bathrooms) | DWG# 16008-5-0 rev2 & 16008-5-1 rev2 | Reference to attached DGA drawings regarding the Vanity Mirrors for the below mentioned areas 1- please provide the specification & details for the Anti fog at 1590mm AFFL for our coordination with our approved 6mm Silver mirrors 2- Please advise if the MEP contractor will provide the Anti-fog pads and make the electrical provision for it | HHS | MKM | 2018-08-16 | 2018-08-18 | 2 | 1. GLI should refer to CI-0077 date 05 Feb.2018. 2. Refer to ID drawing 5-0 Rev.2 Section 5 D.01. 3. DSE received I.D full copies & they are implementing I.D design on their shop drawing. FYI | A |  | 1 2 41
0141 |  | 00 | Kitchen Built-In-Microwave | DWG# MKM-05Q-16-DET-DWG-0109 REV 0, CI-0071, TM-0065, Microwave Specs | 1601 Private Apartment (Kitchen Pantry Unit) | Reference to attached specification of the Microwave issued via TM-0065 “Whirlpool AMW 494/IX” which is Built-In fully integrated model , However as per MKM drawings issued via CI-0071 it shows on the top of the marble top, Please advise. | HHS | MKM | 2018-08-26 | 2018-09-02 | 7 | Please refer to the commented shop drawing DS-0083 / DWG. No. 1252-MKM-05Q-IDP-01-PA-0314 1/2 - 2. | A |  | 1 2 41
0142 |  | 00 | Location of bed from the bathroom wall for clear access. | 1252-MKM-05Q-IDP-01-DWG-0208 REV 1 GENERAL ARRANGEMENT & POWER PLAN | 24th to 29th floor Disabled Room –Type (DKG1) Guestrooms | Reference to attached commented shop drawing kindly define the location of bed from wall for the clear access of wheelchair towards the bathroom. | HHS | MKM | 2018-09-12 | 2018-09-19 | 7 | From edge of bed up to bathroom wall, we minimum require open space of 1500mm for rotation of wheel chair. | A |  | 1 2 41
0143 |  | 00 | LIFT CAR DETAILS | 418-wlcd-7-400-00_REV 1 LIFT CAR DETAILS (1 Page A3) & Email (1 Page A4) | Lift Car | Reference to attached email and WA drawing, please provide the following: • An official Instruction CI (issued for construction) • A key plan shows each lift car location, number & Type • The Lift Car Subcontractor As-Built drawings each type • The total weight allowance for the interior works each type including flooring, wall cladding & ceiling. | HHS | MKM | 2018-09-17 | 2018-09-26 | 9 | See attached info as requested. | A |  | 1 2 41
0144 | ARK-0001 | 00 | NICHE FINISH & LIGHTING DETAILS | 418-WES1-7-100-00, 418-WES1-7-120-00, 418-WES1-7-300-00, 418-WES4-7-100-00, 418-WES4-7-100-00, 418-WES4-7-120-00, 418-WES4-7-300-00, 418-WES4-7-301-00, 418-WES6-7-100-00, 418-WES6-7-120-00, 418-WES6-7-300-00, 418-WES6-7-301-00 | (45th to 50th Floor)EXECTIVE SUITES TYPE 1, TYPE 4 & TYPE 6. | Query 1 Refer to attached WA Drawings; Kindly confirm the double shelf finish at niche taking into consideration that in Elevation B-B of Dwg# 418-WES1-7-300-00 shown clear glass WES-113, please advise. Query 2 Kindly confirm if the lLED strip light is required on the shelf as we found in some power plans example dwg # 418-WES6-7-120-00 & elevation C-C & D-D of dwg# 418-WES4-7-300-00 shows stip light, please advise | HHS | ARK | 2018-09-20 | 2018-10-02 | 12 | 1- Wooden shelves within these niches to be provided for the suites. 2- LED strip light is required for all shelves. | A |  | 1 2 41
0145 | ARK-0002 | 00 | LIFT CAR WLC – 104 CONTROL SAMPLE |  |  | Please provide control sample for the Titanium bronze metal finish by lift car manufacturer as per attached specification of Item no – WLC-104 to match our finishes. | HHS | ARK | 2018-09-20 | 2018-10-02 | 12 | All physical sample pieces are handed over to GLI through MKM. Kindly verify. | A |  | 1 2 60
0146 | ARK-0003 | 00 | 19th - 41st High Aluminum Flashing /Skirting Support Detail |  |  | Reference to RFI No. MKM-05Q-IDP-01-RFI-0139 for the high Aluminum Flashing/Skirting support, we proposed to use gypsum with stud backing as shown in the attached sketch detail. Please review and confirm. | HHS | ARK | 2018-09-25 | 2018-10-02 | 7 | Kindly submit your shop drawing accordingly and thereafter to prepare mock up sample for our review & approvals. | A |  | 1 2 60
0147 | ARK-0004 | 00 | 8th - 17th Bedroom Archway Structural Opening |  |  | Regarding the Bedroom Archway Structural Opening, there are lot of discrepancies in the opening sizes. As per the attached schedules, we require the main contractor to rectify those conflicts in order to produce doors archway in a mass production. Please review and confirm. | HHS | ARK | 2018-10-09 | 2018-10-21 | 12 | Archway details to be exact same as provided at mock up Apt 901. Sizes to be standardize for production | A |  | 1 2 60
0148 | ARK-0005 | 00 | 19F-24F Wardrobes Type 1, 2 &3 - DB Box & GRMS Dimensions and Locations |  |  | The dimensions and locations of installed DB Boxes and GRMS at 19F - 24F were not in accordance with the approved GLI Type 1 - (Level 19 to 41), Type 2 - (Level 24 to 41) and Type 3 - (Level 19 to 41) Wardrobe shop drawings. Refer to attached survey data for the discrepancies together with the approved shop drawings. Note that all the wardrobes had been produced based on our approved shop drawings and had been delivered to site already | HHS | ARK | 2018-10-24 | 2018-11-04 | 11 | Installation of D/B boxes to be coordinated along with commented shop drawings for wardrobes. As for GRMS box, single its depth is more than indicated in drawings, they need to be boxed with shutter in front of the same. All internal surfaces to be properly finished with primer / stucco. | A |  | 1 2 60
0149 | ARK-0006 | 00 | Wardrobe type 10 (modifications for the Big safe) |  |  | Reference to the attached WI & attached emails regarding the modifications on the existing wardrobes to suit the big safe box, Please advise on the following: • Kindly provide the required instruction to proceed the work • Please confirm the modification is applicable to 3 Bedroom Apartments @ Master Bedroom wardrobe. Note: The above mentioned has cost impact will be advised in due course. | HHS | ARK | 2018-10-31 | 2018-11-10 | 10 | 1) Instructions to be provided by MKM/ARK 2) Its applicable one piece to the apts. 3) To be verified & confirmed by MKM/Q.S | A |  | 1 2 60
0150 | ARK-0007 | 00 | Junior Suite Type 1 & 1A Dry Wall Linning Work. |  |  | Reference to the attached clouded WA drawing, Please confirm the dry wall lining work as per CI-0090 @ Junior Suite Type 1 & 1A. Also please advise this dry wall linning work is in GLI scope?. | HHS | ARK | 2018-11-06 | 2018-12-25 | 49 | Dry wall is required to cover expossed conduits. Scope of works to be confirmed by MKM/ARK. Scope of dry wall is under GLI only. Confirmed | A |  | 1 2 60
0151 | ARK-0008 | 00 | 45th To 50th Floor (Executive Suites)_Door Hardware Set Schedule & Physical Sample. |  | 45th To 50th Floor (Executive Suites) | Kindly note that all Ironmongery for all wooden doors is supplied by client, kindly please provide following. *) Please provide the Door Hardware set schedule for all wooden door types ID1,ID2,ID3,ID5,ID6,ID7. *) Please provide the physical samples for our production cut-outs | HHS | ARK | 2018-11-05 | 2018-11-25 | 20 | To be provided by MKM as complete Ironmongery for the project is procured directly by them. | A |  | 1 2 60
0152 | ARK-0009 | 00 | 45th To 50th Floor (Executive Suites)_Architectural Drawings. |  | 45th To 50th Floor. | As per comments at key plan attached our shop drawings we require architectural shop drawings to incooperate the doors number in our key plans. | HHS | ARK | 2018-11-05 | 2018-11-13 | 8 | Contractor to refer to attached shop drawing as requested. All signage at FOH will be done by another contractor. | A |  | 1 2 60
0153 | ARK-0010 | 00 | 19F-24F Junior Suite & guestrooms Wardrobe _ Block dimension issue |  | 19F-24F Junior Suite & guestrooms Wardrobe | The dimensions of block wall installed by main contractor are not as per block drawings received via Transmittal ref MKM-05Q-IDP-01-TM-Greenline-0003 which shows the clear wardrobe wall width is 2800mm while it is executed at site by the main contractor 2650mm we issued the wardrobes Job Order as per the above transmittal and approved shop drawings MKM-05Q-IDP-01-DS-0041 attached "Code A" when the shaft wall were not installed at site & we have allowed tolerance (Filler) both sides to cover up to 40mm differences , However such huge difference (150mm) were not highlighted to Greenline while our mass production was ongoing for those wardrobes and all the above mentioned wardrobes are delivered to site as per approved drawings and block wall drawings received from MKM Kindly instruct the main contractor to rectify the block walls or advise how to proceed the installation. | HHS | ARK | 2018-11-12 | 2019-07-16 | 246 | -THE DETAILS BEEN CONFIRMED ON NOV. 2018 & THE WORK PROCEED ON SITE. | A |  | 1 2 60
0154 | ARK-0011 | 00 | Interconnecting Door Revised Floor Detail |  |  | With reference to received MKM-05Q-IDP-01-0016 with additional marble threshold under the interconnecting doors, kindly find enclosed revised typical flooring details for your kind review and confirmation. Your usual quick response will be highly appreciated. | HHS | ARK | 2018-12-23 | 2019-01-08 | 16 | Accepted as attached drawing. | A
0155 | ARK-0012 | 00 | Wardrobe Revised Details Due to Site Condition |  |  | With reference to above mentioned subject and due to observed DB & GRMS boxes sizes and location, please find enclosed revised wardrobes details @ rooms located within levels 24 to 41 for your kind review and confirmation in order to allow us to proceed accordingly. Attached revised wardrobe types are: • Type-1 • Type-2 • Type-3 • Type-6 In addition, it is recommended to change the wardrobes types as following due to site measurements: • Levels 24 to 29, room no. 8: wardrobe type-2 to be changed to type-6. • Levels 24 to 29, room no. 18 & 19: wardrobe type-2 to be changed to type-1. • Levels 30 to 36, room no. 18 & 19: wardrobe type-2 to be changed to type-1. • Levels 37 to 41, room no. 7, 8, 18 & 19: wardrobe type-2 to be changed to type-1. Your kind confirmation will be highly appreciated in order to proceed accordingly. | HHS | ARK | 2018-12-23 | 2019-01-28 | 36 | ID: Wardrobe deisigns are all by MKM & Not be WAI. RFI needs to be revised in coordinating with MKM Team. MKM: As discussed in the meeting submit the shop drawings based on the mock up. Then will finalize the type. | A
0156 | ARK-0013 | 00 | Orientation of TV Wall Unit Type-2 @ Junior Suites 1 - Bedroom Suite B |  |  | With referene to the above mentioned subject, the TV wall units orientation as per the rvised ID drawings (WJS3-7-100-00 02 issued thru CI-0090-00) is different from the GLI approved shop drawings (1252-MKM-05Q-IDP-01-DWG-0332 1/1 00), Tender & IFC drawings. According the approved shop drawing the small piller is near to the window side and the bigger one is near to door (refer attached the photo taken at Apt. 1906 of the TV nit mock-up is istalled for review and orientation confirmation) Refer also to attached photo taken at apt. 1907 for the TV unit mock-up is installed as per CI-0090-00 for information. All materials had been produced and delivered at site according the approved shop drawing. your kind confirmation will be highly appreciated in order to proceed accordingly. | HHS | ARK | 2019-01-15 | 2019-01-21 | 6 | ID: Shop drawings were not revised and signed of us. Whle Drouts were revised & issued to tall based on our approved presentation(attached To MKM: We definetely recommend contractor to follow new ID drawings. | A
0157 | ARK-0014 | 00 | APT 1601 - LOCATION OF COVE AT TWIN BEDROOM & SIZE OF DB CABINET AT LIVING AREA |  |  | Please confirm presence of cove for air return at Twin Bedroom along entrance door side since the area is occupied by presence of down throw plenum boxes, refer to sheet 5 of 7 of the attached NSC-0013 and also on drawings PA-0109 2/4 01 with Detail 6 on drawing PA-0302 2/2 01 for reference. NSC-0013 sheet 5 of 7 also shows the elevations of existing MEP services and height of plaster which will be the reference of cove height assuming provision of cove for air return is confirmed. Please confirm also the width of DB cabinet since 150mm cannot be achieved due to existing cable trays on wall and ceiling, refer to sheet 6 of 7 and sheet 7 of 7 of the attached NSC-0013 and also on drawing PA-0111 2/4 00 for reference. The minimum width of DB cabinet to cover the MEP services on wall and ceiling is 400mm as shown to Mr. Paul Chapman of M/s ARK and Mr. Naushad of M/s MKM on 29 January 2019. | MW | ARK | 2019-02-02 | 2019-02-12 | 10 | All confirmed except DB cabinet point. ARK/DSE awaiting confirmation of new size increase of DB. | A
0157 | ARK-0014 | 01 | APT 1601 - LOCATION OF COVE AT TWIN BEDROOM & SIZE OF DB CABINET AT LIVING AREA |  |  | 1. Please confirm the width of DB cabinet since 150mm cannot be achieved due to existing cable trays on wall and ceiling, refer to sheet 6 of 7 and sheet 7 of 7 of the attached RFI-0014 00 containing some documents from NSC-0013 and also on drawing PA-0111 2/4 00 for reference. Take note that as per site coordination with DSE and M/s ARK Inspector on 13 March 2019, a minimum width of 300mm is required to accommodate the width of GRMS and the 50mm size of Unifix support bracket. DSE will adjust cable trays on wall and ceiling to make sure they are all inside the DB Cabinet. 2. Please confirm limit of covelight at Master's Bedroom Headboard area based on existing conditions as shown on the attached photos (70mm height of cove was confirmed thru attached WAF-01-GLI-CVI-0009 00). Likewise, the provision of cove at Master's Bedroom shelves area need to confirm as verbal instruction to delete it was issued before by M/s ARK representative (refer to attached photo also). Reference concerning coves should be made on the existing conditions of MEP services as shown on sheet 3 of 7 of NSC-0013 and attached drawings 1252-MKM-05Q-IDP-01-PA-0105 2/4 00, PA-0106 1/2 & 2/2 00 showing location and details of cove. 3. Please confirm detail of ledge for water closet at Master's Bathroom if it is fixed permanently as shown on drawing 16008-5-0 06 from Ducciograssi Architects. In case, it is removable, should a piece of board or any material be fixed under the ledge to prevent it from breaking. 4. Please provide framing detail for the gypsum cladding for the aluminum panels at Facade areas, refer to attached drawing 1252-MKM-05Q-IDP-01-PA-0302 2/2 01 C4 Detail. | MW | HS | 2019-03-16 | 2019-03-23 | 7 | 1. Please propose as pwer thwe site condition & revise the drawing (300mm) as agreed with Ducci during the visit. 2. As discussed and agreed with Duccio, cancel the cove in the headboard wall as highlighted in the drawing. Cancelled only the wooden cladding area (elevations - cove light at shelves also deleted. 3. It should be removable type. | A
0157 | ARK-0014 | 02 | APT 1601 - PROVISION OF BULKHEAD FOR DB CABINET AT LIVING AREA; |  |  | 1. With reference to item 1 of the attached WAF-01-GLI-RFI-0014 Rev. 01, a gypsum bulkhead (100mm high and 150mm wide) projecting from the 300mm wide DB shall be provided to hide the existing electrical cable tray, refer to attached sketch signed by MKM Mr. Noushad. This bulkhead 100mm x 1500mm shall be made of gypsum boards. In addition, please indicate also the termination of the 20mm horizontal groove on the RTR stone wall at Living Area and on the Timber finish wall cladding at Studio Area. 2. With reference to item 4 of the same attached WAF-01-GLI-RFI-0014 Rev. 01, requested framing detail for the gypsum cladding on the aluminum flashing at Facade areas was not provided. A mock-up sample was made inside Master's Bedroom where Main C-channels fixed on the flashings were used as supports. A GI corner bead was provided on the bottom corner as commented on the attached detail 25 - C4 Details, drawing 1252-MKM- 05Q- IDP-01-PA-0302 2/2 01 (refer to attached photos of the mock-up). 3. With reference to item 1 of the attached WAF-01-GLI-CVI-0011 00, confirmed deletion of covelight at Twin Bedroom along entrance door side shall be officially approved thru submission of RFI. Please confirm all the above-mentioned items so that we can proceed with items 1 & 2 and close item 3 thru this RFI. | ROM | HS | 2019-04-10 | 2019-04-20 | 10 | 1. For Item 1. please cladd this gypsum bulkhead (100mmx150mm) by wooden. Same wood used for the DB Cabinet & wall cladding. 2. Mock up approved. Please proceed as per mockup. 3. Confirmed. | A
0158 | ARK-0015 | 00 | REFLECTED CEILING PLAN AT END CORNERS OF MAIN CORRIDORS AT 24F TO 41F |  |  | GLI latest approved shop drawings 1252-MKM-05Q-IDP-01-DWG-0731 1/1 rev. 02 (24th to 41st Floor Corridor Reflected Ceiling Plan & Details) shows termination of covelight at end corners of Main Corridors. However, Corridor Wall Paneling Elevations thru GLI latest approved shop drawing 1252-MKM-05Q-IDP-01- DWG-0730 1/2 rev. 03, 0730 2/2 rev. 00, 0732 1/4 rev. 03, 0732 2/4 rev. 03 and 0732 4/4 rev. 03 show that the covelights with curtains underneath exist at facade areas. Please confirm whether covelights with curtains underneath shall be provided at facade areas or all around the end corners of the main corridors. If confirmed, please provide detail how the level of cove (+2.400) will be terminated to the facade (refer to same attached dwg 1252-MKM-05Q-IDP-01-DWG-0732 4/4 rev. 03. In case GLI latest approved shop drawings 1252-MKM-05Q-IDP-01-DWG-0731 1/1 rev. 02 shall be followed, please provide detail also how end of cove (+2.400) will be terminated to the facade (refer to same attached dwg 1252-MKM-05Q-IDP-01-DWG-0731 1/1 rev. 02. | RM | ARK | 2019-02-18 | 2019-03-11 | 21 | Please follow the curtain bulkhead details on the guest room for the façade termination. Keep all ceiling @ end corner +2400mm Ref: attached sketch. Corridor -001. | A
0159 | ARK-0016 | 0 | Modification of cove height at lvel 17 Lattice Ceiling Area, Atriums 1, 2 & 3 |  | Level 17 | The existing height of perimater cove at level 17 lattice ceiling area, atriums 1, 2, 3 is 50mm above FCL of +2400mm. This condition make the led strip light visible as it is fixed on top of gypsum board 47mm above FC. This is due to the requird 22mm furring channels in between gypsum bords that need to be exteneded until cove edges, refer to attached sketch drawing. Please advise how high should the cove height be increased in order to hide the led strip light and how it whould be done since small piece of additional gypsum boards is not possible to install to meet the required height. | HS | ARK | 2019-03-24 | 2019-04-07 | 14 | -Please proceed as per the mockup approval in Atrium 1 (area apartment - 6) in L17 - As did in the mock up area, cut the gypsum from inside cove, & MEP contractor will fix the lift as their cutouts. | A
0160 | ARK-0017 | 0 | ADDITIONAL DRAWERS UNIT @ WARDROBE UNIT TYPE-6A |  |  | With reference to the attached received commented shop drawing with a comment to add drawers, please note that the said wardrobe was issued for production based on previous comments and DB/GRMS location confirmationa and carcass production was completed. To add additional drawers wll cause cost & time impact. Please confirm and advise if to proceed with additional works accordingly. | MW | ARK | 2019-04-01 | 2019-04-07 | 6 | Please proceed as per the commented shop drawings. Without any additional drawers. | A
0161 | ARK-0018 | 0 | APARTMENT 1601 - COVELIGHT LIMIT ABOVE HEADBOARD AT MASTER'S BEDROOM |  |  | Our GLI Design Team confirmed that the length of the fabric for the Headboard at Master's Bedroom shall be 4346mm as per attached drawing 1252-MKM-05Q-IDP-01-PA-0106 1/2 01 Elevation-1. This dimension of 4346mm shall be the limit of the covelight above the headboard, refer to attached blow-up elevation of the entire wall. Take note that using the existing limit of covelight (refer to attached photo) on the facade side as reference, the width of the Wood Veneer will be 898mm only and not 1003mm as per drawing. On the door side (WD3f for the Dresser Room), the width of the Wood Veneer on the left side of the door is 155mm while on the right side of the door, the width of the Wood Veneer is 232mm. Please confirm the dimensions indicated on the attached blow-up elevation as this will be the basis of the following: 1. Closing the covelight above the Dresser Door (covelight still exist until column). 2, Location of the TV Wall structure (its centerline to coincide with centerline of the Headboard). 3. Location of the electrical boxes since the distance from each box is only 3070mm which should be 3375mm as indicated in our drawing. | MW | ARK | 2019-04-08 | 2019-04-21 | 13 | -Please make the headboard fabric size as 878mm (928-50) = 878mm on both sides. - And increase the size of veneer panel to 998mm (instead of 898mm at site) & match the cove with the veneer panel. | A
0162 | ARK-0019 | 0 | MASTER'S BEDROOM @ 3-BEDROOM APARTMENT, LEVELS 9 TO 17 WALL OPENING HEIGHT OF 2400+ MM AGAINST 2100MM HEIGHT OF ARCHWAY |  |  | The height of wall opening inside Master's Bedroom at Apartments 906, 1006, 1206, 1306, 1406, 1506, 1605 and 1706 is ranging from 2413mm to 2440mm (refer to attached key plans for locations). As per approved drawing 1252-MKM-05Q-IDP-01-DWG-0387 4/5 00, the height of Archway is only 2100mm (top of header), Archway opening height is 2040mm. Please advise how the difference in height of ±300mm shall be closed and finished prior to installation of Archways including the architraves. | MW | ARK | 2019-04-08 | 2019-04-20 | 12 | 1. As informed, heights of arch way frame details to match with bathroom doors. 2. All open gaps to be boarded with suitable frame work in paint finish as specified to have standard heights. | A
0163 | ARK-0020 | 0 | Handle/Knob Details for Dining Units Drawers and Shutters |  |  | With refernce to the attached received commented shop drawings kindly provide the type and specifications of handle/knobs for dining units drawers shutters. | MW | ARK | 2019-04-13 | 2019-04-21 | 8 | Kindly follow ID spec no. SWGS-601. Knobs for this unit. | A
0164 | ARK-0021 | 0 | WARDROBES TYPE-1 AND TYPE-3, LEVELS 19 - 41 SPOTLIGHT COMPARTMENT ABOVE THE MINI BAR |  |  | As per attached approved drawings 1252-MKM-05Q-IDP-01-DWG-0351 2/4 06 Wardrobe Type-1 Detailed Drawing and 1252-MKM-05Q-IDP-01-DWG-0352 2/2 06 Wardrobe Type-1 Detailed Drawing, the height of compartment for the spotlight is 80mm, finish to finish. With 18mm thick top and bottom mdf panel, the space left inside is only 44mm in which the actual sample of spotlight cannot be inserted / fixed, refer to photo below. | MW | ARK | 2019-04-24 | 2019-04-30 | 6 | -Please find attached photos of compartment for this spotlight, shows - 150mm. -Why the drawing shows different. -Please follow the mock up, Or propose from contractor side, how can move forward. | A
0165 | ARK-0022 | 0 | WARDROBES TYPE 3 - MDF SIDE PANEL WITH UNNECESSARY OPENING CAUSED BY THE RELOCATION OF GRMS BOX AT APARTMENTS 3 & 9, LEVELS 19 TO 23 |  |  | Please advise if the veneer finish MDF side panel with unnecessary opening (refer to attached photos) caused by the relocation of GRMS boxes need to be replaced with full piece side panel or will be covered only with exactly the same dimensions of the opening where veneer finish TM-101 shall be same but the texture direction will not match. Take note that at Apartment 1903, the top MDF panel and adjacent panel as shown on the same attached photo need to be changed also. Panels were cut for the first relocation of GRMS box which was rejected due to problem in opening the box. Please confirm so that required job order for the necessary materials can be prepared and issued for production. | RR | ARK | 2019-05-01 | 2019-05-07 | 6 | -In 1903 the side panel fully to be replaced, due to different openings. -Other rooms (3 & 9) rooms, please proceed as per mockup(1909), from 19 to 23. | A
0166 | ARK-0023 | 0 | WARDROBES TYPES 1, 2 & 6A - REQUIRED FINISH ON FILLER MATERIALS |  |  | Revised drawing for Wardrobe Type 1, Dwg 1252-MKM-05Q-IDP-01-DWG-0351 1/4 05 shows filler material is paint finish, refer to Plan Detail 1 - Plan for Counter Left Unit. However, Blow-up Detail 15 shows this filler material is veneer finish. Same discrepancy was also there on Wardrobe Type 2 Dwg 1252-MKM-05Q-IDP-01-DWG-0351 3/4 03 and Type 6A Dwg 1252-MKM-05Q-IDP-01-DWG-0733 1/2 02. Please confirm the final finish of these filler materials so that the required job order for the necessary materials can be prepared and issued for production. | RR | ARK | 2019-05-01 |  | 117 | -As per the mock-up it is paint finish (guest room mockup in ground floor). -we commented to change the wall paper finish to paint, then contractor responsibility change this wall paper to paint in all related drawings. -Please proceed as per paint finish. | A
0167 | ARK-0024 | 0 | Exisiting Upstand Concrete at Maid's Rooms Apartments 903 & 904 |  |  | The existing upstand concrete at Apartments 903 and 904 Maid's Rooms as shown on the attached photos needs to be demolished or covered with finishes either by paint finish on plastered surface or by covering the surfaces with ceramic tiles same as what had been done and approved at Mock-up Apartment 901, refer also to attached photos. Whichever type of finish is approved, upstand concrete needs to be chipped-off in order have its finishes same level with the existing aluminum transom or flushed to existing painted walls. Please confirm action to be done for the existing upstand concrete at Maid's Rooms Apartments 903 and 904 or wherever applicable. | RR | ARK | 2019-06-02 | 2019-06-11 | 9 | -As mentioned & agreed during the site walk, the upstand will be chipped & removed by M/s TAAG. -M/s Greenline to continue the floor tile till the Aluminum Flashing. -Skirting should be followed the Aluminum Flashing. | A
0168 | ARK-0025 | 0 | MARBLE ON TOP OF BATH TUB AT STUDIO B - WITHOUT PROVISION FOR FIXED GLASS ENCLOSURE |  |  | The marble top above bath tub at Studio B, Levels 11 to 17 had been installed without provision of fixed shower glass enclosure. Our marble sub-contractor Stone Factory presented a sample cutting on the installed marble top. However, the result is not acceptable in terms of quality and stability due to difficulty in cutting and its direct connection on the bath tub surface and wall tiles (fixed on plywood and silicate board), refer to attached photos and details. Above-mentioned comments were discussed with MKM Mr. Noushad and Stone Factory's Mr. Pradeep, a proposal to install the SS U Channel 20x16x20mm (316 Grade) on top and at the middle of the marble itself will be submitted for approval (thru the attached detail). In addition, the location of the 600x600mm permanent access panel will be affected by the fixed glass shower enclosure, refer to the projection of the glass enclosure on the wall and on the ceiling. Please advise fixing detail to be used if the above-mentioned fixing detail and relocation of glass enclosure is not acceptable and please confirm also thru this RFI the necessary relocation of 600x600mm permanent access panel. | RR | ARK | 2019-06-08 | 2019-06-15 | 7 | -KEPT THE GROVE FOR GLASS AT THE CTENTER OF MARBLE PORTION, & INSET THE U-CHANNEL. -KEEP THE ACCESS PANEL AWAY FROM THE GLASS. | A
0169 | ARK-0026 | 0 | SITE CONSTRAINTS - EXISTING MEP SERVICES OBTRUCTING INSTALLATION OF 1000mmx800mm ACCESS PANELS INSIDE MASTER'S BATHROOMS |  |  | As of this date, the above-mentioned subject still exist and gypsum ceiling boards cannot be completed (refer to attached photos and copy of email). 1. Two-Bedroom Apartments 1503 & 1403 and One-Bedroom Apartments 1408, 1409 & 1109: - As per attached CVI-0014, 1000mmx800mm access panels with 2-step recessed ceiling design are required. - These access panels were designated also as permanent access panels by MEP. However, due to the obstruction caused by MEP services, installation of access panels is not possible and even the 2-step recessed ceiling design cannot be done. - Apartment 1409 sprinkler head was even dropped within the access panel location. 2. Studio A Apartments 1402 & 1405: - As per attached CVI-0014 00, 1000mmx800mm access panels are not required but the 2-step recessed ceiling design are required but cannot be done due to the obstruction caused by MEP services. 3. Related issue on access panels: - Studio B has a standard 1000mmx800mm access panel as per approved shop drawing with 2-step recessed ceiling design. - However, this access panel was designated also as permanent access panel by MEP but with the dimension of 600mmx600mm only and without the usual 2-step recessed ceiling design (flat ceiling), refer to attached approved permanent access panel drawing WAF-TA-ALL-DSE-CE-RCP-SD-6524 01. - According to DSE Eng'r. Nedal, these dimension of 600mmx600mm permanent access panel on a flat ceiling is required. MKM Mr. Noushad was informed about this and conformed with it, Please advise what action should be taken on item 1 above and with regards to item 2, please advise if the 2-step recessed ceiling design can be deleted (same flat ceiling on item 3). | RR | ARK | 2019-06-09 | 2019-06-15 | 6 | ITEM - 1 & 2. THE FF PIPE WILL BE CHANGED BY MEP CONTRACTOR TO ENABLE THE ACCESS PANEL INSTALLATION. ITEM-3. PLEASE KEEP ACCESS PANEL SIZE AAS PER APPROVED SHOP DRAWING, (1000X800) WHICH IS BIGGER THAN THE REQUIRED SIZE BY MEP. | A
0170 | ARK-0027 | 0 | BATHROOM MIRRORS - LEVELS 10 TO 17 APARTMENTS BATHROOMS & GUEST TOILETS |  |  | The installation of the above-mentioned subject started two months ago and as of this date, mirrors from 17F down to 10F were installed already (refer to attached progress table). A width of 2050mm mirrors were installed at 3-Bedroom Apartments 01 & 06 Master's Bathrooms, Levels 10F to 15F & 17F and Apartments 05 Master's Bathroom, Level 16 instead of required 1950mm based on the attached Mirror Schedule which we received only a week ago. Likewise, a width of 2050mm mirrors also were installed at 2-Bedroom Apartments 03 & 04 Master's Bathroom, Levels 10F to 15F & 17F and Apartments 02 & 03, Level 16 instead of required 2150mm based also on the attached Mirror Schedule. At 2-Bedroom Apartments 03 & 04 Twin Bed Bathrooms, a width of 1550mm mirrors were installed also at Levels 10F to 15F & 17F and Apartments 02 & 03, Level 16 instead of required 1650mm. Please advise relocation of above-mentioned mirrors to their proper locations and change them with correct sizes (all these mirrors that need to be changed are highlighted on the attached progress table). | RR | ARK | 2019-06-13 | 2019-06-18 | 5 | -Please fix the mirror as per the attached schedule, since the mirror delivered as per attached schedule only. | A
0171 | ARK-0028 | 0 | REQUIRED SKIRTING HEIGHT ALONG HIGH LEVEL ALUMINUM TRANSOM WITH GYPSUM CLADDING |  |  | Please advise to proceed installation of 120mm high TM-101 Wooden Skirting as indicated on the attached approved shop drawing 1252-MKM-05Q-IDP-01-DWG-0602 1/1 01 (3D view shown below) to Levels 19 to 41 along the Façade areas at Gridlines 2'/B'-F' and 6'/B'-F' (refer to highlighted areas on the attached key plans). The height of the aluminum transon on these areas is 650mm and cladded with gypsum boards. The 120mm high wood skirting intended for these areas for Levels 19 to 28 had been delivered already and skirtings for Levels 29 to 33 were finished and will be delivered next week. | RR | ARK | 2019-06-18 | 2019-06-24 | 6 | -Please proceed as per the approved drawings. | A
0172 | ARK-0029 | 0 | APARTMENT 1601 - BIGGER DB DOOR PANEL FOR EXISTING THREE ELECTRICAL BOXES |  |  | The number of electrical boxes inside DB Cabinet was increased to 3 (refer to attached photo) instead of 2 as indicated on approved shop drawing 1252-MKM-05Q-IDP-01-DWG-PA-0316 1/1 01. Width of the door panels (2x660mm = 1320mm) will not be enough anymore to access all the 3 electrical boxes which has a total coverage length of 1630mm from edge to edge. Please advise new dimensions as per site condition shown on the attached photo. | RR | ARK | 2019-06-26 | 2019-07-03 | 7 | -PROPOSED 2 PANELS DOOR EQUAL & CENTER ON THE WALL 300X 1710/2 X 300 SHOP DRAWINGS. - ID/DGA WILL APPROVE YOUR PROPOSAL. NOTE: PLEASE REFER TO ATTACHED DGA EMAIL & SKETCH FOR DB 2 PANELS DOOR APPROVAL. PROCEED ACCORDINGLY. | A
0173 | ARK-0030 | 0 | WOODEN PEDESTAL FOR FRIDGE INSIDE THE PANTRY CABINET, ALL PANTRY UNITS 8F TO 17F |  |  | This is to formalize officially provision of the above-mentioned subject thru this RFI form. The height of the bottom fridge door is shorter than the height of the Veneer finish MDF door. This condition required a wooden pedestal to elevate the fridge so that the topside of the bottom fridge door will match the topside level of the Veneer finish MDF door, refer to attached photos. Mock-up Apartment 901 has the same wooden pedestal installed, refer below. Please advise. | RR | ARK | 2019-07-13 | 2019-07-16 | 3 | Confirmed Proceed. Kindly submit your quotation for review by the Eng. | A
0174 | ARK-0031 | 0 | HEADBOARD EXTENDING BEYOND CURTAIN AREA AT 17F APARTMENTS 01&06 SECONDARY KING & TWIN BEDROOMS AND APARTMENTS 03&04 SECONDARY TWIN BEDROOMS |  |  | Please find attached photos of the above-mentioned subject which were installed based on the attached approved shop drawings for 3-Bedroom Apts and as per CI-0094 01 for 2-Bedroom Apts: Three-Bedroom Apartment Units: - Headboard Type 01 (SWA-318) were installed based on DWG-0340 2/2 02 for 3-Bedroom Secondary King, Apts 1701 & 1706. - Headboard Type 03 (SWA-326) were installed based on DWG-0342 1/1 02 for 3-Bedroom Secondary Twin, Apts 1701 & 1706. The furniture layout on these shop drawings are the same as indicated on CI-0094 01 drawings. Two-Bedroom Apartment Units: - Headboard (SWA-326) was installed based on CI-0094 01 drawing DWG-418-WAP2B-7-101 01 for 2- Bedroom Secondary Twin, Apts 1703 & 1704. Approved shop drawing DWG-0343 1/1 02 with 2 bedside tables was not used since the distance between the curtains and the bathroom wall can accommodate only one bedside table. This condition fits the layout indicated on drawing DWG-418-WAP2B-7-101 01 under CI-0094 01 with only 1 bedside table (between Twin Beds). Despite following the approved drawings, all the Headboards mentioned above still extend beyond the curtain areas. Please advise what action has to be taken before installation of wall paper and carpet commence. | RR | ARK | 2019-07-27 | 2019-08-04 | 8 | ID: Comments on attached drawings. Please discuss if not clear. | A
0175 | ARK-0032 | 0 | FURNITURE LAYOUT - HEADBOARDS & BEDSIDE TABLES: - APTS 801 & 806 THREE BEDROOM SECONDARY TWIN BED - APTS 803 & 804 TWO BEDROOM SECONDARY TWIN BED |  |  | Please advise which drawings to follow for the above-mentioned subject where number of Bedside Tables differ from each other. @ Apartment 801 & 806 Secondary Twin Bed have: 1. As per CI-0094 01 drawing DWG 418-WAP3BB-7-100-00 0 - Only one (1) Bedside Table (in the middle) 2. As per approved GLI shop drawing 1252-MKM-05Q-IDP-01-DWG-0164 1/2 02 - Three (3) Bedside Tables @ Apartment 803 & 804 Secondary Twin Bed have: 3. As per CI-0094 01 drawing DWG 418-WAP2BB-7-100-00 0 - Two (2) Bedside Tables 4. As per approved GLI shop drawing 1252-MKM-05Q-IDP-01-DWG-0146 2/2 00 - Three (3) Bedside Tables Please indicate also furniture layout reference (distance) of Bedside Table or Headboard from the Bathroom Walls. | RR | ARK | 2019-07-27 | 2019-07-31 | 4 | -Please proceed as per latest drawing from WAI. CI-0094 Rev.01 | A
0176 | ARK-0033 | 0 | HEIGHT OF PANTRY UNITS & DB CABINETS @ APTS 806, 801, 808 & 809 |  |  | The gypsum ceiling levels at 1 & 3- Bedroom Apartments 808, 809, 801 & 806 Kitchen and DB areas were installed at El. +2500mm based on attached copy of RFI-0023 01 dated 04 March 2017. The existing gypsum board ceiling at +2500mm FCL had to be changed to +2400mm under CI-0094 01 drawings 418-WAP1BB-7-100-00 Rev. 0 for 1-Bedroom & 418-WAF3BB-7-200-00 Rev. 0 for 3-Bedroom received on 26 June 2018. However, existing FCLs of at both apartments were not changed based on the commented WAFI-BRK-CVI-0008, 0009, 0001 & 0006 issued by BRK Interior Decor to MKM. WAI comments on CVI-0008, 0009 & 0006 to manufacture the Kitchen units in accordance with the existing FCLs were received on 13 June 2019 from BRK upon request of GLI. The 2400mm high Pantry units and DB Cabinets delivered at site were produced based on CI-0094 01 and started delivery as early as February of this year. Accordingly, the height of the gap will be 100mm for the Kitchen and DBs for apartments mentioned above, refer to attached photo taken at apartments 801 & 808. For your confirmation or other advice. | RR | ARK | 2019-08-18 |  | 8 |  | OD
0177 | ARK-0034 | 0 | ONE-BEDROOM APARTMENTS 808 & 809 REVISED TO DISABLED UNITS |  |  | The door openings at Main Entrance, Bedroom & Bathroom and the wall openings at Wardrobe & Shower / Water Closet areas at Apartments 808 and 809 were not modified to suit the required openings indicated on CI-0094 01 drawing 418-WAP1BB-7-100-00 Rev 3 and Bathroom was not modified to comply with comments indicated on drawings 1252-MKM-05Q-IDP-01-DWG-0135 03 & 04 under RFI-0138 00. As-built dimensions / distances of openings from various reference points are indicated on the attached drawing 418-WAP1BB-7-100-00 Rev 3. Likewise, photos were attached including the existing structures inside the Bathroom. Please issue corresponding Site Instruction to respective Contractors to modify & confirm the following items of works: 1. Widen door openings at Main entrance, Bedroom and Bathroom - by civil contractor 2. Widen wall openings at Wardrobe and Shower / Water Closet areas - by civil contractor 3. Removal of existing shower bench with marble top and tiles on all sides (had been installed before CI-0094 01 is issued) - by GLI 4. Removal of glass shower enclosure unit including U-channels on wall tiles (had been installed before CI-0094 01 is issued) - by GLI 5. Removal of existing marble thresholds 15mm & 20mm above FFL at Bathroom door and shower area respectively (had been installed before CI-0094 01 is issued) and reinstall new thresholds same levels with the floor tiles. Take note that floor tiles at shower bench area is 10mm higher than outside floor tiles - by GLI 6. Restoration of floor and wall tiles as a result of the above-mentioned modification works - by GLI | RR | ARK | 2019-08-19 | 2019-08-24 | 5 | NOTED. SI will be provided to TAAG to proceed with modification of the door way openings in the Apt 808 and 809. GLI are however to proceed with the works tht are in their scope in accordance with the H/Capped rooms. | A
0178 | ARK-0035 | 0 | BED BASE FOR ZIP AND LOCK BED |  |  | With reference to above mentioned subject and attached received commented shop drawing with a comment of not recommendable this detail as this affect the bed side table, you are requested to provide us the relevant bed base details to make the shop drawing and advise the issues to proceed further. Your quick response will be highly appreciated. | SS | ARK | 2019-08-22 |  | 4 |  | P
[13 empty] | 0 |  | 1 2 60
-
Summary of RFI Log
|  |  | Total No. of RFIs Submitted | Nos Replied |  | Not Replied -P (Less than 7 days) | Not Replied -OD (More than 7 days)
|  |  | 202 | 197 |  | 1 | 4
0
Formulas:
Time Taken to Reply = IF([Date Submitted]="","", IF([Date Received]="",TODAY()-[Date Submitted],[Date Received]-[Date Submitted]))
Status Code = IF([Date Submitted]="",0,IF(((TODAY())-[Date Submitted])>7,"OD","P"))