## Summary
GREENLINE INTERIORS
XYZ PROJECT CITY ABC 2564
SUMMARY OF SHOP DRAWING LOG
As of: 26/8/2019
LEGEND: DRAWING NO: (Example) 1252-MKM-01-SD-0101 |  |  |  | 1252- GLI PROJECT REF, MKM-CLIENT, 01-PACKAGE, SD-SHOP DRAWING, 0101-SEQUENCE NUMBER
Sr. No. | Area | APPROVED (A) | APPROVED AS NOTED (B) | INTERNAL REVIEW RETURN FOR CORRECTION (IR) | REVISE & RESUBMIT (C): | REJECTED (D) | SUBMITTED FOR CONSULTANT COMMENTS (P) | OVERDUE (OD) | TOTAL DRAWINGS SUBMITTED (A+B+C+D+P+OD+IR) | NO LONGER IN USE (X) | FOR INFORMATION (FI) | TOTAL DRAWINGS | BALANCE DRAWINGS TO BE SUBMITTED | ISSUED TO SITE, AWAITED ACKNOWLEDGEMENT
A | 100_GENERAL ARRANGEMENT PLANS | 9 | 0 | 0 | 0 | 0 | 0 | 0 | 9 | 0 | 0 | 9 | 0 | 0
|  | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 100% |  |  | 100% | 0% | 0%
B | 100_FURNITURE,RCP, WALL FINISHES & KEY PLANS - BY ROOM TYPE | 11 | 131 | 0 | 10 | 0 | 0 | 2 | 154 | 1 | 0 | 154 | 0 | 1
|  | 7.143% | 85.06% | 0% | 6.494% | 0% | 0% | 1.299% | 100% |  |  | 100% | 0% | 0.6494%
B.1 | APARTMENT STUDIO UNIT A TYPE (ASA1) | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 5 | 0 | 0 | 5 | 0 | 0
|  | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 100% |  |  | 100% | 0% | 0%
B.2 | APARTMENT STUDIO UNIT A TYPE (ASA2) | 0 | 4 | 0 | 2 | 0 | 0 | 0 | 6 | 0 | 0 | 6 | 0 | 0
|  | 0% | 66.67% | 0% | 33.33% | 0% | 0% | 0% | 100% |  |  | 100% | 0% | 0%
B.3 | APARTMENT STUDIO UNIT A TYPE (ASA3) | 1 | 4 | 0 | 0 | 0 | 0 | 0 | 5 | 0 | 0 | 5 | 0 | 0
|  | 20% | 80% | 0% | 0% | 0% | 0% | 0% | 100% |  |  | 100% | 0% | 0%
B.4 | APARTMENT STUDIO UNIT B TYPE (ASB1) | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 5 | 0 | 0 | 5 | 0 | 0
|  | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 100% |  |  | 100% | 0% | 0%
B.5 | APARTMENT STUDIO UNIT B TYPE (ASB2) | 0 | 4 | 0 | 2 | 0 | 0 | 0 | 6 | 0 | 0 | 6 | 0 | 0
|  | 0% | 66.67% | 0% | 33.33% | 0% | 0% | 0% | 100% |  |  | 100% | 0% | 0%
B.6 | APARTMENT STUDIO UNIT B TYPE (ASB3) | 2 | 3 | 0 | 0 | 0 | 0 | 0 | 5 | 0 | 0 | 5 | 0 | 0
|  | 40% | 60% | 0% | 0% | 0% | 0% | 0% | 100% |  |  | 100% | 0% | 0%
B.7 | APARTMENT 1 BEDROOM UNIT TYPE (A1B1) | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 4 | 0 | 0
|  | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 100% |  |  | 100% | 0% | 0%
B.8 | APARTMENT 1 BEDROOM UNIT TYPE (A1B2) | 0 | 4 | 0 | 2 | 0 | 0 | 0 | 6 | 0 | 0 | 6 | 0 | 0
|  | 0% | 66.67% | 0% | 33.33% | 0% | 0% | 0% | 100% |  |  | 100% | 0% | 0%
B.9 | APARTMENT 1 BEDROOM UNIT TYPE (A1B3) | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 4 | 0 | 0
|  | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 100% |  |  | 100% | 0% | 0%
B.10 | APARTMENT 2 BEDROOM UNIT TYPE (A2B1) | 0 | 9 | 0 | 0 | 0 | 0 | 0 | 9 | 0 | 0 | 9 | 0 | 0
|  | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 100% |  |  | 100% | 0% | 0%
B.11 | APARTMENT 2 BEDROOM UNIT TYPE (A2B2) | 2 | 6 | 0 | 2 | 0 | 0 | 0 | 10 | 0 | 0 | 10 | 0 | 0
|  | 20% | 60% | 0% | 20% | 0% | 0% | 0% | 100% |  |  | 100% | 0% | 0%
B.12 | APARTMENT 2 BEDROOM UNIT TYPE (A2B3) | 3 | 7 | 0 | 0 | 0 | 0 | 0 | 10 | 0 | 0 | 10 | 0 | 0
|  | 30% | 70% | 0% | 0% | 0% | 0% | 0% | 100% |  |  | 100% | 0% | 0%
B.13 | APARTMENT 3 BEDROOM UNIT TYPE (A3B1) | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 10 | 0 | 0 | 10 | 0 | 0
|  | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 100% |  |  | 100% | 0% | 0%
B.14 | APARTMENT 3 BEDROOM UNIT TYPE (A3B2) | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 10 | 0 | 0 | 10 | 0 | 0
|  | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 100% |  |  | 100% | 0% | 0%
B.15 | APARTMENT 3 BEDROOM UNIT TYPE (A3B3) | 0 | 9 | 0 | 0 | 0 | 0 | 0 | 9 | 0 | 0 | 9 | 0 | 0
|  | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 100% |  |  | 100% | 0% | 0%
B.16 | GUEST ROOMS JUNIOR SUITE UNIT TYPE (GJS1) & (GJS1A) | 0 | 6 | 0 | 1 | 0 | 0 | 0 | 7 | 1 | 0 | 7 | 0 | 0
|  | 0% | 85.71% | 0% | 14.29% | 0% | 0% | 0% | 100% |  |  | 100% | 0% | 0%
B.17 | GUEST ROOMS 1 BEDROOM SUITE A TYPE (G1BA) | 0 | 6 | 0 | 1 | 0 | 0 | 0 | 7 | 0 | 0 | 7 | 0 | 0
|  | 0% | 85.71% | 0% | 14.29% | 0% | 0% | 0% | 100% |  |  | 100% | 0% | 0%
B.18 | GUEST ROOMS 1 BEDROOM SUITE B TYPE (G1BB) | 0 | 5 | 0 | 0 | 0 | 0 | 2 | 7 | 0 | 0 | 7 | 0 | 0
|  | 0% | 71.43% | 0% | 0% | 0% | 0% | 28.57% | 100% |  |  | 100% | 0% | 0%
B.19 | GUEST ROOMS STANDARD ROOM UNIT TYPE (GSR1) & (GSR1A) | 0 | 8 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 8 | 0 | 0
|  | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 100% |  |  | 100% | 0% | 0%
B.20 | GUEST ROOMS STANDARD ROOM UNIT TYPE (GSR1B) | 1 | 8 | 0 | 0 | 0 | 0 | 0 | 9 | 0 | 0 | 9 | 0 | 1
|  | 11.11% | 88.89% | 0% | 0% | 0% | 0% | 0% | 100% |  |  | 100% | 0% | 11.11%
B.21 | GUEST ROOMS STANDARD HANDICAPPED ROOM UNIT TYPE (GSRH) | 0 | 6 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 6 | 0 | 0
|  | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 100% |  |  | 100% | 0% | 0%
B.22 | EXECUTIVE ROOM UNIT TYPE (GER1B) | 2 | 4 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 6 | 0 | 0
|  | 33.33% | 66.67% | 0% | 0% | 0% | 0% | 0% | 100% |  |  | 100% | 0% | 0%
C | 300_MILLWORK DETAILS | 28 | 105 | 0 | 3 | 0 | 0 | 6 | 142 | 0 | 0 | 142 | 0 | 0
|  | 19.72% | 73.94% | 0% | 2.113% | 0% | 0% | 4.225% | 100% |  |  | 100% | 0% | 0%
D | 0 | 3 | 21 | 0 | 0 | 0 | 0 | 0 | 24 | 0 | 0 | 24 | 0 | 0
|  | 12.5% | 87.5% | 0% | 0% | 0% | 0% | 0% | 100% |  |  | 100% | 0% | 0%
E | Door Schedule | 4 | 17 | 0 | 0 | 0 | 0 | 0 | 21 | 0 | 0 | 21 | 0 | 0
|  | 19.05% | 80.95% | 0% | 0% | 0% | 0% | 0% | 100% |  |  | 100% | 0% | 0%
F | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 10 | 0 | 0 | 10 | 0 | 0
|  | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 100% |  |  | 100% | 0% | 0%
G | CORRIDOR | 3 | 30 | 0 | 0 | 0 | 0 | 0 | 33 | 0 | 0 | 33 | 0 | 0
|  | 9.091% | 90.91% | 0% | 0% | 0% | 0% | 0% | 100% |  |  | 100% | 0% | 0%
G.1 | Corridor Details, Plan & Elevation @ 8th to 17th Floor | 3 | 30 | 0 | 0 | 0 | 0 | 0 | 33 | 0 | 0 | 33 | 0 | 0
|  | 9.091% | 90.91% | 0% | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 100% | 0% | 0%
H | 16TH FLOOR PRIVATE ROOM | 29 | 122 | 0 | 24 | 0 | 0 | 2 | 177 | 1 | 0 | 184 | 7 | 3
|  | 15.76% | 66.3% | 0% | 13.04% | 0% | 0% | 1.087% | 96.2% |  |  | 100% | 3.804% | 1.63%
H.1 | 100_GENERAL ARRANGEMENT PLANS | 14 | 19 | 0 | 0 | 0 | 0 | 0 | 33 | 0 | 0 | 33 | 0 | 0
|  | 42.42% | 57.58% | 0% | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 100% | 0% | 0%
H.2 | 300_MILLWORK DETAILS | 4 | 21 | 0 | 0 | 0 | 0 | 0 | 25 | 0 | 0 | 25 | 0 | 0
|  | 16% | 84% | 0% | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 100% | 0% | 0%
H.3 | 500_DOORS | 11 | 82 | 0 | 24 | 0 | 0 | 2 | 119 | 1 | 0 | 126 | 7 | 3
|  | 8.73% | 65.08% | 0% | 19.05% | 0% | 0% | 1.587% | 94.44% | 0.7937% | 0% | 100% | 5.556% | 2.381%
I | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
|  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
CUMULATIVE TOTAL (A+B+C+D+E+F+G) |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 1 2
|  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  |  | #REF! | #REF! | #REF! | 1 2

## SDS_Tracking_Log
XYZ PROJECT CITY ABC 2564
PROJECT SHOP DRAWING TRACKING LOG |  |  |  |  | As of:- 26/8/2019 |  |  | STATUS LEGEND
[8 empty] | A - Approved |  |  |  |  | P - Issued for Approval |  |  |  |  | SS - Superseded by New Revision
[8 empty] | B - Approved with Comments |  |  |  |  | OD - Overdue |  |  |  |  | IR- Issued for Coordination
[8 empty] | C - Resubmit |  |  |  |  | X - No Longer in Use/Not in Scope
[8 empty] | D - Rejected |  |  |  |  | FI-For Information
S/N | GLI Submittal Ref. |  | Level | Description | Drawing No. | Sheet # | Scheduled Submittal Date | 1ST SUBMITTAL |  |  |  |  | 2ND SUBMITTAL |  |  |  |  | 3RD SUBMITTAL |  |  |  |  | 4TH SUBMITTAL |  |  |  |  | 5TH SUBMITTAL |  |  |  |  | 6TH SUBMITTAL |  |  |  |  | 7TH SUBMITTAL |  |  |  |  | 8TH SUBMITTAL |  |  |  |  | 9TH SUBMITTAL |  |  |  |  | 10TH SUBMITTAL |  |  |  |  | FINAL STATUS |  |  |  |  | Modified Status | Reason/ Notes | Planned Re-submission Date | Remarks/Notes
|  | ARK Submittal Ref. | [5 empty] | Date Submitted | Date Commented | Time Taken to Reply | Status | Issued To / Commented By | Date Submitted | Date Commented | Time Taken to Reply | Status | Issued To / Commented By | Date Submitted | Date Commented | Time Taken to Reply | Status | Issued To / Commented By | Date Submitted | Date Commented | Time Taken to Reply | Status | Issued To / Commented By | Date Submitted | Date Commented | Time Taken to Reply | Status | Issued To / Commented By | Date Submitted | Date Commented | Time Taken to Reply | Status | Issued To / Commented By | Date Submitted | Date Commented | Time Taken to Reply | Status | Issued To / Commented By | Date Submitted | Date Commented | Time Taken to Reply | Status | Issued To / Commented By | Date Submitted | Date Commented | Time Taken to Reply | Status | Issued To / Commented By | Date Submitted | Date Commented | Time Taken to Reply | Status | Issued To / Commented By | Date Submitted | Date Commented | Time Taken to Reply | Status | Revision
100_GENERAL ARRANGEMENT PLANS | [62 empty] | 0 |  |  |  | 1 2
1 | SD-0004-00 |  | 8 | (8th Floor) General Arrangement Plan | 1252-MKM-05Q-IDP-01-DWG-0101 | 1 OF 1 | 2016-12-22 | 2016-12-22 | 2017-01-10 | 19 | A | MKM | [45 empty] | 2016-12-22 | 2017-01-10 | 19 | A | Rev-0 | A/C | Resub..reqd | 2018-04-17 |  | 1 5 | MKM
2 | SD-0008-00 |  | 9 to 13 | (9th to 13th Floor) General Arrangement Plan | 1252-MKM-05Q-IDP-01-DWG-0102 | 1 OF 1 | 2016-12-22 | 2017-01-03 | 2017-01-10 | 7 | A | MKM | [45 empty] | 2017-01-03 | 2017-01-10 | 7 | A | Rev-0 | A/C | Resub..reqd | 2018-04-17 |  | 1 5 | MKM
3 | SD-0024-00 |  | 14,15 & 17 | (14th, 15th, 17th Floor) General Arrangement Plan | 1252-MKM-05Q-IDP-01-DWG-0103 | 1 OF 1 | 2017-01-22 | 2017-01-23 | 2017-02-14 | 22 | A | MKM | [45 empty] | 2017-01-23 | 2017-02-14 | 22 | A | Rev-0 | A/C | Resub..reqd | 2018-04-17 |  | 1 5 | MKM
4 | SD-0024-00 |  | 16 | (16th Floor) General Arrangement Plan | 1252-MKM-05Q-IDP-01-DWG-0104 | 1 OF 1 | 2017-01-22 | 2017-01-23 | 2017-02-14 | 22 | A | MKM | [45 empty] | 2017-01-23 | 2017-02-14 | 22 | A | Rev-0 | A/C | Resub..reqd | 2018-04-17 |  | 1 5 | MKM
5 | SD-0014-00 |  | 19 to 23 | General Arrangement Plan 19th to 23rd Floor | 1252-MKM-05Q-IDP-01-DWG-0105 | 1 OF 1 | 2017-01-24 | 2017-01-23 | 2017-01-29 | 6 | A | MKM | [45 empty] | 2017-01-23 | 2017-01-29 | 6 | A | Rev-0 | A/C | Resub..reqd | 2018-04-17 |  | 1 5 | MKM
6 | SD-0014-01 |  | 24 to 29 | (24th to 29th Floor) General Arrangement Plan | 1252-MKM-05Q-IDP-01-DWG-0106 | 1 OF 1 | 2017-01-24 | 2017-01-23 | 2017-01-29 | 6 | C | MKM | 2017-03-15 | 2017-04-02 | 18 | A | MKM | [40 empty] | 2017-03-15 | 2017-04-02 | 18 | A | Rev-1 | A/C | Resub..reqd | 2018-04-17 |  | 1 5 | MKM
7 | SD-0014-01 |  | 30 | (30th Floor) General Arrangement Plan | 1252-MKM-05Q-IDP-01-DWG-0107 | 1 OF 1 | 2017-01-26 | 2017-01-23 | 2017-01-29 | 6 | C | MKM | 2017-03-15 | 2017-04-02 | 18 | A | MKM | [40 empty] | 2017-03-15 | 2017-04-02 | 18 | A | Rev-1 | A/C | Resub..reqd | 2018-04-17 |  | 1 5 | MKM
8 | SD-0014-01 |  | 31 to 36 | (31st to 36th Floor) General Arrangement Plan | 1252-MKM-05Q-IDP-01-DWG-0108 | 1 OF 1 | 2017-01-26 | 2017-01-23 | 2017-01-29 | 6 | C | MKM | 2017-03-15 | 2017-04-02 | 18 | A | MKM | [40 empty] | 2017-03-15 | 2017-04-02 | 18 | A | Rev-1 | A/C | Resub..reqd | 2018-04-17 |  | 1 5 | MKM
9 | SD-0014-01 |  | 37 to 41 | (37th to 41st Floor) General Arrangement Plan | 1252-MKM-05Q-IDP-01-DWG-0109 | 1 OF 1 | 2017-01-26 | 2017-01-23 | 2017-01-29 | 6 | C | MKM | 2017-03-15 | 2017-04-02 | 18 | A | MKM | [40 empty] | 2017-03-15 | 2017-04-02 | 18 | A | Rev-1 | A/C | Resub..reqd | 2018-04-17 |  | 1 5 | MKM
100_FURNITURE,RCP, WALL FINISHES & KEY PLANS - BY ROOM TYPE | [66 empty] | 1 12
APARTMENT STUDIO UNIT A TYPE (ASA1) | [66 empty] | 1 13
10 | SD-0001-03 |  | 8 | 8th Floor Studio unit-A Type-1 Apartment (ASA1) General Arrangement Plan | 1252-MKM-05Q-IDP-01-DWG-0110 | 1 OF 2 | 2017-01-16 | 2016-12-19 | 2017-01-08 | 20 | C | MKM | 2017-01-16 | 2017-01-23 | 7 | B | MKM | 2018-07-12 | 2018-08-06 | 25 | B | MKM | [35 empty] | 2018-07-12 | 2018-08-06 | 25 | B | Rev-2 | B | Approved | NA
11 | SD-0001-03 |  | 8 | 8th Floor Studio unit-A Type-1 Apartment (ASA1) Power Plan | 1252-MKM-05Q-IDP-01-DWG-0110 | 2 OF 2 |  | 2018-07-12 | 2018-08-06 | 25 | B | MKM | [45 empty] | 2018-07-12 | 2018-08-06 | 25 | B | Rev-0 | B | Approved | NA
12 | SD-0001-02 |  | 8 | 8th Floor Studio Unit 'A' Type-1 Apartment (ASA1) Plans Ceiling Plan & Details | 1252-MKM-05Q-IDP-01-DWG-0111 | 1 OF 2 | 2017-01-16 | 2016-12-19 | 2017-01-08 | 20 | C | MKM | 2017-01-16 | 2017-01-23 | 7 | B | MKM | 2018-06-25 | 2018-06-28 | 3 | B | MKM | [35 empty] | 2018-06-25 | 2018-06-28 | 3 | B | Rev-2 | B | Approved | NA |  | 1 5 | MKM
13 | SD-0001-01 |  | 8 | 8th Floor Studio Unit 'A' Type-1 Apartment (ASA1) Elevations A & B | 1252-MKM-05Q-IDP-01-DWG-0112 | 1 OF 1 | 2017-01-16 | 2016-12-19 | 2017-01-08 | 20 | C | MKM | 2017-01-16 | 2017-01-23 | 7 | B | MKM | [40 empty] | 2017-01-16 | 2017-01-23 | 7 | B | Rev-1 | B | Approved | NA |  | 1 5 | MKM
14 | SD-0001-01 |  | 8 | 8th Floor Studio Unit 'A' Type-1 Apartment (ASA1) Elevations C & D | 1252-MKM-05Q-IDP-01-DWG-0113 | 1 OF 1 | 2017-01-16 | 2016-12-19 | 2017-01-08 | 20 | C | MKM | 2017-01-16 | 2017-01-23 | 7 | B | MKM | [40 empty] | 2017-01-16 | 2017-01-23 | 7 | B | Rev-1 | B | Approved | NA |  | 1 5 | MKM
APARTMENT STUDIO UNIT A TYPE (ASA2) | [62 empty] | 0 |  |  |  | 1 20
15 | SD-0011-05 |  |  | 9th to 13th Floor Studio Unit ‘A’ Type-2 Apartment (ASA2) General Arrangement Plan | 1252-MKM-05Q-IDP-01-DWG-0114 | 1 OF 2 | 2017-01-19 | 2017-01-03 | 2017-01-12 | 9 | C | MKM | 2017-01-22 | 2017-02-12 | 21 | A | MKM | 2018-02-27 | 2018-03-13 | 14 | B | MKM | 2018-07-12 | 2018-07-17 | 5 | B | MKM | [30 empty] | 2018-07-12 | 2018-07-17 | 5 | B | Rev-3 | B | Approved | NA |  | 1 5 | MKM
16 | SD-0011-02 |  |  | 9th to 13th Studio Unit 'A' Type-2 Apartment (ASA2) Flooring Plan | 1252-MKM-05Q-IDP-01-DWG-0114 | 2 OF 2 | 2017-01-19 | 2018-02-27 | 2018-03-13 | 14 | B | MKM | [45 empty] | 2018-02-27 | 2018-03-13 | 14 | B | Rev-0 | B | Approved | NA |  | 1 5 | MKM
17 | SD-0011-04 |  |  | 9th to 13th Floor Studio Unit-A Type-2 Apartment (ASA2) Ceiling Plan & Details | 1252-MKM-05Q-IDP-01-DWG-0115 | 1 OF 2 | 2017-01-19 | 2017-01-03 | 2017-01-12 | 9 | C | MKM | 2017-01-22 | 2017-02-12 | 21 | A | MKM | 2018-02-27 | 2018-03-13 | 14 | C | MKM | 2018-03-20 | 2018-03-26 | 6 | C | MKM | 2018-06-25 | 2018-06-28 | 3 | B | MKM | [25 empty] | 2018-06-25 | 2018-06-28 | 3 | B | Rev-4 | C | Resub..reqd | 2018-04-08 |  | 1 5 | MKM
18 | SD-0011-05 |  |  | 9th to 13th Floor Studio Unit ‘A’ Type-2 Apartment (ASA2) Power Plan | 1252-MKM-05Q-IDP-01-DWG-0115 | 2 OF 2 | 2017-01-19 | 2018-02-27 | 2018-03-13 | 14 | B | MKM | 2018-07-12 | 2018-07-17 | 5 | B | MKM | [40 empty] | 2018-07-12 | 2018-07-17 | 5 | B | Rev-1 | C | Resub..reqd | 2018-04-08 |  | 1 5 | MKM
19 | SD-0011-03 |  |  | 9th to 13th Floor Studio Unit 'A' Type-2 Apartment (ASA2) Elevations A & B | 1252-MKM-05Q-IDP-01-DWG-0116 | 1 OF 1 | 2017-01-19 | 2017-01-03 | 2017-01-12 | 9 | C | MKM | 2017-01-22 | 2017-02-12 | 21 | A | MKM | 2018-02-27 | 2018-03-13 | 14 | C | MKM | 2018-03-20 | 2018-03-26 | 6 | C | MKM | [30 empty] | 2018-03-20 | 2018-03-26 | 6 | C | Rev-3 | C | Resub..reqd | 2018-04-08 |  | 1 5 | MKM
20 | SD-0011-03 |  |  | 9th to 13th Floor Studio Unit 'A' Type-2 Apartment (ASA2) Elevations C & D | 1252-MKM-05Q-IDP-01-DWG-0117 | 1 OF 1 | 2017-01-19 | 2017-01-03 | 2017-01-12 | 9 | C | MKM | 2017-01-22 | 2017-02-12 | 21 | A | MKM | 2018-02-27 | 2018-03-13 | 14 | C | MKM | 2018-03-20 | 2018-03-26 | 6 | C | MKM | [30 empty] | 2018-03-20 | 2018-03-26 | 6 | C | Rev-3 | C | Resub..reqd | 2018-04-08 |  | 1 5 | MKM
APARTMENT STUDIO UNIT A TYPE (ASA3) | [62 empty] | 0 |  |  |  | 1 27
21 | SD-0023-02 |  |  | 14th to 17th Floor Studio Unit ‘A’ Type-3 Apartment (ASA3) General Arrangement Plan | 1252-MKM-05Q-IDP-01-DWG-0118 | 1 OF 1 | 2017-01-19 | 2017-01-22 | 2017-02-13 | 22 | A | MKM | 2018-07-12 | 2018-07-17 | 5 | B | MKM | [40 empty] | 2018-07-12 | 2018-07-17 | 5 | B | Rev-1 | A/C | Resub..reqd | 2018-04-17 |  | 1 5 | MKM
22 | SD-0023-01 |  |  | 14th to 17th Floor Studio Unit ‘A’ Type-3 Apartment (ASA3) Ceiling Plan & Details | 1252-MKM-05Q-IDP-01-DWG-0119 | 1 OF 2 | 2017-01-19 | 2017-01-22 | 2017-02-13 | 22 | A | MKM | 2018-06-25 | 2018-06-28 | 3 | B | MKM | [40 empty] | 2018-06-25 | 2018-06-28 | 3 | B | Rev-1 | A/C | Resub..reqd | 2018-04-17 |  | 1 5 | MKM
23 | SD-0023-02 |  |  | 14th to 17th Floor Studio Unit ‘A’ Type-3 Apartment (ASA3) Power Plan | 1252-MKM-05Q-IDP-01-DWG-0119 | 2 OF 2 |  | 2018-07-12 | 2018-07-17 | 5 | B | MKM | [45 empty] | 2018-07-12 | 2018-07-17 | 5 | B | Rev-0 | A/C | Resub..reqd | 2018-04-17 |  | 1 5 | MKM
24 | SD-0023-00 |  |  | 14th to 17th Floor Studio Unit 'A' Type-3 Apartment (ASA3) Elevation A & B | 1252-MKM-05Q-IDP-01-DWG-0120 | 1 OF 1 | 2017-01-19 | 2017-01-22 | 2017-02-13 | 22 | B | MKM | [45 empty] | 2017-01-22 | 2017-02-13 | 22 | B | Rev-0 | B/C | Resub..reqd | 2018-04-17 |  | 1 5 | MKM
25 | SD-0023-00 |  |  | 14th to 17th Floor Studio Unit 'A' Type-3 Apartment (ASA3) Elevation C & D | 1252-MKM-05Q-IDP-01-DWG-0121 | 1 OF 1 | 2017-01-19 | 2017-01-22 | 2017-02-13 | 22 | A | MKM | [45 empty] | 2017-01-22 | 2017-02-13 | 22 | A | Rev-0 | A/C | Resub..reqd | 2018-04-17 |  | 1 5 | MKM
APARTMENT STUDIO UNIT B TYPE (ASB1) | [62 empty] | 0 |  |  |  | 1 34
26 | SD-0004-03 |  | 8 | 8th Floor Studio Unit 'B' Type-1 Apartment (ASB1) General Arrangement Plan | 1252-MKM-05Q-IDP-01-DWG-0122 | 1 OF 1 | 2017-01-16 | 2016-12-22 | 2017-01-10 | 19 | C | MKM | 2017-01-16 | 2017-01-19 | 3 | B | MKM | 2018-07-12 | 2018-07-17 | 5 | B | MKM | [35 empty] | 2018-07-12 | 2018-07-17 | 5 | B | Rev-2 | B/C | Resub..reqd | 2018-04-17 |  | 1 5 | MKM
27 | SD-0004-02 |  | 8 | 8th Floor Studio Unit 'B' Type -1 Apartment (ASB1) Reflected Ceiling Plan | 1252-MKM-05Q-IDP-01-DWG-0123 | 1 OF 2 | 2017-01-16 | 2016-12-22 | 2017-01-10 | 19 | C | MKM | 2017-01-16 | 2017-01-19 | 3 | B | MKM | 2018-06-25 | 2018-06-28 | 3 | B | MKM | [35 empty] | 2018-06-25 | 2018-06-28 | 3 | B | Rev-2 | B/C | Resub..reqd | 2018-04-17 |  | 1 5 | MKM
28 | SD-0004-04 |  | 8 | 8th Floor Studio Unit 'B' Type-1 Apartment (ASB1) Power Plan | 1252-MKM-05Q-IDP-01-DWG-0123 | 2 OF 2 |  | 2018-07-12 | 2018-07-17 | 5 | C | MKM | 2018-07-26 | 2018-08-06 | 11 | B | MKM | [40 empty] | 2018-07-26 | 2018-08-06 | 11 | B | Rev-1 | B/C | Resub..reqd | 2018-04-17 |  | 1 5 | MKM
29 | SD-0004-01 |  | 8 | Apartment Studio unit B Type (ASB1)_Elevations A & B | 1252-MKM-05Q-IDP-01-DWG-0124 | 1 OF 1 | 2017-01-16 | 2016-12-22 | 2017-01-10 | 19 | C | MKM | 2017-01-16 | 2017-01-19 | 3 | B | MKM | [40 empty] | 2017-01-16 | 2017-01-19 | 3 | B | Rev-1 | B/C | Resub..reqd | 2018-04-17 |  | 1 5 | MKM
30 | SD-0004-01 |  | 8 | Apartment Studio unit B Type (ASB1)_Elevations C & D | 1252-MKM-05Q-IDP-01-DWG-0125 | 1 OF 1 | 2017-01-16 | 2016-12-22 | 2017-01-10 | 19 | C | MKM | 2017-01-16 | 2017-01-19 | 3 | B | MKM | [40 empty] | 2017-01-16 | 2017-01-19 | 3 | B | Rev-1 | B/C | Resub..reqd | 2018-04-17 |  | 1 5 | MKM
APARTMENT STUDIO UNIT B TYPE (ASB2) | [62 empty] | 0 |  |  |  | 1 41
31 | SD-0013-05 |  | 9 to 13 | 9th to 13th Floor Studio Unit ‘B’ Type-2 Apartment (ASB2) General Arrangement Plan | 1252-MKM-05Q-IDP-01-DWG-0126 | 1 OF 2 | 2017-01-19 | 2017-01-03 | 2017-01-14 | 11 | C | MKM | 2017-01-22 | 2017-02-12 | 21 | B | MKM | 2018-02-26 | 2018-03-04 | 6 | B | MKM | 2018-07-12 | 2018-07-17 | 5 | B | MKM | [30 empty] | 2018-07-12 | 2018-07-17 | 5 | B | Rev-3 | B | Approved |  |  | 1 5 | MKM
32 | SD-0013-02 |  | 9 to 13 | Apartment Studio unit B Type (ASB2) Plans | 1252-MKM-05Q-IDP-01-DWG-0126 | 2 OF 2 | 2017-01-19 | 2018-02-26 | 2018-03-04 | 6 | B | MKM | [45 empty] | 2018-02-26 | 2018-03-04 | 6 | B | Rev-0 | B | Approved |  |  | 1 5 | MKM
33 | SD-0013-05 |  | 9 to 13 | 9th to 13th Floor Studio Unit ‘B’ Type-2 Apartment (ASB2) Power Plan | 1252-MKM-05Q-IDP-01-DWG-0127 | 1 OF 2 | 2017-01-19 | 2017-01-03 | 2017-01-14 | 11 | C | MKM | 2017-01-22 | 2017-02-12 | 21 | A | MKM | 2018-02-26 | 2018-03-04 | 6 | B | MKM | 2018-07-12 | 2018-07-17 | 5 | B | MKM | [30 empty] | 2018-07-12 | 2018-07-17 | 5 | B | Rev-3 | B | Approved |  |  | 1 5 | MKM
34 | SD-0013-04 |  | 9 to 13 | 9th to 13th Studio Unit 'B' Type- 2 Apartment (ASB2) Reflected Ceiling Plan | 1252-MKM-05Q-IDP-01-DWG-0127 | 2 OF 2 | 2017-01-19 | 2018-02-26 | 2018-03-04 | 6 | C | MKM | 2018-04-17 | 2018-05-01 | 14 | B | MKM | 2018-06-25 | 2018-06-28 | 3 | B | MKM | [35 empty] | 2018-06-25 | 2018-06-28 | 3 | B | Rev-2 | C | Resub..reqd | 2018-04-08 |  | 1 5 | MKM
35 | SD-0013-02 |  | 9 to 13 | 9th to 13 Floor Studio Unit 'B' Type-2 Apartment (ASB2) Elevations A & B | 1252-MKM-05Q-IDP-01-DWG-0128 | 1 OF 1 | 2017-01-19 | 2017-01-03 | 2017-01-14 | 11 | C | MKM | 2017-01-22 | 2017-02-12 | 21 | B | MKM | 2018-02-26 | 2018-03-04 | 6 | C | MKM | [35 empty] | 2018-02-26 | 2018-03-04 | 6 | C | Rev-2 | C | Resub..reqd | 2018-04-08 |  | 1 5 | MKM
36 | SD-0013-02 |  | 9 to 13 | 9th to 13 Floor Studio Unit 'B' Type-2 Apartment (ASB2) Elevations C | 1252-MKM-05Q-IDP-01-DWG-0129 | 1 OF 1 | 2017-01-19 | 2017-01-03 | 2017-01-14 | 11 | C | MKM | 2017-01-22 | 2017-02-12 | 21 | B | MKM | 2018-02-26 | 2018-03-04 | 6 | C | MKM | [35 empty] | 2018-02-26 | 2018-03-04 | 6 | C | Rev-2 | C | Resub..reqd | 2018-04-08 |  | 1 5 | MKM
APARTMENT STUDIO UNIT B TYPE (ASB3) | [62 empty] | 0 |  |  |  | 1 48
37 | SD-0015-03 |  |  | 14th to 17th Floor Studio Unit ‘B’ Type-3 Apartment (ASB3) General Arrangement Plan | 1252-MKM-05Q-IDP-01-DWG-0130 | 1 OF 1 | 2017-01-23 | 2017-01-23 | 2017-02-13 | 21 | A | MKM | 2018-07-12 | 2018-07-17 | 5 | B | MKM | [40 empty] | 2018-07-12 | 2018-07-17 | 5 | B | Rev-1 | A/C | Resub..reqd | 2018-04-17 |  | 1 5 | MKM
38 | SD-0015-02 |  |  | 14th to 16th Floor Studio Unit 'B' Type-3 Apartment (ASB3) Reflected Ceiling Plan | 1252-MKM-05Q-IDP-01-DWG-0131 | 1 OF 2 | 2017-01-23 | 2017-01-23 | 2017-02-13 | 21 | A | MKM | 2018-04-18 | 2018-05-01 | 13 | B | MKM | 2018-06-25 | 2018-06-28 | 3 | B | MKM | [35 empty] | 2018-06-25 | 2018-06-28 | 3 | B | Rev-2 | A/C | Resub..reqd | 2018-04-17 |  | 1 5 | MKM
39 | SD-0015-03 |  |  | 14th to 17th Floor Studio Unit ‘B’ Type-3 Apartment (ASB3) Power Plan | 1252-MKM-05Q-IDP-01-DWG-0131 | 2 OF 2 |  | 2018-07-12 | 2018-07-17 | 5 | B | MKM | [45 empty] | 2018-07-12 | 2018-07-17 | 5 | B | Rev-0 | A/C | Resub..reqd | 2018-04-17 |  | 1 5 | MKM
40 | SD-0015-00 |  |  | Apartment Studio unit B Type (ASB3)_Elevations | 1252-MKM-05Q-IDP-01-DWG-0132 | 1 OF 1 | 2017-01-23 | 2017-01-23 | 2017-02-13 | 21 | A | MKM | [45 empty] | 2017-01-23 | 2017-02-13 | 21 | A | Rev-0 | A/C | Resub..reqd | 2018-04-17 |  | 1 5 | MKM
41 | SD-0015-00 |  |  | Apartment Studio unit B Type (ASB3)_Elevations | 1252-MKM-05Q-IDP-01-DWG-0133 | 1 OF 1 | 2017-01-23 | 2017-01-23 | 2017-02-13 | 21 | A | MKM | [45 empty] | 2017-01-23 | 2017-02-13 | 21 | A | Rev-0 | A/C | Resub..reqd | 2018-04-17 |  | 1 5 | MKM
APARTMENT 1 BEDROOM UNIT TYPE (A1B1) | [62 empty] | 0 |  |  |  | 1 55
42 | SD-0005-03 |  | 8 | 8th Floor 1 Bedroom Unit Apartment (A1B1) Type-1 General Arrangement Plan | 1252-MKM-05Q-IDP-01-DWG-0134 | 1 OF 1 | 2017-01-16 | 2016-12-22 | 2017-01-10 | 19 | C | MKM | 2017-01-16 | 2017-02-12 | 27 | B | MKM | 2018-07-16 | 2018-07-22 | 6 | B | MKM | [35 empty] | 2018-07-16 | 2018-07-22 | 6 | B | Rev-2 | B/C | Resub..reqd | 2018-04-17 |  | 1 5 | MKM
43 | SD-0005-04 |  | 8 | 8th Floor 1 Bedroom Unit Apartment (A1B1) Type-1 Power Plan | 1252-MKM-05Q-IDP-01-DWG-0135 | 1 OF 1 | 2017-01-16 | 2016-12-22 | 2017-01-10 | 19 | C | MKM | 2017-01-16 | 2017-02-12 | 27 | B | MKM | 2018-06-25 | 2018-06-28 | 3 | B | MKM | 2018-07-16 | 2018-07-22 | 6 | C | MKM | 2018-08-29 | 2018-09-05 | 7 | B | MKM | [25 empty] | 2018-08-29 | 2018-09-05 | 7 | B | Rev-4 | B/C | Resub..reqd | 2018-04-17 |  | 1 5 | MKM
44 | SD-0005-01 |  | 8 | 8th Floor 1 Bedroom Unit Apartment (A1B1) Type-1 Elevations A & B | 1252-MKM-05Q-IDP-01-DWG-0136 | 1 OF 1 | 2017-01-16 | 2016-12-22 | 2017-01-10 | 19 | C | MKM | 2017-01-16 | 2017-02-12 | 27 | B | MKM | [40 empty] | 2017-01-16 | 2017-02-12 | 27 | B | Rev-1 | B/C | Resub..reqd | 2018-04-17 |  | 1 5 | MKM
45 | SD-0005-01 |  | 8 | 8th Floor 1 Bedroom Unit Apartment (A1B1) Type-1 Elevations C & D | 1252-MKM-05Q-IDP-01-DWG-0137 | 1 OF 1 | 2017-01-16 | 2016-12-22 | 2017-01-10 | 19 | C | MKM | 2017-01-16 | 2017-02-12 | 27 | B | MKM | [40 empty] | 2017-01-16 | 2017-02-12 | 27 | B | Rev-1 | B/C | Resub..reqd | 2018-04-17 |  | 1 5 | MKM
APARTMENT 1 BEDROOM UNIT TYPE (A1B2) | [62 empty] | 0 |  |  |  | 1 62
46 | SD-0009-05 |  | 9 to 13 | 9th to 13th Floor One Bedroom Unit Apartment (A1B2) Type-2 General Arrangement Plan | 1252-MKM-05Q-IDP-01-DWG-0138 | 1 OF 2 | 2017-01-18 | 2017-01-03 | 2017-01-10 | 7 | C | MKM | 2017-01-18 | 2017-02-13 | 26 | B | MKM | 2018-02-27 | 2018-03-13 | 14 | B | MKM | 2018-07-16 | 2018-07-22 | 6 | B | MKM | [30 empty] | 2018-07-16 | 2018-07-22 | 6 | B | Rev-3 | B | Approved |  |  | 1 5 | MKM
47 | SD-0009-02 |  | 9 to 13 | 9th to 13th Floor One Bedroom Unit Apartment (A1B2) Type-2 Plans | 1252-MKM-05Q-IDP-01-DWG-0138 | 2 OF 2 | 2017-01-18 | 2018-02-27 | 2018-03-13 | 14 | B | MKM | [45 empty] | 2018-02-27 | 2018-03-13 | 14 | B | Rev-0 | B | Approved |  |  | 1 5 | MKM
48 | SD-0009-05 |  | 9 to 13 | 9th to 13th Floor One Bedroom Unit Apartment (A1B2) Type-2 Power Plan | 1252-MKM-05Q-IDP-01-DWG-0139 | 1 OF 1 | 2017-01-18 | 2017-01-03 | 2017-01-10 | 7 | C | MKM | 2017-01-18 | 2017-02-13 | 26 | B | MKM | 2018-02-27 | 2018-03-13 | 14 | C | MKM | 2018-04-29 | 2018-05-05 | 6 | C | MKM | 2018-06-25 | 2018-06-28 | 3 | B | MKM | 2018-07-16 | 2018-07-22 | 6 | B | MKM | [20 empty] | 2018-07-16 | 2018-07-22 | 6 | B | Rev-5 | C | Resub..reqd | 2018-04-08 |  | 1 5 | MKM
49 | SD-0009-02 |  | 9 to 13 | 9th to 13th Floor 1 Bedroom Unit Apartment (A1B2) Type-2 Plans | 1252-MKM-05Q-IDP-01-DWG-0139 | 2 OF 2 | 2017-01-18 | 2018-02-27 | 2018-03-13 | 14 | B | MKM | [45 empty] | 2018-02-27 | 2018-03-13 | 14 | B | Rev-0 | C | Resub..reqd | 2018-04-08 |  | 1 5 | MKM
50 | SD-0009-02 |  | 9 to 13 | 9th to 13th Floor 1 Bedroom Unit Apartment (A1B2) Type-2 Elevations A & B | 1252-MKM-05Q-IDP-01-DWG-0140 | 1 OF 1 | 2017-01-18 | 2017-01-03 | 2017-01-10 | 7 | C | MKM | 2017-01-18 | 2017-02-13 | 26 | B | MKM | 2018-02-27 | 2018-03-13 | 14 | C | MKM | [35 empty] | 2018-02-27 | 2018-03-13 | 14 | C | Rev-2 | C | Resub..reqd | 2018-04-08 |  | 1 5 | MKM
51 | SD-0009-02 |  | 9 to 13 | 9th to 13th Floor 1 Bedroom Unit Apartment (A1B2) Type-2 Elevations C & D | 1252-MKM-05Q-IDP-01-DWG-0141 | 1 OF 1 | 2017-01-18 | 2017-01-03 | 2017-01-10 | 7 | C | MKM | 2017-01-18 | 2017-02-13 | 26 | B | MKM | 2018-02-27 | 2018-03-13 | 14 | C | MKM | [35 empty] | 2018-02-27 | 2018-03-13 | 14 | C | Rev-2 | C | Resub..reqd | 2018-04-08 |  | 1 5 | MKM
APARTMENT 1 BEDROOM UNIT TYPE (A1B3) | [62 empty] | 0 |  |  |  | 1 69
52 | SD-0016-03 |  |  | 14th to 17th Floor One Bedroom Unit Apartment (A1B3) Type-3 General Arrangement Plan | 1252-MKM-05Q-IDP-01-DWG-0142 | 1 OF 1 | 2017-01-23 | 2017-01-23 | 2017-02-12 | 20 | A | MKM | 2018-07-16 | 2018-07-22 | 6 | B | MKM | [40 empty] | 2018-07-16 | 2018-07-22 | 6 | B | Rev-1 | A/C | Resub..reqd | 2018-04-17 |  | 1 5 | MKM
53 | SD-0016-03 |  |  | 14th to 17th Floor One Bedroom Unit Apartment (A1B3) Type-3 Power Plan | 1252-MKM-05Q-IDP-01-DWG-0143 | 1 OF 1 | 2017-01-23 | 2017-01-23 | 2017-02-12 | 20 | A | MKM | 2018-04-22 | 2018-05-05 | 13 | C | MKM | 2018-06-25 | 2018-06-28 | 3 | B | MKM | 2018-07-16 | 2018-07-22 | 6 | B | MKM | [30 empty] | 2018-07-16 | 2018-07-22 | 6 | B | Rev-3 | A/C | Resub..reqd | 2018-04-17 |  | 1 5 | MKM
54 | SD-0016-00 |  |  | 14,15,16,17th Floor 1 Bedroom Unit Apartment (A1B3) Type-3 Elevation A & B | 1252-MKM-05Q-IDP-01-DWG-0144 | 1 OF 1 | 2017-01-23 | 2017-01-23 | 2017-02-12 | 20 | B | MKM | [45 empty] | 2017-01-23 | 2017-02-12 | 20 | B | Rev-0 | B/C | Resub..reqd | 2018-04-17 |  | 1 5 | MKM
55 | SD-0016-00 |  |  | 14,15,16,17th Floor 1 Bedroom Unit Apartment (A1B3) Type-3 Elevation C & D | 1252-MKM-05Q-IDP-01-DWG-0145 | 1 OF 1 | 2017-01-23 | 2017-01-23 | 2017-02-12 | 20 | B | MKM | [45 empty] | 2017-01-23 | 2017-02-12 | 20 | B | Rev-0 | B/C | Resub..reqd | 2018-04-17 |  | 1 5 | MKM
APARTMENT 2 BEDROOM UNIT TYPE (A2B1) | [62 empty] | 0 |  |  |  | 1 76
56 | SD-0006-04 |  | 8 | 8th Floor 2 Bedroom Unit Apartment (A2B1) General Arrangement Plans | 1252-MKM-05Q-IDP-01-DWG-0146 | 1 OF 2 | 2017-01-18 | 2016-12-22 | 2017-01-10 | 19 | C | MKM | 2017-01-18 | 2017-02-13 | 26 | B | MKM | 2018-07-23 | 2018-08-05 | 13 | B | MKM | [35 empty] | 2018-07-23 | 2018-08-05 | 13 | B | Rev-2 | B/C | Resub..reqd | 2018-04-17 |  | 1 5 | MKM
57 | SD-0006-04 |  | 8 | 8th Floor 2 Bedroom Unit Apartment (A2B1) General Arrangement Plans | 1252-MKM-05Q-IDP-01-DWG-0146 | 2 OF 2 |  | 2018-07-23 | 2018-08-05 | 13 | B | MKM | [45 empty] | 2018-07-23 | 2018-08-05 | 13 | B | Rev-0 | B/C | Resub..reqd | 2018-04-17 |  | 1 5 | MKM
58 | SD-0006-01 |  | 8 | 8th Floor 2 Bedroom Unit Apartment (A2B1) Plans | 1252-MKM-05Q-IDP-01-DWG-0147 | 1 OF 1 | 2017-01-18 | 2016-12-22 | 2017-01-10 | 19 | C | MKM | 2017-01-18 | 2017-02-13 | 26 | B | MKM | [40 empty] | 2017-01-18 | 2017-02-13 | 26 | B | Rev-1 | B/C | Resub..reqd | 2018-04-17 |  |  | MKM
59 | SD-0006-03 |  | 8 | 8th Floor 2 Bedroom Unit Apartment Type (A2B1) Plans | 1252-MKM-05Q-IDP-01-DWG-0148 | 1 OF 1 | 2017-01-18 | 2016-12-22 | 2017-01-10 | 19 | C | MKM | 2017-01-18 | 2017-02-13 | 26 | B | MKM | 2018-06-25 | 2018-06-28 | 3 | C | MKM | 2018-07-03 | 2018-07-09 | 6 | B | MKM | [30 empty] | 2018-07-03 | 2018-07-09 | 6 | B | Rev-3 | B/C | Resub..reqd | 2018-04-17 |  |  | MKM
60 | SD-0006-04 |  | 8 | 8th Floor 2 Bedroom Unit Apartment (A2B1) Power Plan | 1252-MKM-05Q-IDP-01-DWG-0149 | 1 OF 2 | 2017-01-18 | 2016-12-22 | 2017-01-10 | 19 | C | MKM | 2017-01-18 | 2017-02-13 | 26 | B | MKM | 2018-07-23 | 2018-08-05 | 13 | B | MKM | [35 empty] | 2018-07-23 | 2018-08-05 | 13 | B | Rev-2 | B/C | Resub..reqd | 2018-04-17 |  | 1 5 | MKM
61 | SD-0006-04 |  | 8 | 8th Floor 2 Bedroom Unit Apartment (A2B1) Power Plan | 1252-MKM-05Q-IDP-01-DWG-0149 | 2 OF 2 |  | 2018-07-23 | 2018-08-05 | 13 | B | MKM | [45 empty] | 2018-07-23 | 2018-08-05 | 13 | B | Rev-0 | B/C | Resub..reqd | 2018-04-17 |  | 1 5 | MKM
62 | SD-0006-01 |  | 8 | 8th Floor 2 Bedroom Unit Apartment (A2B1) Elevations A | 1252-MKM-05Q-IDP-01-DWG-0150 | 1 OF 1 | 2017-01-18 | 2016-12-22 | 2017-01-10 | 19 | C | MKM | 2017-01-18 | 2017-02-13 | 26 | B | MKM | [40 empty] | 2017-01-18 | 2017-02-13 | 26 | B | Rev-1 | B/C | Resub..reqd | 2018-04-17 |  | 1 5 | MKM
63 | SD-0006-01 |  | 8 | 8th Floor 2 Bedroom Unit Apartment (A2B1) Elevations B & C | 1252-MKM-05Q-IDP-01-DWG-0151 | 1 OF 2 | 2017-01-18 | 2016-12-22 | 2017-01-10 | 19 | C | MKM | 2017-01-18 | 2017-02-13 | 26 | B | MKM | [40 empty] | 2017-01-18 | 2017-02-13 | 26 | B | Rev-1 | B/C | Resub..reqd | 2018-04-17
64 | SD-0006-01 |  | 8 | 8th Floor 2 Bedroom Unit Apartment (A2B1) Elevations D & E | 1252-MKM-05Q-IDP-01-DWG-0151 | 2 OF 2 | 2017-01-18 | 2016-12-22 | 2017-01-10 | 19 | C | MKM | 2017-01-18 | 2017-02-13 | 26 | B | MKM | [40 empty] | 2017-01-18 | 2017-02-13 | 26 | B | Rev-1 | B/C | Resub..reqd | 2018-04-17 |  | 1 5 | MKM
APARTMENT 2 BEDROOM UNIT TYPE (A2B2) | [62 empty] | 0 |  |  |  | 1 83
65 | SD-0010-06 |  | 9 to 13 | 9th to 13th Floor 2 Bedroom Unit Apartment (A2B2) General Arrangement Plans | 1252-MKM-05Q-IDP-01-DWG-0152 | 1 OF 2 | 2017-01-18 | 2017-01-03 | 2017-01-11 | 8 | C | MKM | 2017-01-18 | 2017-02-14 | 27 | A | MKM | 2018-02-27 | 2018-03-08 | 9 | B | MKM | 2018-07-23 | 2018-08-05 | 13 | B | MKM | [30 empty] | 2018-07-23 | 2018-08-05 | 13 | B | Rev-3 | B | Approved |  |  | 1 5 | MKM
66 | SD-0010-06 |  | 9 to 13 | 9th to 13th Floor 2 Bedroom Unit Apartment (A2B2) General Arrangement Plans | 1252-MKM-05Q-IDP-01-DWG-0152 | 2 OF 2 | 2017-01-18 | 2018-02-27 | 2018-03-08 | 9 | B | MKM | 2018-07-23 | 2018-08-05 | 13 | B | MKM | [40 empty] | 2018-07-23 | 2018-08-05 | 13 | B | Rev-1 | B | Approved |  |  | 1 5 | MKM
67 | SD-0010-05 |  | 9 to 13 | 9th to 13th Floor 2 Bedroom Apartment Unit (A2B2) Reflected Ceiling Layout | 1252-MKM-05Q-IDP-01-DWG-0153 | 1 OF 3 | 2017-01-18 | 2017-01-03 | 2017-01-11 | 8 | C | MKM | 2017-01-18 | 2017-02-14 | 27 | B | MKM | 2018-02-27 | 2018-03-08 | 9 | B | MKM | 2018-04-24 | 2018-05-01 | 7 | B | MKM | 2018-06-25 | 2018-06-28 | 3 | C | MKM | 2018-07-03 | 2018-07-09 | 6 | B | MKM | [20 empty] | 2018-07-03 | 2018-07-09 | 6 | B | Rev-5 | B | Approved |  |  |  | MKM
68 | SD-0010-06 |  | 9 to 13 | 9th to 13th Floor 2 Bedroom Apartment Unit Type (A2B2) Power Plan | 1252-MKM-05Q-IDP-01-DWG-0153 | 2 OF 3 | 2017-01-18 | 2018-02-27 | 2018-03-08 | 9 | B | MKM | 2018-07-23 | 2018-08-05 | 13 | B | MKM | [40 empty] | 2018-07-23 | 2018-08-05 | 13 | B | Rev-1 | B | Approved |  |  |  | MKM
69 | SD-0010-06 |  | 9 to 13 | 9th to 13th Floor 2 Bedroom Apartment Unit Type (A2B2) Power Plan | 1252-MKM-05Q-IDP-01-DWG-0153 | 3 OF 3 |  | 2018-07-23 | 2018-08-05 | 13 | B | MKM | [45 empty] | 2018-07-23 | 2018-08-05 | 13 | B | Rev-0 | B | Approved |  |  |  | MKM
70 | SD-0010-01 |  | 9 to 13 | Apartment 2 Bedroom Apartment Type (A2B2) Plans | 1252-MKM-05Q-IDP-01-DWG-0154 | 2 OF 2 | 2017-01-18 | 2017-01-03 | 2017-01-11 | 8 | C | MKM | 2017-01-18 | 2017-02-14 | 27 | A | MKM | [40 empty] | 2017-01-18 | 2017-02-14 | 27 | A | Rev-1 | A | Approved |  |  | 1 5 | MKM
71 | SD-0010-01 |  | 9 to 13 | Apartment 2 Bedroom Apartment Type (A2B2) Elevations A & A1 | 1252-MKM-05Q-IDP-01-DWG-0155 | 1 OF 1 | 2017-01-18 | 2017-01-03 | 2017-01-11 | 8 | C | MKM | 2017-01-18 | 2017-02-14 | 27 | A | MKM | [40 empty] | 2017-01-18 | 2017-02-14 | 27 | A | Rev-1 | A | Approved |  |  | 1 5 | MKM
72 | SD-0010-02 |  | 9 to 13 | Apartment 2 Bedroom Apartment Type (A2B2) Elevations B & C | 1252-MKM-05Q-IDP-01-DWG-0156 | 1 OF 1 | 2017-01-18 | 2017-01-03 | 2017-01-11 | 8 | C | MKM | 2017-01-18 | 2017-02-14 | 27 | B | MKM | 2018-02-27 | 2018-03-08 | 9 | B | MKM | [35 empty] | 2018-02-27 | 2018-03-08 | 9 | B | Rev-2 | B | Approved |  |  | 1 5 | MKM
73 | SD-0010-02 |  | 9 to 13 | Apartment 2 Bedroom Apartment Type (A2B2) Elevations D | 1252-MKM-05Q-IDP-01-DWG-0157 | 1 OF 2 | 2017-01-18 | 2017-01-03 | 2017-01-11 | 8 | C | MKM | 2017-01-18 | 2017-02-14 | 27 | B | MKM | 2018-02-27 | 2018-03-08 | 9 | C | MKM | [35 empty] | 2018-02-27 | 2018-03-08 | 9 | C | Rev-2 | C | Resub..reqd | 2018-04-08 |  | 1 5 | MKM
74 | SD-0010-02 |  | 9 to 13 | Apartment 2 Bedroom Apartment Type (A2B2) Elevations D | 1252-MKM-05Q-IDP-01-DWG-0157 | 2 OF 2 | 2017-01-18 | 2017-01-03 | 2017-01-11 | 8 | C | MKM | 2017-01-18 | 2017-02-14 | 27 | A | MKM | 2018-02-27 | 2018-03-08 | 9 | C | MKM | [35 empty] | 2018-02-27 | 2018-03-08 | 9 | C | Rev-2 | C | Resub..reqd | 2018-04-08 |  | 1 5 | MKM
APARTMENT 2 BEDROOM UNIT TYPE (A2B3) | [62 empty] | 0 |  |  |  | 1 90
75 | SD-0017-04 |  |  | 14th to 17th Floor 2 Bedroom Unit Apartment (A2B3) General Arragement Plans | 1252-MKM-05Q-IDP-01-DWG-0158 | 1 OF 2 | 2017-01-29 | 2017-01-29 | 2017-02-13 | 15 | A | MKM | 2018-07-23 | 2018-08-05 | 13 | B | MKM | [40 empty] | 2018-07-23 | 2018-08-05 | 13 | B | Rev-1 | A/C | Resub..reqd | 2018-04-17 |  | 1 5 | MKM
76 | SD-0017-04 |  |  | 14th to 17th Floor 2 Bedroom Unit Apartment (A2B3) General Arragement Plans | 1252-MKM-05Q-IDP-01-DWG-0158 | 2 OF 2 |  | 2018-07-23 | 2018-08-05 | 13 | B | MKM | [45 empty] | 2018-07-23 | 2018-08-05 | 13 | B | Rev-0 | A/C | Resub..reqd | 2018-04-17 |  | 1 5 | MKM
77 | SD-0017-00 |  |  | Apartment 2 Bedroom unit A Type (A2B3)_Floor finish layout | 1252-MKM-05Q-IDP-01-DWG-0159 | 1 OF 1 | 2017-01-29 | 2017-01-29 | 2017-02-13 | 15 | B | MKM | [45 empty] | 2017-01-29 | 2017-02-13 | 15 | B | Rev-0 | B/C | Resub..reqd | 2018-04-17 |  |  | MKM
78 | SD-0017-03 |  |  | 14,15,16th Floor 2 Bedroom Unit Apartment (A2B3) Type-3 Reflected Ceiling Plan | 1252-MKM-05Q-IDP-01-DWG-0160 | 1 OF 2 | 2017-01-29 | 2017-01-29 | 2017-02-13 | 15 | A | MKM | 2018-04-30 | 2018-05-05 | 5 | B | MKM | 2018-06-25 | 2018-06-28 | 3 | C | MKM | 2018-07-03 | 2018-07-09 | 6 | B | MKM | [30 empty] | 2018-07-03 | 2018-07-09 | 6 | B | Rev-3 | A/C | Resub..reqd | 2018-04-17 |  | 1 5 | MKM
79 | SD-0017-03 |  |  | 17th Floor 2 Bedroom Unit Apartment (A2B3) Type-3 Reflected Ceiling Plan | 1252-MKM-05Q-IDP-01-DWG-0160 | 2 OF 2 | 2017-01-29 | 2018-04-30 | 2018-05-05 | 5 | B | MKM | 2018-06-25 | 2018-06-28 | 3 | C | MKM | 2018-07-03 | 2018-07-09 | 6 | B | MKM | [35 empty] | 2018-07-03 | 2018-07-09 | 6 | B | Rev-2 | A/C | Resub..reqd | 2018-04-17 |  | 1 5 | MKM
80 | SD-0017-04 |  |  | 14th to 17th Floor 2 Bedroom Unit (A2B3) Power Plan | 1252-MKM-05Q-IDP-01-DWG-0161 | 1 OF 2 | 2017-01-29 | 2017-01-29 | 2017-02-13 | 15 | A | MKM | 2018-07-23 | 2018-08-05 | 13 | B | MKM | [40 empty] | 2018-07-23 | 2018-08-05 | 13 | B | Rev-1 | A/C | Resub..reqd | 2018-04-17 |  | 1 5 | MKM
81 | SD-0017-04 |  |  | 14th to 17th Floor 2 Bedroom Unit (A2B3) Power Plan | 1252-MKM-05Q-IDP-01-DWG-0161 | 2 OF 2 |  | 2018-07-23 | 2018-08-05 | 13 | B | MKM | [45 empty] | 2018-07-23 | 2018-08-05 | 13 | B | Rev-0 | A/C | Resub..reqd | 2018-04-17 |  | 1 5 | MKM
82 | SD-0017-00 |  |  | Apartment 2 Bedroom unit Type (A2B3)_Elevations | 1252-MKM-05Q-IDP-01-DWG-0162 | 1 OF 1 | 2017-01-29 | 2017-01-29 | 2017-02-13 | 15 | A | MKM | [45 empty] | 2017-01-29 | 2017-02-13 | 15 | A | Rev-0 | A/C | Resub..reqd | 2018-04-17 |  | 1 5 | MKM
83 | SD-0017-00 |  |  | Apartment 2 Bedroom unit Type (A2B3)_Elevations | 1252-MKM-05Q-IDP-01-DWG-0163 | 1 of 2 | 2017-01-29 | 2017-01-29 | 2017-02-13 | 15 | A | MKM | [45 empty] | 2017-01-29 | 2017-02-13 | 15 | A | Rev-0 | A/C | Resub..reqd | 2018-04-17 |  | 1 5 | MKM
84 | SD-0017-00 |  |  | Apartment 2 Bedroom unit Type (A2B3)_Elevations | 1252-MKM-05Q-IDP-01-DWG-0163 | 2 of 2 | 2017-01-29 | 2017-01-29 | 2017-02-13 | 15 | A | MKM | [45 empty] | 2017-01-29 | 2017-02-13 | 15 | A | Rev-0 | A/C | Resub..reqd | 2018-04-17 |  | 1 5 | MKM
APARTMENT 3 BEDROOM UNIT TYPE (A3B1) | [62 empty] | 0 |  |  |  | 1 97
85 | SD-0007-05 |  | 8 | 8th Floor 3 Bedroom Unit Apartment (A3B3) General Arrangement Plans | 1252-MKM-05Q-IDP-01-DWG-0164 | 1 of 2 | 2017-01-17 | 2016-12-22 | 2017-01-10 | 19 | C | MKM | 2017-01-17 | 2017-01-19 | 2 | B | MKM | 2018-08-02 | 2018-08-12 | 10 | B | MKM | [35 empty] | 2018-08-02 | 2018-08-12 | 10 | B | Rev-2 | B/C | Resub..reqd | 2018-04-17 |  | 1 5 | MKM
86 | SD-0007-05 |  | 8 | 8th Floor 3 Bedroom Unit Apartment (A3B3) General Arrangement Plans | 1252-MKM-05Q-IDP-01-DWG-0164 | 2 of 2 |  | 2018-08-02 | 2018-08-12 | 10 | B | MKM | [45 empty] | 2018-08-02 | 2018-08-12 | 10 | B | Rev-0 | B/C | Resub..reqd | 2018-04-17 |  | 1 5 | MKM
87 | SD-0007-01 |  | 8 | Apartment 3 Bedroom unit A Type (A3B1)_(Type-1)_Plans | 1252-MKM-05Q-IDP-01-DWG-0165 | 1 OF 1 | 2017-01-17 | 2016-12-22 | 2017-01-10 | 19 | C | MKM | 2017-01-17 | 2017-01-19 | 2 | B | MKM | [40 empty] | 2017-01-17 | 2017-01-19 | 2 | B | Rev-1 | B/C | Resub..reqd | 2018-04-17 |  |  | MKM
88 | SD-0007-05 |  | 8 | 8th Floor 3 Bedroom Unit Apartment (A3B3) Power Plan | 1252-MKM-05Q-IDP-01-DWG-0166 | 1 of 3 | 2017-01-17 | 2016-12-22 | 2017-01-10 | 19 | C | MKM | 2017-01-17 | 2017-01-19 | 2 | B | MKM | 2018-06-25 | 2018-06-28 | 3 | C | MKM | 2018-07-03 | 2018-07-09 | 6 | C | MKM | 2018-07-12 | 2018-07-17 | 5 | B | MKM | 2018-08-02 | 2018-08-12 | 10 |  | Superseded as previously approved with Rev-04 (As per Hassan) | [20 empty] | 2018-08-02 | 2018-08-12 | 10 | B | Rev-4 | B/C | Resub..reqd | 2018-04-17 |  |  | Superseded as previously approved with Rev-04 (As per Hassan)
89 | SD-0007-06 |  | 8 | 8th Floor 3 Bedroom Unit Apartment (A3B1) Power Plan | 1252-MKM-05Q-IDP-01-DWG-0166 | 2 of 3 |  | 2018-08-02 | 2018-08-12 | 10 | B | MKM | 2018-08-28 | 2018-09-05 | 8 | B | MKM | [40 empty] | 2018-08-28 | 2018-09-05 | 8 | B | Rev-1 | B/C | Resub..reqd | 2018-04-17 |  |  | MKM
90 | SD-0007-06 |  | 8 | 8th Floor 3 Bedroom Unit Apartment (A3B1) Power Plan | 1252-MKM-05Q-IDP-01-DWG-0166 | 3 of 3 |  | 2018-08-28 | 2018-09-05 | 8 | B | MKM | [45 empty] | 2018-08-28 | 2018-09-05 | 8 | B | Rev-0 | B/C | Resub..reqd | 2018-04-17 |  |  | MKM
91 | SD-0007-01 |  | 8 | 8th Floor 3 Bedroom Unit Apartment (A3B1) Type-1 Plans | 1252-MKM-05Q-IDP-01-DWG-0167 | 1 OF 1 | 2017-01-17 | 2016-12-22 | 2017-01-10 | 19 | C | MKM | 2017-01-17 | 2017-01-19 | 2 | B | MKM | [40 empty] | 2017-01-17 | 2017-01-19 | 2 | B | Rev-1 | B/C | Resub..reqd | 2018-04-17 |  | 1 5 | MKM
92 | SD-0007-01 |  | 8 | 8th Floor 3 Bedroom Unit Apartment (A3B1) Elevations A | 1252-MKM-05Q-IDP-01-DWG-0168 | 1 OF 1 | 2017-01-17 | 2016-12-22 | 2017-01-10 | 19 | C | MKM | 2017-01-17 | 2017-01-19 | 2 | B | MKM | [40 empty] | 2017-01-17 | 2017-01-19 | 2 | B | Rev-1 | B/C | Resub..reqd | 2018-04-17 |  | 1 5 | MKM
93 | SD-0007-01 |  | 8 | 8th Floor 3 Bedroom Unit Apartment (A3B1) Elevations B & C | 1252-MKM-05Q-IDP-01-DWG-0169 | 1 OF 2 | 2017-01-17 | 2016-12-22 | 2017-01-10 | 19 | C | MKM | 2017-01-17 | 2017-01-19 | 2 | B | MKM | [40 empty] | 2017-01-17 | 2017-01-19 | 2 | B | Rev-1 | B/C | Resub..reqd | 2018-04-17
94 | SD-0007-01 |  | 8 | 8th Floor 3 Bedroom Unit Apartment (A3B1) Elevations D & E | 1252-MKM-05Q-IDP-01-DWG-0169 | 2 OF 2 | 2017-01-17 | 2016-12-22 | 2017-01-10 | 19 | C | MKM | 2017-01-17 | 2017-01-19 | 2 | B | MKM | [40 empty] | 2017-01-17 | 2017-01-19 | 2 | B | Rev-1 | B/C | Resub..reqd | 2018-04-17
APARTMENT 3 BEDROOM UNIT TYPE (A3B2) | [66 empty] | 1 104
95 | SD-0012-07 |  | 9 to 13 | 9th to 13th Floor Three Bedroom Unit Apartment (A3B2) General Arrangement Plans | 1252-MKM-05Q-IDP-01-DWG-0170 | 1 OF 2 | 2017-01-18 | 2017-01-03 | 2017-01-12 | 9 | C | MKM | 2017-01-18 | 2017-02-21 | 34 | A | MKM | 2018-01-03 |  | 600 | Not Reviewed | MKM | 2018-08-02 | 2018-08-12 | 10 | B | MKM | [30 empty] | 2018-08-02 | 2018-08-12 | 10 | B | Rev-3 | B | Approved |  |  | 1 5 | MKM
96 | SD-0012-07 |  | 9 to 13 | 9th to 13th Floor Three Bedroom Unit Apartment (A3B2) General Arrangement Plans | 1252-MKM-05Q-IDP-01-DWG-0170 | 2 OF 2 |  | 2018-08-02 | 2018-08-12 | 10 | B | MKM | [45 empty] | 2018-08-02 | 2018-08-12 | 10 | B | Rev-0 | B | Approved |  |  | 1 5 | MKM
97 | SD-0012-02 |  | 9 to 13 | Apartment 3 Bedroom Unit Type (A3B2) Plans | 1252-MKM-05Q-IDP-01-DWG-0171 | 1 OF 1 | 2017-01-18 | 2017-01-03 | 2017-01-12 | 9 | C | MKM | 2017-01-18 | 2017-02-21 | 34 | B | MKM | 2018-01-03 |  | 600 | Not Reviewed | MKM | [35 empty] | 2018-01-03 | 2017-02-21 | 600 | Not Reviewed | Rev-2 | B | Approved |  |  |  | MKM
98 | SD-0012-06 |  | 9 to 13 | 9th to 13th Floor 3 Bedroom Unit Apartment (Type-2) Reflected Ceiling Plan | 1252-MKM-05Q-IDP-01-DWG-0172 | 1 OF 3 | 2017-01-18 | 2017-01-03 | 2017-01-12 | 9 | C | MKM | 2017-01-18 | 2017-02-21 | 34 | B | MKM | 2018-06-25 | 2018-06-28 | 3 | C | MKM | 2018-07-03 | 2018-07-09 | 6 | B | MKM | [30 empty] | 2018-07-03 | 2018-07-09 | 6 | B | Rev-3 | B | Approved |  |  | 1 5 | MKM
99 | SD-0012-07 |  | 9 to 13 | 9th to 13th Floor Three Bedroom Unit Apartment (A3B2) Power Plan | 1252-MKM-05Q-IDP-01-DWG-0172 | 2 OF 3 |  | 2018-08-02 | 2018-08-12 | 10 | B | MKM | [45 empty] | 2018-08-02 | 2018-08-12 | 10 | B | Rev-0 | B | Approved |  |  | 1 5 | MKM
100 | SD-0012-07 |  | 9 to 13 | 9th to 13th Floor Three Bedroom Unit Apartment (A3B2) Power Plan | 1252-MKM-05Q-IDP-01-DWG-0172 | 3 OF 3 |  | 2018-08-02 | 2018-08-12 | 10 | B | MKM | [45 empty] | 2018-08-02 | 2018-08-12 | 10 | B | Rev-0 | B | Approved |  |  | 1 5 | MKM
101 | SD-0012-04 |  | 9 to 13 | Apartment 3 Bedroom Unit Type (A3B2) Plans | 1252-MKM-05Q-IDP-01-DWG-0173 | 1 OF 1 | 2017-01-18 | 2017-01-03 | 2017-01-12 | 9 | C | MKM | 2017-01-18 | 2017-02-21 | 34 | B | MKM | 2018-01-04 | 2018-01-07 | 3 | C | MKM | 2018-01-16 | 2018-01-21 | 5 | B | MKM | [30 empty] | 2018-01-16 | 2018-01-21 | 5 | B | Rev-3 | B | Approved |  |  | 1 5 | MKM
102 | SD-0012-04 |  | 9 to 13 | Apartment 3 Bedroom unit Type (A3B2)_Elevation A | 1252-MKM-05Q-IDP-01-DWG-0174 | 1 OF 1 | 2017-01-18 | 2017-01-03 | 2017-01-12 | 9 | C | MKM | 2017-01-18 | 2017-02-21 | 34 | B | MKM | 2018-01-08 | 2018-01-09 | 1 | C | MKM | 2018-01-16 | 2018-01-21 | 5 | B | MKM | [30 empty] | 2018-01-16 | 2018-01-21 | 5 | B | Rev-3 | B | Approved |  |  | 1 5 | MKM
103 | SD-0012-04 |  | 9 to 13 | Apartment 3 Bedroom unit Type (A3B2)_Elevations B & C | 1252-MKM-05Q-IDP-01-DWG-0175 | 1 OF 3 | 2017-01-18 | 2017-01-03 | 2017-01-12 | 9 | C | MKM | 2017-01-18 | 2017-02-21 | 34 | B | MKM | 2018-01-08 | 2018-01-09 | 1 | C | MKM | 2018-01-16 | 2018-01-21 | 5 | B | MKM | [30 empty] | 2018-01-16 | 2018-01-21 | 5 | B | Rev-3 | B | Approved |  |  | 1 5 | MKM
104 | SD-0012-04 |  | 9 to 13 | Apartment 3 Bedroom unit Type (A3B2)_Elevations D & E | 1252-MKM-05Q-IDP-01-DWG-0175 | 2 OF 3 | 2017-01-18 | 2017-01-03 | 2017-01-12 | 9 | C | MKM | 2017-01-18 | 2017-02-21 | 34 | B | MKM | 2018-01-08 | 2018-01-09 | 1 | C | MKM | 2018-01-16 | 2018-01-21 | 5 | B | MKM | [30 empty] | 2018-01-16 | 2018-01-21 | 5 | B | Rev-3 | B | Approved |  |  | 1 5 | MKM
105 | SD-0012-04 |  | 9 to 13 | Apartment 3 Bedroom unit Type (A3B2)_Elevations D & E | 1252-MKM-05Q-IDP-01-DWG-0175 | 3 OF 3 | 2017-01-18 | 2018-01-08 | 2018-01-09 | 1 | C | MKM | 2018-01-16 | 2018-01-21 | 5 | B | MKM | [40 empty] | 2018-01-16 | 2018-01-21 | 5 | B | Rev-1 | B | Approved |  |  | 1 5 | MKM
APARTMENT 3 BEDROOM UNIT TYPE (A3B3) | [62 empty] | 0 |  |  |  | 1 111
106 | SD-0018-04 |  |  | 14th, 15th & 17th Floor Three Bedroom Unit Apartment (A3B3) General Arrangement Plans | 1252-MKM-05Q-IDP-01-DWG-0176 | 1 OF 2 | 2017-01-31 | 2017-02-01 | 2017-02-21 | 20 | B | MKM | 2018-08-02 | 2018-08-12 | 10 | B | MKM | [40 empty] | 2018-08-02 | 2018-08-12 | 10 | B | Rev-1 | B/C | Resub..reqd | 2018-04-17 |  | 1 5 | MKM
107 | SD-0018-04 |  |  | 14th, 15th & 17th Floor Three Bedroom Unit Apartment (A3B3) General Arrangement Plans | 1252-MKM-05Q-IDP-01-DWG-0176 | 2 OF 2 |  | 2018-08-02 | 2018-08-12 | 10 | B | MKM | [45 empty] | 2018-08-02 | 2018-08-12 | 10 | B | Rev-0 | B/C | Resub..reqd | 2018-04-17 |  | 1 5 | MKM
108 | SD-0018-00 |  |  | 14th, 15th & 17th Floor 3 Bedroom Unit Apartment (A3B3) Type-3 Plans | 1252-MKM-05Q-IDP-01-DWG-0177 | 1 OF 1 | 2017-01-31 | 2017-02-01 | 2017-02-21 | 20 | B | MKM | [45 empty] | 2017-02-01 | 2017-02-21 | 20 | B | Rev-0 | B/C | Resub..reqd | 2018-04-17 |  |  | MKM
109 | SD-0018-04 |  |  | 14th, 15th & 17th Floor Three Bedroom Unit Apartment (A3B3) Power Plan | 1252-MKM-05Q-IDP-01-DWG-0178 | 1 OF 2 | 2017-01-31 | 2017-02-01 | 2017-02-21 | 20 | B | MKM | 2018-04-29 | 2018-05-05 | 6 | C | MKM | 2018-06-25 | 2018-06-28 | 3 | C | MKM | 2018-07-03 | 2018-07-09 | 6 | B | MKM | 2018-08-02 | 2018-08-12 | 10 | B | MKM | [25 empty] | 2018-08-02 | 2018-08-12 | 10 | B | Rev-4 | B/C | Resub..reqd | 2018-04-17 |  | 1 5 | MKM
110 | SD-0018-04 |  |  | 14th, 15th & 17th Floor Three Bedroom Unit Apartment (A3B3) Power Plan | 1252-MKM-05Q-IDP-01-DWG-0178 | 2 OF 2 |  | 2018-08-02 | 2018-08-12 | 10 | B | MKM | [45 empty] | 2018-08-02 | 2018-08-12 | 10 | B | Rev-0 | B/C | Resub..reqd | 2018-04-17 |  | 1 5 | MKM
111 | SD-0018-00 |  |  | 14th, 15ht & 17th Floor 3 Bedroom Unit Apartment (A3B3) Type-3 Plans | 1252-MKM-05Q-IDP-01-DWG-0179 | 1 OF 1 | 2017-01-31 | 2017-02-01 | 2017-02-21 | 20 | B | MKM | [45 empty] | 2017-02-01 | 2017-02-21 | 20 | B | Rev-0 | B/C | Resub..reqd | 2018-04-17 |  | 1 5 | MKM
112 | SD-0018-00 |  |  | 14th, 15tjh & 17th Floor 3 Bedroom Unit Apartment (A3B3) Type-3 Elevations | 1252-MKM-05Q-IDP-01-DWG-0180 | 1 OF 1 | 2017-01-31 | 2017-02-01 | 2017-02-21 | 20 | B | MKM | [45 empty] | 2017-02-01 | 2017-02-21 | 20 | B | Rev-0 | B/C | Resub..reqd | 2018-04-17 |  | 1 5 | MKM
113 | SD-0018-00 |  |  | 14th, 15tjh & 17th Floor 3 Bedroom Unit Apartment (A3B3) Type-3 Elevations | 1252-MKM-05Q-IDP-01-DWG-0181 | 1 OF 2 | 2017-01-31 | 2017-02-01 | 2017-02-21 | 20 | B | MKM | [45 empty] | 2017-02-01 | 2017-02-21 | 20 | B | Rev-0 | B/C | Resub..reqd | 2018-04-17 |  | 1 5 | MKM
114 | SD-0018-00 |  |  | 14th, 15th & 17th Floor 3 Bedroom Unit Apartment (A3B3) Type-3 Elevations | 1252-MKM-05Q-IDP-01-DWG-0181 | 2 OF 2 | 2017-01-31 | 2017-02-01 | 2017-02-21 | 20 | B | MKM | [45 empty] | 2017-02-01 | 2017-02-21 | 20 | B | Rev-0 | B/C | Resub..reqd | 2018-04-17 |  | 1 5 | MKM
GUEST ROOMS JUNIOR SUITE UNIT TYPE (GJS1) & (GJS1A) | [62 empty] | 0 |  |  |  | 1 118
115 | SD-0030-03 | ARK-0009-00 | 19-21 | 19th to 21st Floor Junior Suite (Type-1) Furniture Layout | 1252-MKM-05Q-IDP-01-DWG-0182 | 1 OF 2 | 2017-02-02 | 2017-02-01 | 2017-02-21 | 20 | B | MKM | 2018-03-13 | 2018-03-28 | 15 | C | MKM | 2018-06-05 | 2018-06-13 | 8 | B | MKM | 2018-07-05 | 2018-07-11 | 6 | B | MKM | 2018-09-25 | 2018-10-07 | 12 | B | MKM | [25 empty] | 2018-09-25 | 2018-10-07 | 12 | B | Rev-4 | C | Resub..reqd | 2018-04-09 |  | 1 5 | MKM
116 | SD-0030-02 | ARK-0009-00 | 19-21 | 19th to 21st Floor Junior Suite (Type-1) Reflected Ceiling Plan | 1252-MKM-05Q-IDP-01-DWG-0182 | 2 OF 2 | 2017-02-02 | 2018-03-13 | 2018-03-28 | 15 | C | MKM | 2018-06-05 | 2018-06-13 | 8 | B | MKM | 2018-09-25 | 2018-10-07 | 12 | B | MKM | [35 empty] | 2018-09-25 | 2018-10-07 | 12 | B | Rev-2 | C | Resub..reqd | 2018-04-09 |  | 1 5 | MKM
117 | SD-0030-04 | ARK-0009-00 | 19-21 | 19th to 21st Floor Junior Suite (Type-1) Power Layout | 1252-MKM-05Q-IDP-01-DWG-0183 | 1 OF 2 | 2017-02-02 | 2017-02-01 | 2017-02-21 | 20 | B | MKM | 2018-03-13 | 2018-03-28 | 15 | C | MKM | 2018-06-05 | 2018-06-13 | 8 | B | MKM | 2018-09-25 | 2018-10-07 | 12 | B | MKM | [30 empty] | 2018-09-25 | 2018-10-07 | 12 | B | Rev-3 | C | Resub..reqd | 2018-04-09 |  | 1 5 | MKM
118 | SD-0030-01 |  |  | Guest rooms Junior Suite unit A Type (GJS1) & (GJS1A) _Reflected ceiling plan | 1252-MKM-05Q-IDP-01-DWG-0183 | 2 OF 2 | 2017-02-02 | 2018-03-13 | 2018-03-28 | 15 | C | MKM |  |  |  | X | [41 empty] | 2018-03-13 | 2018-03-28 | 15 | X | Rev-0 | C | Resub..reqd | 2018-04-09 |  | 1 5 | MKM
119 | SD-0030-01 |  | 19-23 | 19th to 23rd Floor Guest Room Junior Suite Type-1 Elevations A,B & C | 1252-MKM-05Q-IDP-01-DWG-0184 | 1 OF 1 | 2017-02-02 | 2017-02-01 | 2017-02-21 | 20 | B | MKM | 2018-03-13 | 2018-03-28 | 15 | C | MKM | [40 empty] | 2018-03-13 | 2018-03-28 | 15 | C | Rev-1 | C | Resub..reqd | 2018-04-09 |  | 1 5 | MKM
120 | SD-0030-03 | ARK-0009-00 | 22-23 | 22nd to 23rd Floor Junior Suite (Type-1A) Furniture Layout | 1252-MKM-05Q-IDP-01-DWG-0185 | 1 OF 3 | 2017-02-02 | 2018-06-05 | 2018-06-13 | 8 | B | MKM | 2018-07-05 | 2018-07-11 | 6 | B | MKM | 2018-09-25 | 2018-10-07 | 12 | B | MKM | [35 empty] | 2018-09-25 | 2018-10-07 | 12 | B | Rev-2 | C | Resub..reqd | 2018-04-09 |  | 1 5 | MKM
121 | SD-0030-02 | ARK-0009-00 | 22-23 | 22nd to 23rd Floor Junior Suite (Type-1A) Reflected Ceiling Plan | 1252-MKM-05Q-IDP-01-DWG-0185 | 2 OF 3 | 2017-02-02 | 2018-06-05 | 2018-06-13 | 8 | B | MKM | 2018-09-25 | 2018-10-07 | 12 | B | MKM | [40 empty] | 2018-09-25 | 2018-10-07 | 12 | B | Rev-1 | C | Resub..reqd | 2018-04-09 |  | 1 5 | MKM
122 | SD-0030-04 | ARK-0009-00 |  | 22nd to 23rd Floor Junior Suite (Type-1A) Power Layout | 1252-MKM-05Q-IDP-01-DWG-0185 | 3 OF 3 | 2017-02-02 | 2018-06-05 | 2018-06-13 | 8 | B | MKM | 2018-09-25 | 2018-10-07 | 12 | B | MKM | [40 empty] | 2018-09-25 | 2018-10-07 | 12 | B | Rev-1 | C | Resub..reqd | 2018-04-09 |  | 1 5 | MKM
GUEST ROOMS 1 BEDROOM SUITE A TYPE (G1BA) | [62 empty] | 0 |  |  |  | 1 125
123 | SD-0035-03 |  | 19th - 21st | Junior Suite Type-2 1 Bedroom Suite-A 19th to 21st Floor Furniture Plan | 1252-MKM-05Q-IDP-01-DWG-0186 | 1 OF 3 | 2017-02-06 | 2017-02-06 | 2017-02-21 | 15 | B | MKM | 2018-03-21 | 2018-03-26 | 5 | B | MKM | 2018-06-05 | 2018-06-13 | 8 | B | MKM | [35 empty] | 2018-06-05 | 2018-06-13 | 8 | B | Rev-2 | B | Approved |  |  | 1 5 | MKM
124 | SD-0035-03 |  | 22nd - 23rd | Junior Suite Type-2 1 Bedroom Suite-A 22nd & 23rd Floor Furniture Plan | 1252-MKM-05Q-IDP-01-DWG-0186 | 2 OF 3 | 2017-02-06 | 2018-03-21 | 2018-03-26 | 5 | C | MKM | 2018-06-05 | 2018-06-13 | 8 | B | MKM | [40 empty] | 2018-06-05 | 2018-06-13 | 8 | B | Rev-1 | C | Resub..reqd | 2018-04-09 |  | 1 5 | MKM
125 | SD-0035-03 |  | 19th - 23rd | Junior Suite Type-2 1 Bedroom Suite-A 19th - 23rd Reflected Ceiling Plan | 1252-MKM-05Q-IDP-01-DWG-0186 | 3 OF 3 | 2017-02-06 | 2018-03-21 | 2018-03-26 | 5 | OD | MKM | 2018-06-05 | 2018-06-13 | 8 | B | MKM | [40 empty] | 2018-06-05 | 2018-06-13 | 8 | B | Rev-1 | B | Approved |  |  | 1 5 | MKM
126 | SD-0035-03 |  | 19th - 21st | Junior Suite Type-2 1 Bedroom Suite-A 19th to 21st Floor Finish Plan | 1252-MKM-05Q-IDP-01-DWG-0187 | 1 OF 2 | 2017-02-06 | 2017-02-06 | 2017-02-21 | 15 | B | MKM | 2018-03-21 | 2018-03-26 | 5 | B | MKM | 2018-06-05 | 2018-06-13 | 8 | B | MKM | [35 empty] | 2018-06-05 | 2018-06-13 | 8 | B | Rev-2 | B | Approved |  |  | 1 5 | MKM
127 | SD-0035-03 |  | 19th - 23rd | Junior Suite Type-2 1 Bedroom Suite-A 19th to 23rd Power Layout Plan | 1252-MKM-05Q-IDP-01-DWG-0187 | 2 OF 2 | 2017-02-06 | 2018-03-21 | 2018-03-26 | 5 | C | MKM | 2018-06-05 | 2018-06-13 | 8 | B | MKM | [40 empty] | 2018-06-05 | 2018-06-13 | 8 | B | Rev-1 | C | Resub..reqd | 2018-04-09 |  | 1 5 | MKM
128 | SD-0035-02 |  | 19th - 21st | 19th to 21st Floor 1 Bedroom Suite-A Elevations A, B, C, D, E | 1252-MKM-05Q-IDP-01-DWG-0188 | 1 OF 1 | 2017-02-06 | 2017-02-06 | 2017-02-21 | 15 | C | MKM | 2017-03-09 | 2017-03-13 | 4 | A | MKM | 2018-03-21 | 2018-03-26 | 5 | C | MKM | [35 empty] | 2018-03-21 | 2018-03-26 | 5 | C | Rev-2 | C | Resub..reqd | 2018-04-09 |  | 1 5 | MKM
129 | SD-0073-02 |  | 19th - 23rd | 19th to 23rd Floor Guest Room 1 Bedroom Suite -A Type (GIBA) DB Cabinet Details | 1252-MKM-05Q-IDP-01-DWG-0380 | 1 OF 1 | 2017-02-06 | 2017-12-20 | 2018-01-17 | 28 | C | MKM | 2018-03-18 | 2018-03-20 | 2 | C | MKM | 2018-03-26 | 2018-05-01 | 36 | B | MKM | [35 empty] | 2018-03-26 | 2018-05-01 | 36 | B | Rev-2 | P |  |  |  | 1 5 | MKM
GUEST ROOMS 1 BEDROOM SUITE B TYPE (G1BB) | [62 empty] | 0 |  |  |  | 1 132
130 | SD-0036-02 |  | 19th - 23rd | Junior Suite Type-3 1 Bedroom Suite - B 19th to 23rd Floor Furniture Plan | 1252-MKM-05Q-IDP-01-DWG-0190 | 1 OF 2 | 2017-02-06 | 2017-02-09 | 2017-02-21 | 12 | B | MKM | 2018-03-13 | 2018-03-28 | 15 | C | MKM | 2018-06-05 | 2018-06-13 | 8 | B | MKM | [35 empty] | 2018-06-05 | 2018-06-13 | 8 | B | Rev-2 | C | Resub..reqd | 2018-04-09 |  | 1 5 | MKM
131 | SD-0036-02 |  | 19th - 23rd | Junior Suite Type-3 1 Bedroom Suite - B 19th to 23rd Floor Finishes Plan | 1252-MKM-05Q-IDP-01-DWG-0190 | 2 OF 2 | 2017-02-06 | 2018-03-13 | 2018-03-28 | 15 | C | MKM | 2018-06-05 | 2018-06-13 | 8 | B | MKM | [40 empty] | 2018-06-05 | 2018-06-13 | 8 | B | Rev-1 | C | Resub..reqd | 2018-04-09 |  | 1 5 | MKM
132 | SD-0036-02 |  | 19th - 23rd | Junior Suite Type-3 1 Bedroom Suite - B 19th to 23rd Floor Reflected Ceiling plan | 1252-MKM-05Q-IDP-01-DWG-0191 | 1 OF 2 | 2017-02-06 | 2017-02-09 | 2017-02-21 | 12 | B | MKM | 2018-03-13 | 2018-03-28 | 15 | C | MKM | 2018-06-05 | 2018-06-13 | 8 | B | MKM | [35 empty] | 2018-06-05 | 2018-06-13 | 8 | B | Rev-2 | C | Resub..reqd | 2018-04-09 |  | 1 5 | MKM
133 | SD-0036-02 |  | 19th - 23rd | Junior Suite Type-3 1 Bedroom Suite - B 19th to 23rd Floor Power Layout | 1252-MKM-05Q-IDP-01-DWG-0191 | 2 OF 2 | 2017-02-06 | 2018-03-13 | 2018-03-28 | 15 | C | MKM | 2018-06-05 | 2018-06-13 | 8 | B | MKM | [40 empty] | 2018-06-05 | 2018-06-13 | 8 | B | Rev-1 | C | Resub..reqd | 2018-04-09 |  | 1 5 | MKM
134 | SD-0036-04 | ARK-0055-00 | 19th - 23rd | 19th to 23rd Floor Guest Rooms 1 Bedroom Suite Type B (G1BB) Elevation A & D | 1252-MKM-05Q-IDP-01-DWG-0192 | 1 OF 1 | 2017-02-06 | 2017-02-09 | 2017-02-21 | 12 | B | MKM | 2018-03-13 | 2018-03-28 | 15 | C | MKM | 2019-07-15 |  | 42 | OD | MKM | 2019-08-06 |  | 20 | OD | MKM | [30 empty] | 2019-08-06 |  | 20 | OD | Rev-3 | C | Resub..reqd | 2018-04-09 |  | 1 5 | MKM
135 | SD-0036-04 | ARK-0055-00 | 19th - 23rd | 19th to 23rd Floor Guest Rooms 1 Bedroom Suite Type B (G1BB) Elevation C & D | 1252-MKM-05Q-IDP-01-DWG-0193 | 1 OF 1 | 2017-02-06 | 2017-02-09 | 2017-02-21 | 12 | B | MKM | 2018-03-13 | 2018-03-28 | 15 | C | MKM | 2019-07-15 |  | 42 | OD | MKM | 2019-08-06 |  | 20 | OD | MKM | [30 empty] | 2019-08-06 |  | 20 | OD | Rev-3 | C | Resub..reqd | 2018-04-09 |  | 1 5 | MKM
136 | SD-0073-02 |  | 19th - 23rd | 19th to 23rd Floor Guest Room 1 Bedroom Suite Type B (GIBB) DB Cabinet Details | 1252-MKM-05Q-IDP-01-DWG-0381 | 1 OF 1 | 2017-02-06 | 2017-12-20 | 2018-01-17 | 28 | C | MKM | 2018-03-18 | 2018-03-20 | 2 | C | MKM | 2018-03-26 | 2018-05-01 | 36 | B | MKM | [35 empty] | 2018-03-26 | 2018-05-01 | 36 | B | Rev-2 | P |  |  |  | 1 5 | MKM
GUEST ROOMS STANDARD ROOM UNIT TYPE (GSR1) & (GSR1A) | [66 empty] | 1 139
137 | SD-0037-03 |  | 24th - 27th | 24th to 27th Floor Guest Rooms Standard King Room_Type-04 (SKG4) General Arrangement & Power Plan | 1252-MKM-05Q-IDP-01-DWG-0194 | 1 OF 6 | 2017-02-06 | 2017-02-09 | 2017-02-28 | 19 | B | MKM | 2018-01-30 | 2018-02-01 | 2 | B | MKM | 2018-08-28 | 2018-09-05 | 8 | B | MKM | [35 empty] | 2018-08-28 | 2018-09-05 | 8 | B | Rev-2 | B | Approved |  |  | 1 5 | MKM
138 | SD-0037-03 |  | 28th | 28th Floor Guest Rooms Standard King Room Type_04A (SKG4A) General Arrangement & Power Plan | 1252-MKM-05Q-IDP-01-DWG-0194 | 2 OF 6 | 2017-02-06 | 2018-08-28 | 2018-09-05 | 8 | B | MKM | [45 empty] | 2018-08-28 | 2018-09-05 | 8 | B | Rev-0 | B | Approved |  |  | 1 5 | MKM
139 | SD-0037-03 |  | 29th | 29th Floor Guest Rooms Standard King Room Type_04B (SKG4B) General Arrangement & Power Plan | 1252-MKM-05Q-IDP-01-DWG-0194 | 3 OF 6 | 2017-02-06 | 2018-08-28 | 2018-09-05 | 8 | B | MKM | [45 empty] | 2018-08-28 | 2018-09-05 | 8 | B | Rev-0 | B | Approved |  |  | 1 5 | MKM
140 | SD-0037-03 |  | 30th - 33rd | 30th to 33th Floor Guest Rooms Standard King Room Type_05B (SKG5B) General Arrangement& Power Plan | 1252-MKM-05Q-IDP-01-DWG-0194 | 4 OF 6 | 2017-02-06 | 2018-08-28 | 2018-09-05 | 8 | B | MKM | [45 empty] | 2018-08-28 | 2018-09-05 | 8 | B | Rev-0 | B | Approved |  |  | 1 5 | MKM
141 | SD-0037-03 |  | 34th - 35th | 34th to 35th Floor Guest Rooms Standard King Room Type_05A (SKG5A) General Arrangement& Power Plan | 1252-MKM-05Q-IDP-01-DWG-0194 | 5 OF 6 | 2017-02-06 | 2018-08-28 | 2018-09-05 | 8 | B | MKM | [45 empty] | 2018-08-28 | 2018-09-05 | 8 | B | Rev-0 | B | Approved |  |  | 1 5 | MKM
142 | SD-0037-03 |  | 36th | 346th Floor Guest Rooms Standard King Room Type_05 (SKG5) General Arrangement& Power Plan | 1252-MKM-05Q-IDP-01-DWG-0194 | 6 OF 6 | 2017-02-06 | 2018-08-28 | 2018-09-05 | 8 | B | MKM | [45 empty] | 2018-08-28 | 2018-09-05 | 8 | B | Rev-0 | B | Approved |  |  | 1 5 | MKM
143 | SD-0037-02 |  | 24th - 41st | 24th to 41st Floor Guest Rooms Standard King Room_Type-01 (SKG1) Reflected Ceiling Plan | 1252-MKM-05Q-IDP-01-DWG-0195 | 1 OF 2 | 2017-02-06 | 2017-02-09 | 2017-02-28 | 19 | B | MKM | 2018-01-30 | 2018-02-01 | 2 | B | MKM | 2018-07-02 | 2018-07-09 | 7 | B | MKM | [35 empty] | 2018-07-02 | 2018-07-09 | 7 | B | Rev-2 | B | Approved |  |  | 1 5 | MKM
144 | SD-0037-01 |  | 24th - 36th | 24th to 36th Floor Guest Rooms Standard Room King Bed-Type (GSR1) & (GSR1A) General Arrangement Plans | 1252-MKM-05Q-IDP-01-DWG-0196 | 1 OF 1 | 2017-02-06 | 2017-02-09 | 2017-02-28 | 19 | B | MKM | 2018-01-30 | 2018-02-01 | 2 | B | MKM | [40 empty] | 2018-01-30 | 2018-02-01 | 2 | B | Rev-1 | B | Approved |  |  | 1 5 | MKM
GUEST ROOMS STANDARD ROOM UNIT TYPE (GSR1B) | [62 empty] | 0 |  |  |  | 1 146
145 | SD-0046-03 |  | 24th-41st | 24th to 41st Floor King Guest Room Type-3 (SKG3) Reflected Ceiling Plan | 1252-MKM-05Q-IDP-01-DWG-0198 | 1 OF 2 | 2017-02-09 | 2017-02-13 | 2017-02-27 | 14 | C | MKM | 2017-03-15 | 2017-04-02 | 18 | B | MKM | 2018-07-02 | 2018-07-09 | 7 | B | MKM | Issued to Site on 27-06-2018 | [34 empty] | Issued to Site on 27-06-2018 | 2018-07-09 | 7 | B | Rev-2 | B/C | Resub..reqd | 2018-04-04 |  | 1 5 | MKM
146 | SD-0046-04 |  | 24th-41st | 24th to 41st Floor King Guest Room Type-3 (SKG3) General Arrangement & Power Plan | 1252-MKM-05Q-IDP-01-DWG-0198 | 2 OF 2 | 2017-02-09 | 2018-08-28 | 2018-09-05 | 8 | B | MKM | [45 empty] | 2018-08-28 | 2018-09-05 | 8 | B | Rev-0 | A/C | Resub..reqd | 2018-04-04 |  | 1 5 | MKM
147 | SD-0154-00 | ARK-0051-00 | 30 | 30th Floor King guest Room - Type (SKG3) General Arrangement & Power Plan) | 1252-MKM-05Q-IDP-01-DWG-0199 | 1 OF 2 |  | 2019-03-24 | 2019-04-22 | 29 | B | MKM | [45 empty] | 2019-03-24 | 2019-04-22 | 29 | B | Rev-0 | A/C | Resub..reqd | 2018-04-04 |  | 1 5 | MKM
148 | SD-0154-00 | ARK-0051-00 | 30 | 30th Floor King guest Room - Type (SKG3) Reflected Ceiling Plan | 1252-MKM-05Q-IDP-01-DWG-0199 | 2 OF 2 |  | 2019-03-24 | 2019-04-22 | 29 | B | MKM | [45 empty] | 2019-03-24 | 2019-04-22 | 29 | B | Rev-0 | A/C | Resub..reqd | 2018-04-04 |  | 1 5 | MKM
149 | SD-0046-01 |  | 24th-36th | 24tf to 36th Floor Guest Rooms Standard Room Unit Type (GSR1B) Elevation A & B | 1252-MKM-05Q-IDP-01-DWG-0200 | 1 OF 1 | 2017-02-09 | 2017-02-13 | 2017-02-27 | 14 | C | MKM | 2017-03-15 | 2017-04-02 | 18 | A | MKM | [40 empty] | 2017-03-15 | 2017-04-02 | 18 | A | Rev-1 | A/C | Resub..reqd | 2018-04-04 |  | 1 5 | MKM
GUEST ROOMS STANDARD ROOM UNIT TYPE (GSR1C) | [62 empty] | 0 |  |  |  | 1 146
150 | SD-0037-00 |  | 24th - 36th | 24th to 36th Floor Guest Rooms Standard Room King Bed-Type (GSR1C) Plan & Elevation | 1252-MKM-05Q-IDP-01-DWG-0202 | 1 OF 1 | 2017-02-09 | 2017-02-09 | 2017-02-27 | 18 | B | MKM | [45 empty] | 2017-02-09 | 2017-02-27 | 18 | B | Rev-0 | B/C | Resub..reqd | 2018-04-04 |  | 1 5 | MKM
GUEST ROOMS STANDARD ROOM UNIT TYPE (GSR2) & (GSR2A) | [62 empty] | 0 |  |  |  | 1 146
151 | SD-0045-02 |  | 24th-41st | 24th to 41st Floor Guest Room Standard Room Twin Bed-Type (STW) General Arrangement & Power Plan | 1252-MKM-05Q-IDP-01-DWG-0204 | 1 OF 1 | 2017-02-09 | 2017-02-13 | 2017-02-28 | 15 | B | MKM | 2018-08-28 | 2018-09-05 | 8 | B | MKM | [40 empty] | 2018-08-28 | 2018-09-05 | 8 | B | Rev-1 | B/C | Resub..reqd | 2018-04-04 |  | 1 5 | MKM
152 | SD-0045-01 |  | 24th-41st | 24th to 41st Floor Standard Twin Room (STW) Reflected Ceiling Plan | 1252-MKM-05Q-IDP-01-DWG-0205 | 1 OF 2 | 2017-02-09 | 2017-02-13 | 2017-02-28 | 15 | B | MKM | 2018-07-02 | 2018-07-09 | 7 | B | MKM | [40 empty] | 2018-07-02 | 2018-07-09 | 7 | B | Rev-1 | B/C | Resub..reqd | 2018-04-04 |  | 1 5 | MKM
153 | SD-0045-02 |  | 37th-41st | 37th to 41st Floor Guest Rooms Standard King Room Type_06 (SKG6) General Arrangement & Power Plan | 1252-MKM-05Q-IDP-01-DWG-0206 | 1 OF 1 | 2017-02-09 | 2017-02-13 | 2017-02-28 | 15 | B | MKM | 2018-08-28 | 2018-09-05 | 8 | B | MKM | [40 empty] | 2018-08-28 | 2018-09-05 | 8 | B | Rev-1 | B/C | Resub..reqd | 2018-04-04 |  | 1 5 | MKM
GUEST ROOMS STANDARD HANDICAPPED ROOM UNIT TYPE (GSRH) | [62 empty] | 0 |  |  |  | 1 153
154 | SD-0049-03 | ARK-0008-00 | 24th-29th | 24th to 29th Floor Guest Room Standard Room Disabled Room-Type (DGG1) General Arrangement & Power Plan | 1252-MKM-05Q-IDP-01-DWG-0208 | 1 OF 1 | 2017-02-09 | 2017-02-16 | 2017-02-28 | 12 | B | MKM | 2018-08-28 | 2018-09-05 | 8 | C | MKM | 2018-09-25 | 2018-10-07 | 12 | B | MKM | [35 empty] | 2018-09-25 | 2018-10-07 | 12 | B | Rev-2 | B/C | Resub..reqd | 2018-04-04 |  | 1 5 | MKM
155 | SD-0049-01 |  | 24th-29th | 24th to 29th Floor Disable King Room (DKG1) Reflected Ceiling Plan | 1252-MKM-05Q-IDP-01-DWG-0209 | 1 OF 2 | 2017-02-09 | 2017-02-16 | 2017-02-28 | 12 | B | MKM | 2018-07-02 | 2018-07-09 | 7 | B | MKM | [40 empty] | 2018-07-02 | 2018-07-09 | 7 | B | Rev-1 | B/C | Resub..reqd | 2018-04-04 |  | 1 5 | MKM
156 | SD-0049-00 |  | 24th-29th | 24th to 29th Guest Room Standard Room Handicapped-Type (GSRH) Elevation A, B &C | 1252-MKM-05Q-IDP-01-DWG-0210 | 1 OF 1 | 2017-02-09 | 2017-02-16 | 2017-02-28 | 12 | B | MKM | [45 empty] | 2017-02-16 | 2017-02-28 | 12 | B | Rev-0 | B/C | Resub..reqd | 2018-04-04 |  | 1 5 | MKM
EXECUTIVE ROOM UNIT TYPE (GER1) & (GER1A) | [62 empty] | 0 |  |  |  | 1 160
157 | SD-0050-02 |  | 24th-41st | 24th to 41st King Guest Room - Type - 1 (SKG1) General Arrangement & Power Plan | 1252-MKM-05Q-IDP-01-DWG-0212 | 1 OF 1 | 2017-02-09 | 2017-02-16 | 2017-02-28 | 12 | B | MKM | 2018-09-12 | 2018-09-19 | 7 | B | MKM | [40 empty] | 2018-09-12 | 2018-09-19 | 7 | B | Rev-1 | B/C | Resub..reqd | 2018-04-04 |  | 1 5 | MKM
158 | SD-0050-01 |  | 37th-41st | 37th to 41st Floor Standard Kingroom Type-6 (SKG6) Reflected Ceiling Plan | 1252-MKM-05Q-IDP-01-DWG-0213 | 1 OF 2 | 2017-02-09 | 2017-02-16 | 2017-02-28 | 12 | B | MKM | 2018-07-02 | 2018-07-09 | 7 | B | MKM | [40 empty] | 2018-07-02 | 2018-07-09 | 7 | B | Rev-1 | B/C | Resub..reqd | 2018-04-04 |  | 1 5 | MKM
159 | SD-0050-00 |  | 37th-41st | 37th to 41st Floor Executive Room Unit Type (GER1) & (GER1A) Elevations | 1252-MKM-05Q-IDP-01-DWG-0214 | 1 OF 1 | 2017-02-09 | 2017-02-16 | 2017-02-28 | 12 | B | MKM | [45 empty] | 2017-02-16 | 2017-02-28 | 12 | B | Rev-0 | B/C | Resub..reqd | 2018-04-04 |  | 1 5 | MKM
EXECUTIVE ROOM UNIT TYPE (GER1B) | [66 empty] | 1 160
160 | SD-0051-01 |  | 37th-41st | 37th to 41st Floor Executive Room Unit Type (GER1B) General Arragement Plans | 1252-MKM-05Q-IDP-01-DWG-0216 | 1 OF 1 | 2017-02-09 | 2017-02-16 | 2017-03-02 | 14 | C | MKM | 2017-03-15 | 2017-04-02 | 18 | A | MKM | [40 empty] | 2017-03-15 | 2017-04-02 | 18 | A | Rev-1 |  |  |  |  | 1 5 | MKM
161 | SD-0051-01 |  | 37th-41st | 37th to 41st Floor Executive Room Unit Type (GER1B) Elevation A & B | 1252-MKM-05Q-IDP-01-DWG-0218 | 1 OF 1 | 2017-02-09 | 2017-02-16 | 2017-03-02 | 14 | C | MKM | 2017-03-15 | 2017-04-02 | 18 | A | MKM | [40 empty] | 2017-03-15 | 2017-04-02 | 18 | A | Rev-1 |  |  |  |  | 1 5 | MKM
EXECUTIVE ROOM UNIT TYPE (GER1C) | [62 empty] | 0 |  |  |  | 1 160
162 | SD-0052-02 |  | 37th-41st | 37th to 41st Floor Executive Room Type (GER1C) Plan & Elevation | 1252-MKM-05Q-IDP-01-DWG-0220 | 1 OF 1 | 2017-02-09 | 2017-02-16 | 2017-03-02 | 14 | C | MKM | 2017-03-15 | 2017-04-02 | 18 | B | MKM | 2018-09-12 | 2018-09-19 | 7 | B | MKM | [35 empty] | 2018-09-12 | 2018-09-19 | 7 | B | Rev-2 | B/C | Resub..reqd | 2018-04-04 |  | 1 5 | MKM
EXECUTIVE ROOM UNIT TYPE (GER2) | [62 empty] | 0 |  |  |  | 1 160
163 | SD-0053-00 |  | 37th - 41st | 37th to 41st Floor Executive Twin Bed Room Type-(GER2) General Arragement Plan | 1252-MKM-05Q-IDP-01-DWG-0222 | 1 OF 1 | 2017-02-09 | 2017-02-16 | 2017-03-02 | 14 | B | MKM | [45 empty] | 2017-02-16 | 2017-03-02 | 14 | B | Rev-0 | B/C | Resub..reqd | 2018-04-04 |  | 1 5 | MKM
164 | SD-0053-03 |  | 30th - 36th | 30th to 36th Floor King Guest Room (Type-05) (SKG5) Reflected Ceiling Plan | 1252-MKM-05Q-IDP-01-DWG-0223 | 1 OF 2 | 2017-02-09 | 2017-02-16 | 2017-03-02 | 14 | C | MKM | 2017-03-15 | 2017-04-02 | 18 | A | MKM | 2018-07-02 | 2018-07-09 | 7 | B | MKM | [35 empty] | 2018-07-02 | 2018-07-09 | 7 | B | Rev-2 | A/C | Resub..reqd | 2018-04-04 |  | 1 5 | MKM
165 | SD-0053-01 |  | 37th - 41st | 37th to 41st Floor Executive Twin Bed Room Type-(GER2) Elevation A,B&C | 1252-MKM-05Q-IDP-01-DWG-0224 | 1 OF 1 | 2017-02-09 | 2017-02-16 | 2017-03-02 | 14 | C | MKM | 2017-03-15 | 2017-04-02 | 18 | B | MKM | [40 empty] | 2017-03-15 | 2017-04-02 | 18 | B | Rev-1 | B/C | Resub..reqd | 2018-04-04 |  | 1 5 | MKM
300_MILLWORK DETAILS | [66 empty] | 1 167
PANTRY UNITS | [66 empty] | 1 160
166 | SD-0019-00 |  |  | Pantry Units - Schedule | 1252-MKM-05Q-IDP-01-DWG-0300 | 1 OF 1 | 2017-01-22 | 2017-01-22 | 2017-02-07 | 16 | SS | MKM | [45 empty] | 2017-01-22 | 2017-02-07 | 16 | SS | Rev-0 | X |  |  |  | 1 5 | MKM
167 | SD-0019-06 |  |  | Kitchen High Counter Details | 1252-MKM-05Q-IDP-01-DWG-0301 | 1 OF 1 | 2017-01-22 | 2017-01-22 | 2017-02-07 | 16 | B | MKM | 2017-03-16 | 2017-03-30 | 14 | A | MKM | 2017-06-19 | 2017-06-20 | 1 | B | MKM | 2017-06-29 | 2017-07-03 | 4 | B | MKM | 2017-07-11 | 2017-07-15 | 4 | B | MKM | 2018-01-03 | 2018-01-04 | 1 | SS | MKM | [20 empty] | 2018-01-03 | 2018-01-04 | 1 | SS | Rev-5 | X |  |  |  | 1 5 | MKM
168 | SD-0019-05 |  |  | Pantry Unit Type 1 & 1A | 1252-MKM-05Q-IDP-01-DWG-0302 | 1 OF 1 | 2017-01-22 | 2017-01-22 | 2017-02-07 | 16 | C | MKM | 2017-03-16 | 2017-03-30 | 14 | B | MKM | 2017-06-29 | 2017-07-03 | 4 | B | MKM | 2017-07-11 | 2017-07-15 | 4 | SS | MKM | [30 empty] | 2017-07-11 | 2017-07-15 | 4 | SS | Rev-3 | X
169 | SD-0019-05 |  |  | Pantry Unit Type 2 & 2A | 1252-MKM-05Q-IDP-01-DWG-0303 | 1 OF 1 | 2017-01-22 | 2017-01-22 | 2017-02-07 | 16 | C | MKM | 2017-03-16 | 2017-03-30 | 14 | B | MKM | 2017-06-29 | 2017-07-03 | 4 | B | MKM | 2017-07-11 | 2017-07-15 | 4 | SS | MKM | [30 empty] | 2017-07-11 | 2017-07-15 | 4 | SS | Rev-3 | X
170 | SD-0019-05 |  |  | Pantry Unit Type 3 & 3A | 1252-MKM-05Q-IDP-01-DWG-0304 | 1 OF 2 | 2017-01-22 | 2017-01-22 | 2017-02-07 | 16 | C | MKM | 2017-03-16 | 2017-03-30 | 14 | B | MKM | 2017-06-29 | 2017-07-03 | 4 | B | MKM | 2017-07-11 | 2017-07-15 | 4 | SS | MKM | [30 empty] | 2017-07-11 | 2017-07-15 | 4 | SS | Rev-3 | X
171 | SD-0019-05 |  |  | Pantry Unit Type 3 & 3A | 1252-MKM-05Q-IDP-01-DWG-0304 | 2 OF 2 | 2017-01-22 | 2017-01-22 | 2017-02-07 | 16 | C | MKM | 2017-03-16 | 2017-03-30 | 14 | A | MKM | 2017-06-29 | 2017-07-03 | 4 | B | MKM | 2017-07-11 | 2017-07-15 | 4 | SS | MKM | [30 empty] | 2017-07-11 | 2017-07-15 | 4 | SS | Rev-3 | X
172 | SD-0019-06 |  |  | Pantry Unit Type 4 & 4A | 1252-MKM-05Q-IDP-01-DWG-0305 | 1 OF 2 | 2017-01-22 | 2017-01-22 | 2017-02-07 | 16 | C | MKM | 2017-03-16 | 2017-03-30 | 14 | B | MKM | 2017-06-29 | 2017-07-03 | 4 | B | MKM | 2017-07-11 | 2017-07-15 | 4 | SS | MKM | [30 empty] | 2017-07-11 | 2017-07-15 | 4 | SS | Rev-3 | X
173 | SD-0019-06 |  |  | Pantry Unit Type 4 & 4A | 1252-MKM-05Q-IDP-01-DWG-0305 | 2 OF 2 | 2017-01-22 | 2017-01-22 | 2017-02-07 | 16 | C | MKM | 2017-03-16 | 2017-03-30 | 14 | B | MKM | 2017-06-29 | 2017-07-03 | 4 | B | MKM | 2017-07-11 | 2017-07-15 | 4 | SS | MKM | [30 empty] | 2017-07-11 | 2017-07-15 | 4 | SS | Rev-3 | X
174 | SD-0019-05 |  |  | Pantry Unit Type 5 & 5A | 1252-MKM-05Q-IDP-01-DWG-0306 | 1 OF 1 | 2017-01-22 | 2017-01-22 | 2017-02-07 | 16 | C | MKM | 2017-03-16 | 2017-03-30 | 14 | B | MKM | 2017-04-13 | 2017-04-20 | 7 | A | MKM | 2017-06-29 | 2017-07-03 | 4 | B | MKM | 2017-07-11 | 2017-07-15 | 4 | SS | MKM | [25 empty] | 2017-07-11 | 2017-07-15 | 4 | SS | Rev-4 | X
PANTRY UNITS | [62 empty] | 0 |  |  |  | 1 160
175 | SD-0091-00 |  | 8th - 17th | 8th to 17th Floor Pantry / Pantry Schedule | 1252-MKM-05Q-IDP-01-DWG-0300 | 1 OF 1 | 2017-01-22 | 2018-03-06 | 2018-03-12 | 6 | B | MKM | [45 empty] | 2018-03-06 | 2018-03-12 | 6 | B | Rev-0 | B | Approved |  |  | 1 5 | MKM
176 | SD-0091-00 |  | 8th - 17th | 8th Floor Apartment Type-A Kitchen Counter Detail Drawing | 1252-MKM-05Q-IDP-01-DWG-0301 | 1 OF 1 | 2017-01-22 | 2018-03-06 | 2018-03-12 | 6 | B | MKM | [45 empty] | 2018-03-06 | 2018-03-12 | 6 | B | Rev-0 | B | Approved |  |  | 1 5 | MKM
177 | SD-0091-03 |  |  | Pantry Unit Type -1 (Left) Pantry Unit Type - 1A (Right) Details | 1252-MKM-05Q-IDP-01-DWG-0302 | 1 OF 1 | 2017-01-22 | 2018-03-06 | 2018-03-12 | 6 | B | MKM | 2018-07-05 | 2018-07-11 | 6 | B | MKM | [40 empty] | 2018-07-05 | 2018-07-11 | 6 | B | Rev-1 | B | Approved
178 | SD-0091-03 |  |  | Pantry Unit Type 2 (Left) Pantry Unit - 2A (Right) Details | 1252-MKM-05Q-IDP-01-DWG-0303 | 1 OF 2 | 2017-01-22 | 2018-03-06 | 2018-03-12 | 6 | C | MKM | 2018-03-18 | 2018-03-24 | 6 | C | MKM | 2018-07-05 | 2018-07-11 | 6 | B | MKM | [35 empty] | 2018-07-05 | 2018-07-11 | 6 | B | Rev-2 | C | Resub..reqd. Awaiting RFI | 2018-04-05
179 | SD-0091-03 |  |  | Pantry Unit Type 2 (Left) Pantry Unit - 2A (Right) Details | 1252-MKM-05Q-IDP-01-DWG-0303 | 2 OF 2 |  | 2018-07-05 | 2018-07-11 | 6 | B | MKM | [45 empty] | 2018-07-05 | 2018-07-11 | 6 | B | Rev-0 | C | Resub..reqd. Awaiting RFI | 2018-04-05
180 | SD-0091-05 |  |  | Pantry Unit Type - 3 (Left) Pantry Unit Type - 3A (Right) Details | 1252-MKM-05Q-IDP-01-DWG-0304 | 1 OF 2 | 2017-01-22 | 2018-03-06 | 2018-03-12 | 6 | C | MKM | 2018-03-18 | 2018-03-24 | 6 | B | MKM | 2018-07-05 | 2018-07-11 | 6 | B | MKM | 2018-07-22 | 2018-07-29 | 7 | C | MKM | 2018-07-31 | 2018-08-28 | 28 | B | MKM | [25 empty] | 2018-07-31 | 2018-08-28 | 28 | B | Rev-4 | B | Approved
181 | SD-0091-05 |  |  | Pantry Unit Type - 3 (Left) Pantry Unit Type - 3A (Right) Details | 1252-MKM-05Q-IDP-01-DWG-0304 | 2 OF 2 | 2017-01-22 | 2018-03-06 | 2018-03-12 | 6 | C | MKM | 2018-03-18 | 2018-03-24 | 6 | B | MKM | 2018-07-05 | 2018-07-11 | 6 | B | MKM | 2018-07-22 | 2018-07-29 | 7 | C | MKM | 2018-07-31 | 2018-08-28 | 28 | B | MKM | [25 empty] | 2018-07-31 | 2018-08-28 | 28 | B | Rev-4 | B | Approved
182 | SD-0091-02 |  |  | Pantry Unit Type 4 & 4A | 1252-MKM-05Q-IDP-01-DWG-0305 | 1 OF 2 | 2017-01-22 | 2018-03-06 | 2018-03-12 | 6 | B | MKM | 2018-06-20 | 2018-06-27 | 7 | B | MKM | [40 empty] | 2018-06-20 | 2018-06-27 | 7 | B | Rev-1 | B | Approved
183 | SD-0091-02 |  |  | Pantry Unit Type 4 & 4A | 1252-MKM-05Q-IDP-01-DWG-0305 | 2 OF 2 | 2017-01-22 | 2018-03-06 | 2018-03-12 | 6 | B | MKM | 2018-06-20 | 2018-06-27 | 7 | B | MKM | [40 empty] | 2018-06-20 | 2018-06-27 | 7 | B | Rev-1 | B | Approved
184 | SD-0091-03 |  |  | Pantry Unit Type - 5 (Left) Pantry Unit Type - 5A (Right) Details | 1252-MKM-05Q-IDP-01-DWG-0306 | 1 OF 1 | 2017-01-22 | 2018-03-06 | 2018-03-12 | 6 | B | MKM | 2018-07-05 | 2018-07-11 | 6 | B | MKM | [40 empty] | 2018-07-05 | 2018-07-11 | 6 | B | Rev-1 | B | Approved
185 | SD-0102-01 |  |  | Work Desk Typical Details | 1252-MKM-05Q-IDP-01-DWG-0307 | 1 OF 1 |  | 2018-06-09 | 2018-07-24 | 45 | C | MKM | 2018-07-31 | 2018-08-06 | 6 | B | MKM | [40 empty] | 2018-07-31 | 2018-08-06 | 6 | B | Rev-1 |  |  |  |  | 1 5 | MKM
186 | SD-0103-00 |  | 17th Floor | 17th Floor Studio Unit 'B' Apartment Rooms # 1707 & 1710 Reflected Ceiling Plan | 1252-MKM-05Q-IDP-01-DWG-0307a | 1 OF 1 |  | 2018-06-25 | 2018-06-28 | 3 | B | MKM | [45 empty] | 2018-06-25 | 2018-06-28 | 3 | B | Rev-0 | B | Approved
187 | SD-0104-01 |  | 19th - 23rd Floor | 19th to 23rd Floor Junior Suites 1 & 1A Work Desk Type - 4A Details | 1252-MKM-05Q-IDP-01-DWG-0308 | 1 OF 1 |  | 2018-06-26 | 2018-07-03 | 7 | C | MKM | 2018-07-31 | 2018-08-06 | 6 | B | MKM | [40 empty] | 2018-07-31 | 2018-08-06 | 6 | B | Rev-1 | B | Approved
188 | SD-0105-02 |  | 8th - 17th | 8th to 17th Floor One Bedroom Apartment Niche Details | 1252-MKM-05Q-IDP-01-DWG-0309 | 1 OF 1 |  | 2018-06-27 | 2018-07-03 | 6 | B | MKM | 2018-07-22 | 2018-07-29 | 7 | B | MKM | 2018-07-31 | 2018-08-28 | 28 | B | MKM | [35 empty] | 2018-07-31 | 2018-08-28 | 28 | B | Rev-2 | B | Approved
189 | SD-0106-00 |  | 24th - 41st Floor | 24th to 41st Floor Guest Rooms Standard King Room_Type-02 (SKG2) Reflected Ceiling Plan | 1252-MKM-05Q-IDP-01-DWG-0311 | 1 OF 1 |  | 2018-07-02 | 2018-07-09 | 7 | B | MKM | [45 empty] | 2018-07-02 | 2018-07-09 | 7 | B | Rev-0 | B | Approved
190 | SD-0106-00 |  | 24th - 29th Floor | 24th to 29thFloor Guest Rooms Standard King Room_Type-02 (SKG2) Reflected Ceiling Plan | 1252-MKM-05Q-IDP-01-DWG-0312 | 1 OF 1 |  | 2018-07-02 | 2018-07-09 | 7 | B | MKM | [45 empty] | 2018-07-02 | 2018-07-09 | 7 | B | Rev-0 | B | Approved
191 | SD-0107-01 |  | 8th Floor | 8th Floor 1 Bedroom Apartment Handicapped Bathroom Detail Room # S' 0808 & 0809 | 1252-MKM-05Q-IDP-01-DWG-0310 | 1 OF 1 |  | 2018-07-02 | 2018-07-09 | 7 | FI | MKM | 2018-07-11 | 2018-07-17 | 6 | B | MKM | [40 empty] | 2018-07-11 | 2018-07-17 | 6 | B | Rev-1 | B | Approved
192 | SD-0108-00 |  |  | 8th Floor 1 Bedroom Apartments Handicapped Bathroom Door Detail Room # S' 0808 & 0809 | 1252-MKM-05Q-IDP-01-DWG-0313 | 1 OF 1 |  | 2018-07-04 | 2018-07-11 | 7 | B | MKM | [45 empty] | 2018-07-04 | 2018-07-11 | 7 | B | Rev-0 | B | Approved
193 | SD-0108-00 |  |  | 8th Floor 1 Bedroom Apartments Handicapped Apartments Main Entrance Door (WD1) 60 Min. Fire Rated | 1252-MKM-05Q-IDP-01-DWG-0314 | 1 OF 1 |  | 2018-07-04 | 2018-07-11 | 7 | B | MKM | [45 empty] | 2018-07-04 | 2018-07-11 | 7 | B | Rev-0 | B | Approved
194 | SD-0110-01 |  |  | 24th to 33rd Floor King Room Type-4 & 5 Work Desk (Type-06) Details | 1252-MKM-05Q-IDP-01-DWG-0315 | 1 OF 1 |  | 2018-07-09 | 2018-07-16 | 7 | C | MKM | 2018-07-31 | 2018-08-06 | 6 | B | MKM | [40 empty] | 2018-07-31 | 2018-08-06 | 6 | B | Rev-1 | B | Approved
195 | SD-0111-00 |  |  | 8th Floor_1 Bedroom Apartments Handicapped Bedroom Door Details Room No's 0808 & 0809 | 1252-MKM-05Q-IDP-01-DWG-0316 | 1 OF 1 |  | 2018-07-22 | 2018-08-05 | 14 | B | MKM | [45 empty] | 2018-07-22 | 2018-08-05 | 14 | B | Rev-0 | B | Approved
WORK DESKS | [62 empty] | 0 |  |  |  | 1 160
196 | SD-0028-00 |  | 8-17th | Work Desks -Location Layout | 1252-MKM-05Q-IDP-01-DWG-0320 | 1 OF 3 | 2017-01-25 | 2017-01-29 | 2017-02-09 | 11 | SS | MKM | [45 empty] | 2017-01-29 | 2017-02-09 | 11 | SS | Rev-0 | X
197 | SD-0028-00 |  | 8-17th | Work Desks -Location Layout | 1252-MKM-05Q-IDP-01-DWG-0320 | 2 OF 3 | 2017-01-25 | 2017-01-29 | 2017-02-09 | 11 | SS | MKM | [45 empty] | 2017-01-29 | 2017-02-09 | 11 | SS | Rev-0 | X
198 | SD-0039-00 |  | 8-17th | Work Desks -Location Layout | 1252-MKM-05Q-IDP-01-DWG-0320 | 3 OF 3 | 2017-01-25 | 2017-02-09 | 2017-03-01 | 20 | SS | MKM | [45 empty] | 2017-02-09 | 2017-03-01 | 20 | SS | Rev-0 | X
199 | SD-0028-01 |  | 8-17th | Work Desk Type - 1A, 1B & 1C | 1252-MKM-05Q-IDP-01-DWG-0321 | 1 OF 1 | 2017-01-25 | 2017-01-29 | 2017-02-09 | 11 | C | MKM | 2017-02-19 | 2017-02-28 | 9 | A | MKM | [40 empty] | 2017-02-19 | 2017-02-28 | 9 | A | Rev-1
200 | SD-0028-04 |  | 8-17th | 8th Floor Apartment Type-2 Work Desk Detail Drawing | 1252-MKM-05Q-IDP-01-DWG-0322 | 1 OF 4 | 2017-01-25 | 2017-01-29 | 2017-02-09 | 11 | B | MKM | 2017-07-02 | 2017-08-01 | 30 | A | MKM | [40 empty] | 2017-07-02 | 2017-08-01 | 30 | A | Rev-1
201 | SD-0028-04 |  | 8-17th | 9th to 11th Floor Apartment Type-2A Work Desk Detail Drawing | 1252-MKM-05Q-IDP-01-DWG-0322 | 2 OF 4 | 2017-01-25 | 2017-07-02 | 2017-08-01 | 30 | A | MKM | [45 empty] | 2017-07-02 | 2017-08-01 | 30 | A | Rev-0
202 | SD-0028-04 |  | 8-17th | Work Desk Type - 2B | 1252-MKM-05Q-IDP-01-DWG-0322 | 3 OF 4 | 2017-01-25 | 2017-07-02 | 2017-08-01 | 30 | C | MKM | 2017-08-02 | 2017-09-07 | 36 | SS | MKM | Superseded due to the Design Changes | [39 empty] | Superseded due to the Design Changes | 2017-09-07 | 36 | SS | Rev-1 | X
203 | SD-0028-04 |  | 8-17th | Work Desk Type - 2C | 1252-MKM-05Q-IDP-01-DWG-0322 | 4 OF 4 | 2017-01-25 | 2017-07-02 | 2017-08-01 | 30 | C | MKM | 2017-08-02 | 2017-09-07 | 36 | SS | MKM | Superseded due to the Design Changes | [39 empty] | Superseded due to the Design Changes | 2017-09-07 | 36 | SS | Rev-1 | X
204 | SD-0028-04 |  | 8-17th | Work Desk Type - 2C | 1252-MKM-05Q-IDP-01-DWG-0322 | 4 OF 4 | 2017-01-25 | 2017-08-02 | 2017-09-07 | 36 | SS | MKM | Superseded due to the Design Changes | [44 empty] | Superseded due to the Design Changes | 2017-09-07 | 36 | SS | Rev-0 | X
202 | SD-0028-03 |  | 8-17th | 8th to 17th Floor Apartment Type-3 Work Desk Detail Drawing | 1252-MKM-05Q-IDP-01-DWG-0323 | 1 OF 4 | 2017-01-25 | 2017-01-29 | 2017-02-09 | 11 | B | MKM | 2017-07-02 | 2017-07-04 | 2 | A | MKM | [40 empty] | 2017-07-02 | 2017-07-04 | 2 | A | Rev-1
203 | SD-0028-03 |  | 8-17th | 8th to 17th Floor Apartment Type-3A Work Desk Detail Drawing | 1252-MKM-05Q-IDP-01-DWG-0323 | 2 OF 4 | 2017-01-25 | 2017-01-29 | 2017-02-09 | 11 | B | MKM | 2017-07-02 | 2017-07-04 | 2 | A | MKM | [40 empty] | 2017-07-02 | 2017-07-04 | 2 | A | Rev-1
204 | SD-0028-03 |  | 8-17th | 8th to 17th Floor Apartment Type-5 Work Desk Detail Drawing | 1252-MKM-05Q-IDP-01-DWG-0323 | 3 OF 4 |  | 2017-07-02 | 2017-07-04 | 2 | A | MKM | [45 empty] | 2017-07-02 | 2017-07-04 | 2 | A | Rev-0
205 | SD-0028-03 |  | 8-17th | 8th to 17th Floor Apartment Type-5A Work Desk Detail Drawing | 1252-MKM-05Q-IDP-01-DWG-0323 | 4 OF 4 |  | 2017-07-02 | 2017-07-04 | 2 | A | MKM | [45 empty] | 2017-07-02 | 2017-07-04 | 2 | A | Rev-0
206 | SD-0028-05 |  | 8-17th | 8th to 17th Floor Apartment Work Desk Type-1 @ Studio - A Detail Drawing | 1252-MKM-05Q-IDP-01-DWG-0324 | 1 OF 1 | 2017-01-25 | 2017-01-29 | 2017-02-09 | 11 | B | MKM | 2018-06-19 | 2018-06-27 | 8 | B | MKM | [40 empty] | 2018-06-19 | 2018-06-27 | 8 | B | Rev-1 |  |  |  |  | 1 5 | MKM
207 | SD-0039-06 |  | 24th - 41st | 24th to 41st Floor Work Desk Details Type-06 | 1252-MKM-05Q-IDP-01-DWG-0325 | 1 OF 2 | 2017-02-02 | 2017-02-09 | 2017-03-01 | 20 | B | MKM | 2017-11-14 | 2018-01-23 | 70 | B | MKM | 2018-01-30 | 2018-02-01 | 2 | C | MKM | 2018-02-05 | 2018-02-08 | 3 | B | MKM | 2018-03-08 | 2018-03-13 | 5 | B | MKM | 2018-06-17 | 2018-06-24 | 7 | B | MKM | [20 empty] | 2018-06-17 | 2018-06-24 | 7 | B | Rev-5 | B | Approved
208 | SD-0039-05 |  | 24th - 41st | 24th to 41st Floor Work Desk Details Type-06 | 1252-MKM-05Q-IDP-01-DWG-0325 | 2 OF 2 | 2017-02-02 | 2017-02-09 | 2017-03-01 | 20 | B | MKM | 2017-11-14 | 2018-01-23 | 70 | B | MKM | 2018-01-30 | 2018-02-01 | 2 | C | MKM | 2018-02-05 | 2018-02-08 | 3 | B | MKM | 2018-03-08 | 2018-03-13 | 5 | B | MKM | [25 empty] | 2018-03-08 | 2018-03-13 | 5 | B | Rev-4 | B | Approved
209 | SD-0039-01 |  | 8-17th | Work Desk Type - 7 & 8 | 1252-MKM-05Q-IDP-01-DWG-0326 | 1 OF 2 | 2017-02-02 | 2017-02-09 | 2017-03-01 | 20 | B | MKM | 2017-11-14 | 2018-01-23 | 70 | SS | MKM | [40 empty] | 2017-11-14 | 2018-01-23 | 70 | SS | Rev-1 | X
210 | SD-0039-01 |  | 8-17th | Work Desk Type - 7 & 8 | 1252-MKM-05Q-IDP-01-DWG-0326 | 2 OF 2 |  | 2017-11-14 | 2018-01-23 | 70 | SS | MKM | [45 empty] | 2017-11-14 | 2018-01-23 | 70 | SS | Rev-0 | X
211 | SD-0039-00 |  | 8-17th | Work Desk Type - 9 | 1252-MKM-05Q-IDP-01-DWG-0327 | 1 OF 1 | 2017-02-02 | 2017-02-09 | 2017-03-01 | 20 | SS | MKM | [45 empty] | 2017-02-09 | 2017-03-01 | 20 | SS | Rev-0 | X
212 | SD-0039-06 |  | 24th - 41st | 24th to 41st Floor Work Desk (SWGS-319) Details | 1252-MKM-05Q-IDP-01-DWG-0328 | 1 OF 2 | 2017-02-02 | 2017-02-09 | 2017-03-01 | 20 | B | MKM | 2017-11-14 | 2018-01-23 | 70 | B | MKM | 2018-04-02 | 2018-04-05 | 3 | C | MKM | 2018-06-17 | 2018-06-24 | 7 | B | MKM | [30 empty] | 2018-06-17 | 2018-06-24 | 7 | B | Rev-3 | B/C | Resub..reqd | 2018-04-03
213 | SD-0039-06 |  | 24th - 41st | 24th to 41st Floor Work Desk (SWGS-319) Details | 1252-MKM-05Q-IDP-01-DWG-0328 | 2 OF 2 | 2017-02-02 | 2018-04-02 | 2018-04-05 | 3 | C | MKM | 2018-06-17 | 2018-06-24 | 7 | B | MKM | [40 empty] | 2018-06-17 | 2018-06-24 | 7 | B | Rev-1
214 | SD-0028-02 |  | 8-17th | Work Desk Type - 11 | 1252-MKM-05Q-IDP-01-DWG-0329 | 1 OF 1 | 2017-02-02 | 2017-01-29 | 2017-02-09 | 11 | B | MKM | 2017-04-04 | 2017-04-05 | 1 | A | MKM | [40 empty] | 2017-04-04 | 2017-04-05 | 1 | A | Rev-1 | A/C | Resub..reqd | 2018-04-03
215 | SD-0068-03 |  | 24th-31st | 24th to 31st Floor Work Desk Details Type-12 | 1252-MKM-05Q-IDP-01-DWG-0379 | 1 OF 3 |  | 2017-09-13 | 2017-11-06 | 54 | C | MKM | 2017-11-21 | 2017-11-23 | 2 | C | MKM | 2017-11-28 | 2017-12-07 | 9 | C | MKM | 2017-12-13 | 2018-01-17 | 35 | A | MKM | [30 empty] | 2017-12-13 | 2018-01-17 | 35 | A | Rev-3
216 | SD-0068-00 |  | 24th-41st | 24th to 41st Floor Work Desk Details Type-12 | 1252-MKM-05Q-IDP-01-DWG-0379 | 2 OF 3 |  | 2017-09-13 | 2017-11-06 | 54 | B | MKM | [45 empty] | 2017-09-13 | 2017-11-06 | 54 | B | Rev-0
217 | SD-0068-00 |  | 24th-41st | 24th to 41st Floor Work Desk Details Type-12 | 1252-MKM-05Q-IDP-01-DWG-0379 | 3 OF 3 |  | 2017-09-13 | 2017-11-06 | 54 | B | MKM | [45 empty] | 2017-09-13 | 2017-11-06 | 54 | B | Rev-0
WORK DESKS | [62 empty] | B | Approved |  |  | 1 160
218 | SD-0090-01 |  | 8th-17th | 8th & 9th to 13th Floor Apartments Workdesk Location Layout | 1252-MKM-05Q-IDP-01-DWG-0320 | 1 OF 3 | 2017-01-25 | 2018-03-06 | 2018-03-12 | 6 | C | MKM | 2018-03-18 | 2018-03-20 | 2 | B | MKM | [40 empty] | 2018-03-18 | 2018-03-20 | 2 | B | Rev-1 | B | Approved
219 | SD-0090-00 |  | 8th-17th | 8th & 17th Floor Apartments Oval Work Desk Type - 01 Details | 1252-MKM-05Q-IDP-01-DWG-0382 | 1 OF 2 |  | 2018-03-06 | 2018-03-12 | 6 | B | MKM | [45 empty] | 2018-03-06 | 2018-03-12 | 6 | B | Rev-0 | B | Approved |  |  | 1 5 | MKM
220 | SD-0090-00 |  | 8th-17th | 8th & 17th Floor Apartments Oval Work Desk Type - 01 Details | 1252-MKM-05Q-IDP-01-DWG-0382 | 2 OF 2 |  | 2018-03-06 | 2018-03-12 | 6 | B | MKM | [45 empty] | 2018-03-06 | 2018-03-12 | 6 | B | Rev-0 | B | Approved |  |  | 1 5 | MKM
221 | SD-0090-00 |  | 8th-17th | 8th & 17th Floor Apartments Work Desk Type -2 Detail | 1252-MKM-05Q-IDP-01-DWG-0383 | 1 OF 1 |  | 2018-03-06 | 2018-03-12 | 6 | B | MKM | [45 empty] | 2018-03-06 | 2018-03-12 | 6 | B | Rev-0 | B | Approved |  |  | 1 5 | MKM
222 | SD-0096-00 |  | 19th to 23rd Floor | Work Desks -Location Layout | 1252-MKM-05Q-IDP-01-DWG-0320 | 3 OF 4 | 2017-01-25 | 2018-03-21 | 2018-03-26 | 5 | B | MKM | [45 empty] | 2018-03-21 | 2018-03-26 | 5 | B | Rev-0 | B | Approved
223 | SD-0096-02 |  | 19th to 23rd Floor | 19th to 23rd Floor @ Dresser / Work Desk Type-7 Junior Suite Type-2 | 1252-MKM-05Q-IDP-01-DWG-0326 | 1 OF 2 | 2017-02-02 | 2018-03-21 | 2018-03-26 | 5 | B | MKM | 2018-06-17 | 2018-07-24 | 37 | C | MKM | 2018-07-31 | 2018-08-06 | 6 | B | MKM | [35 empty] | 2018-07-31 | 2018-08-06 | 6 | B | Rev-2 | B | Approved
224 | SD-0096-00 |  | 19th to 23rd Floor | 19th to 23rd Floor @ Dresser / Work Desk Type-7 Details Junior Suite Type-2 | 1252-MKM-05Q-IDP-01-DWG-0326 | 2 OF 2 |  | 2018-03-21 | 2018-03-26 | 5 | B | MKM | [45 empty] | 2018-03-21 | 2018-03-26 | 5 | B | Rev-0 | B | Approved
225 | SD-0096-01 |  | 19th to 23rd Floor | 19th to 23rd Floor Junior Suite Type-1 Work Desk Details 4A & 4B | 1252-MKM-05Q-IDP-01-DWG-0327 | 1 OF 1 | 2017-02-02 | 2018-03-21 | 2018-03-26 | 5 | B | MKM | 2018-06-17 | 2018-07-24 | 37 | C | MKM | [40 empty] | 2018-06-17 | 2018-07-24 | 37 | C | Rev-1
TV WALL UNIT | [62 empty] | X |  |  |  | 1 160
226 | SD-0027-04 |  | 8 | TV Wall unit Schedule | 1252-MKM-05Q-IDP-01-DWG-0330 | 1 OF 2 | 2017-01-25 | 2017-01-29 | 2017-02-07 | 9 | SS | MKM | [45 empty] | 2017-01-29 | 2017-02-07 | 9 | SS | Rev-0 | X |  |  |  | 1 5 | MKM
227 | SD-0027-00 |  | 8 | TV Wall unit Schedule | 1252-MKM-05Q-IDP-01-DWG-0330 | 2 OF 2 | 2017-01-25 | 2017-01-29 | 2017-02-07 | 9 | SS | MKM | [45 empty] | 2017-01-29 | 2017-02-07 | 9 | SS | Rev-0 | X |  |  |  | 1 5 | MKM
228 | SD-0027-02 |  | 8 | TV Wall unit Type - 1 | 1252-MKM-05Q-IDP-01-DWG-0331 | 1 OF 1 | 2017-01-22 | 2017-01-29 | 2017-02-07 | 9 | B | MKM | 2017-09-05 | 2017-09-07 | 2 | B | MKM | 2017-11-13 | 2017-11-14 | 1 | SS | MKM | [35 empty] | 2017-11-13 | 2017-11-14 | 1 | SS | Rev-2 | B | Approved |  |  | 1 5 | MKM
229 | SD-0027-03 |  |  | TV Wall unit Type - 2, 2A, 2B & 2C | 1252-MKM-05Q-IDP-01-DWG-0332 | 1 OF 1 | 2017-01-25 | 2017-01-29 | 2017-02-07 | 9 | B | MKM | [45 empty] | 2017-01-29 | 2017-02-07 | 9 | B | Rev-0 | X
230 | SD-0002-02 |  |  | TV Wall unit Type - 3, 3A & 3B | 1252-MKM-05Q-IDP-01-DWG-0333 | 1 OF 3 | 2017-01-17 | 2017-01-17 | 2017-02-08 | 22 | B | MKM | 2017-06-19 | 2017-06-20 | 1 | SS | MKM | [40 empty] | 2017-06-19 | 2017-06-20 | 1 | SS | Rev-1 | B | Approved
231 | SD-0002-02 |  |  | 9th to 13th Floor Studio Type-A TV Unit & Dressing Table (Type-3A) Detail Drawing | 1252-MKM-05Q-IDP-01-DWG-0333 | 2 OF 3 |  | 2017-06-19 | 2017-06-20 | 1 | B | MKM | [45 empty] | 2017-06-19 | 2017-06-20 | 1 | B | Rev-0 | B | Approved
232 | SD-0002-02 |  |  | 14th to 17th Floor Studio Type-A TV Unit & Dressing Table (Type-3B) Detail Drawing | 1252-MKM-05Q-IDP-01-DWG-0333 | 3 OF 3 |  | 2017-06-19 | 2017-06-20 | 1 | B | MKM | [45 empty] | 2017-06-19 | 2017-06-20 | 1 | B | Rev-0 | B | Approved
233 | SD-0027-00 |  |  | TV Wall unit Type - 4 & 4A | 1252-MKM-05Q-IDP-01-DWG-0334 | 1 OF 1 | 2017-01-25 | 2017-01-29 | 2017-02-07 | 9 | B | MKM | [45 empty] | 2017-01-29 | 2017-02-07 | 9 | B | Rev-0 | B | Approved
234 | SD-0040-03 |  | 8th - 17th | 8th to 17th Floor 1BR, 2BR & 3BR Apartments TV Shelf Details | 1252-MKM-05Q-IDP-01-DWG-0335 | 1 OF 3 |  | 2017-02-09 | 2017-02-19 | 10 | C | MKM | 2017-05-10 | 2017-05-23 | 13 | B | MKM | 2018-07-03 | 2018-07-09 | 6 | C | MKM | 2018-07-24 | 2018-08-05 | 12 | B | MKM | [30 empty] | 2018-07-24 | 2018-08-05 | 12 | B | Rev-3 | X
235 | SD-0040-03 |  | 19th - 41st | 19th to 41st Floor Junior Suites & Guest Rooms TV Shelf Details | 1252-MKM-05Q-IDP-01-DWG-0335 | 2 OF 3 |  | 2018-07-03 | 2018-07-09 | 6 | C | MKM | 2018-07-24 | 2018-08-05 | 12 | B | MKM | [40 empty] | 2018-07-24 | 2018-08-05 | 12 | B | Rev-1 | X
236 | SD-0040-03 |  | 19th - 41st | 19th to 41st Floor Junior Suites & Guest Rooms TV Shelf Details | 1252-MKM-05Q-IDP-01-DWG-0335 | 3 OF 3 |  | 2018-07-24 | 2018-08-05 | 12 | B | MKM | [45 empty] | 2018-07-24 | 2018-08-05 | 12 | B | Rev-0 | X
237 | SD-0044-01 |  |  | 19th to 23rd Floor Side Board Unit Detail @ Guestrooms 1 Bedroom Suite type B (G1BB) | 1252-MKM-05Q-IDP-01-DWG-0336 | 1 OF 1 |  | 2017-02-09 | 2017-02-19 | 10 | B | MKM | 2017-03-06 | 2017-03-13 | 7 | SS | MKM | [40 empty] | 2017-03-06 | 2017-03-13 | 7 | SS | Rev-1 | B | Approved
238 | SD-0055-00 |  | 8th-17th | 8th to 17th Floor 2 & 3 Bedroom Apartment Laundry Room Cabinet Details (Type-1) | 1252-MKM-05Q-IDP-01-DWG-0337 | 1 OF 1 |  | 2017-03-01 | 2017-03-08 | 7 | B | MKM | [45 empty] | 2017-03-01 | 2017-03-08 | 7 | B | Rev-0 | B | Approved
239 | SD-0055-00 |  | 8th-17th | 8th to 17th Floor Studio - A & B & 1 Bedroom Apartment Laundry Room Cabinet Details (Type-2) | 1252-MKM-05Q-IDP-01-DWG-0338 | 1 OF 1 |  | 2017-03-01 | 2017-03-08 | 7 | B | MKM | [45 empty] | 2017-03-01 | 2017-03-08 | 7 | B | Rev-0 | X
240 | SD-0075-00 |  |  | TV unit details -Type -1 @ Master Bedroom | 1252-MKM-05Q-IDP-01-DWG-0339 | 1 OF 1 |  | 2018-01-08 | 2018-01-08 | 0 | SS | MKM | [45 empty] | 2018-01-08 | 2018-01-08 | 0 | SS | Rev-0
TV WALL UNIT | [62 empty] | B | Approved |  |  | 1 160
241 | SD-0089-00 |  | 8th to 17th Floor | 8th to 17th Floor Apartments TV Unit Schedule | 1252-MKM-05Q-IDP-01-DWG-0330 | 1 OF 2 | 2017-01-25 | 2018-03-06 | 2018-03-12 | 6 | B | MKM | [45 empty] | 2018-03-06 | 2018-03-12 | 6 | B | Rev-0 | B | Approved |  |  | 1 5 | MKM
242 | SD-0089-03 |  | 8th to 17th Floor | 8th to 17th Floor Apartments TV Unit (Type-3) Detail | 1252-MKM-05Q-IDP-01-DWG-0333 | 1 OF 1 | 2017-01-17 | 2018-03-06 | 2018-03-12 | 6 | C | MKM | 2018-03-18 | 2018-03-20 | 2 | B | MKM | 2018-07-09 | 2018-07-16 | 7 | B | MKM | [35 empty] | 2018-07-09 | 2018-07-16 | 7 | B | Rev-2 | B | Approved
243 | SD-0089-02 |  | 8th to 17th Floor | Mock Up Apartment - 901 TV Unit Type-01 & Dresser Table Details (Modified) | 1252-MKM-05Q-IDP-01-DWG-0339 | 1 OF 1 |  | 2018-03-06 | 2018-03-12 | 6 | B | MKM | 2018-05-03 | 2018-06-27 | 55 | B | MKM | [40 empty] | 2018-05-03 | 2018-06-27 | 55 | B | Rev-1 | B | Approved
244 | SD-0089-00 |  | 8th to 17th Floor | 8th to 17th Floor Apartments TV Unit Type -2 & 2A Detail | 1252-MKM-05Q-IDP-01-DWG-0384 | 1 OF 2 |  | 2018-03-06 | 2018-03-12 | 6 | B | MKM | [45 empty] | 2018-03-06 | 2018-03-12 | 6 | B | Rev-0 | B | Approved |  |  | 1 5 | MKM
245 | SD-0089-00 |  | 8th to 17th Floor | 8th to 17th Floor Apartments TV Unit Type -2 & 2A Detail | 1252-MKM-05Q-IDP-01-DWG-0384 | 2 OF 2 |  | 2018-03-06 | 2018-03-12 | 6 | B | MKM | [45 empty] | 2018-03-06 | 2018-03-12 |  | B | Rev-0 | P |  |  |  | 1 5 | MKM
246 | SD-0095-00 |  | 19th to 23rd Floor | TV Wall unit Schedule | 1252-MKM-05Q-IDP-01-DWG-0330 | 2 OF 2 | 2017-01-25 | 2018-03-22 | 2018-04-02 | 11 | C | MKM |  |  |  | SS | AS PER HASSAN | [40 empty] | 2018-03-22 | 2018-04-02 | 11 | SS | Rev-0 | P |  |  |  | 1 5 | AS PER HASSAN
247 | SD-0095-01 |  | 19th to 23rd Floor | (19th to 23rd Floor) TV Wall Unit Type - 1 Detail | 1252-MKM-05Q-IDP-01-DWG-0331 | 1 OF 1 | 2017-01-22 | 2018-03-22 | 2018-04-02 | 11 | B | MKM | 2018-06-17 | 2018-06-24 | 7 | B | MKM | [40 empty] | 2018-06-17 | 2018-06-24 | 7 | B | Rev-1 | P |  |  |  | 1 5 | MKM
248 | SD-0095-03 |  | 19th to 21st Floor | 19th to 21st Floor Junior Suite – (Type 1) Dining Unit (Type-1) Details | 1252-MKM-05Q-IDP-01-DWG-0336 | 1 OF 3 |  | 2018-03-22 | 2018-04-02 | 11 | C | MKM | 2018-06-17 | 2018-06-24 | 7 | C | MKM | 2018-07-05 | 2018-07-11 | 6 | C | MKM | 2018-07-17 | 2018-07-24 | 7 | B | MKM | [30 empty] | 2018-07-17 | 2018-07-24 | 7 | B | Rev-3 | P
249 | SD-0095-03 |  | 19th to 23rd Floor | 22nd to 23rd Floor Junior Suite – (Type 1A) Dining Unit (Type-1A) Details | 1252-MKM-05Q-IDP-01-DWG-0336 | 2 OF 3 |  | 2018-07-05 | 2018-07-11 | 6 | C | MKM | 2018-07-17 | 2018-07-24 | 7 | B | MKM | [40 empty] | 2018-07-17 | 2018-07-24 | 7 | B | Rev-1 | P
250 | SD-0095-03 |  | 19th to 23rd Floor | 19th to 23rd Floor Junior Suite – (Type 2 & 3) Dining Unit (Type-2) Details | 1252-MKM-05Q-IDP-01-DWG-0336 | 3 OF 3 |  | 2018-03-22 | 2018-04-02 | 11 | B | MKM | 2018-06-17 | 2018-06-24 | 7 | C | MKM | 2018-07-05 | 2018-07-11 | 6 | C | MKM | 2018-07-17 | 2018-07-24 | 7 | B | MKM | [30 empty] | 2018-07-17 | 2018-07-24 | 7 | B | Rev-3 | 0
HEADBOARD DETAILS | [62 empty] | X |  |  |  | 1 160
251 | SD-0002-04 |  |  | Headboard details - Type-01 | 1252-MKM-05Q-IDP-01-DWG-0340 | 1 OF 1 | 2017-01-17 | 2017-01-17 | 2017-02-08 | 22 | B | MKM | 2018-01-04 | 2018-01-07 | 3 | SS | MKM | [40 empty] | 2018-01-04 | 2018-01-07 | 3 | SS | Rev-1 |  |  |  |  | 1 5 | MKM
252 | SD-0032-10 |  | 8th | 8th Floor 2 & 3 Bedroom Apartments Secondary Twin Bed_Headboard Type-02 (SWA-326) Details | 1252-MKM-05Q-IDP-01-DWG-0341 | 1 OF 1 | 2017-02-12 | 2017-02-06 | 2017-02-19 | 13 | C | MKM | 2017-03-15 | 2017-03-30 | 15 | A | MKM | 2018-06-19 | 2018-06-27 | 8 | C | MKM | 2018-07-11 | 2018-07-16 | 5 | B | MKM | [30 empty] | 2018-07-11 | 2018-07-16 | 5 | B | Rev-3 | X
253 | SD-0032-06 |  |  | Headboard details - Type-03 | 1252-MKM-05Q-IDP-01-DWG-0342 | 1 OF 1 | 2017-02-12 | 2017-02-06 | 2017-02-19 | 13 | B | MKM | 2018-01-08 | 2018-01-09 | 1 | SS | MKM | [40 empty] | 2018-01-08 | 2018-01-09 | 1 | SS | Rev-1
254 | SD-0032-10 |  | 9th - 17th | 9th to 17th Floor 2 Bedroom Apartments Secondary Twin Bed_Headboard Type-04 (SWA-326) Details | 1252-MKM-05Q-IDP-01-DWG-0343 | 1 OF 1 | 2017-02-12 | 2017-02-06 | 2017-02-19 | 13 | B | MKM | 2018-06-19 | 2018-06-27 | 8 | C | MKM | 2018-07-11 | 2018-07-16 | 5 | B | MKM | [35 empty] | 2018-07-11 | 2018-07-16 | 5 | B | Rev-2 | X
255 | SD-0032-03 |  |  | Headboard details - Type-05 | 1252-MKM-05Q-IDP-01-DWG-0344 | 1 OF 2 | 2017-02-12 | 2017-02-06 | 2017-02-19 | 13 | D | MKM | 2017-03-15 | 2017-03-30 | 15 | C | MKM | 2017-04-26 | 2017-05-02 | 6 | C | MKM | 2017-05-13 | 2017-05-21 | 8 | SS | MKM | [30 empty] | 2017-05-13 | 2017-05-21 | 8 | SS | Rev-3 | X
256 | SD-0032-03 |  |  | Headboard details - Type-05 | 1252-MKM-05Q-IDP-01-DWG-0344 | 2 OF 2 | 2017-02-12 | 2017-02-06 | 2017-02-19 | 13 | D | MKM | 2017-03-15 | 2017-03-30 | 15 | C | MKM | 2017-04-26 | 2017-05-02 | 6 | B | MKM | 2017-05-13 | 2017-05-21 | 8 | SS | MKM | [30 empty] | 2017-05-13 | 2017-05-21 | 8 | SS | Rev-3 | B | Approved
257 | SD-0032-11 | ARK-0043-00 | 24th-41st | 24th to 41st Floor Disabled King Room & STD King Room Head Board Type -1 Detail | 1252-MKM-05Q-IDP-01-DWG-0345 | 1 OF 2 | 2017-02-12 | 2017-02-06 | 2017-02-19 | 13 | B | MKM | 2018-01-30 | 2018-02-01 | 2 | B | MKM | 2018-06-17 | 2018-06-24 | 7 | B | MKM | 2018-11-27 | 2018-12-10 | 13 | B | MKM | [30 empty] | 2018-11-27 | 2018-12-10 | 13 | B | Rev-3 | B | Approved
258 | SD-0032-11 | ARK-0043-00 | 24th-41st | 24th to 41st Floor Disabled King Room & STD King Room Head Board Type -1 Detail | 1252-MKM-05Q-IDP-01-DWG-0345 | 2 OF 2 | 2017-02-12 | 2017-02-06 | 2017-02-19 | 13 | B | MKM | 2018-01-30 | 2018-02-01 | 2 | B | MKM | 2018-06-17 | 2018-06-24 | 7 | B | MKM | 2018-11-27 | 2018-12-10 | 13 | B | MKM | [30 empty] | 2018-11-27 | 2018-12-10 | 13 | B | Rev-3 | P
259 | SD-0032-12 | ARK-0043-00 | 24th-41st | Level 24 to 41 STD Twin Room Head Board Details Type-2 | 1252-MKM-05Q-IDP-01-DWG-0346 | 1 OF 2 | 2017-02-12 | 2017-02-06 | 2017-02-19 | 13 | B | MKM | 2018-03-29 | 2018-04-02 | 4 | B | MKM | 2018-06-17 | 2018-06-24 | 7 | C | MKM | 2018-06-27 | 2018-07-03 | 6 | B | MKM | 2018-11-27 | 2018-12-10 | 13 | C | MKM | 2018-12-23 | 2019-01-03 | 11 | B | MKM | [20 empty] | 2018-12-23 | 2019-01-03 | 11 | B | Rev-5 | P
260 | SD-0032-12 | ARK-0043-00 | 24th-41st | Level 24 to 41 STD Twin Room Head Board Details Type-2 | 1252-MKM-05Q-IDP-01-DWG-0346 | 2 OF 2 | 2017-02-12 | 2017-02-06 | 2017-02-19 | 13 | B | MKM | 2018-03-29 | 2018-04-02 | 4 | B | MKM | 2018-06-17 | 2018-06-24 | 7 | C | MKM | 2018-06-27 | 2018-07-03 | 6 | B | MKM | 2018-11-27 | 2018-12-10 | 13 | C | MKM | 2018-12-23 | 2019-01-03 | 11 | B | MKM | [20 empty] | 2018-12-23 | 2019-01-03 | 11 | B | Rev-5 | X
261 | SD-0075-00 |  |  | Headboard details - Type-02 @ King Headboard | 1252-MKM-05Q-IDP-01-DWG-0347 | 1 OF 1 |  | 2018-01-08 | 2018-01-08 | 0 | SS | MKM | [45 empty] | 2018-01-08 | 2018-01-08 | 0 | SS | Rev-0 | X
262 | SD-0033-00 |  |  | Headboard Schedule | 1252-MKM-05Q-IDP-01-DWG-0349 | 1 OF 3 | 2017-02-12 | 2017-02-06 | 2017-02-16 | 10 | SS | MKM | [45 empty] | 2017-02-06 | 2017-02-16 | 10 | SS | Rev-0 | X
263 | SD-0033-00 |  |  | Headboard Schedule | 1252-MKM-05Q-IDP-01-DWG-0349 | 2 OF 3 | 2017-02-12 | 2017-02-06 | 2017-02-16 | 10 | SS | MKM | [45 empty] | 2017-02-06 | 2017-02-16 | 10 | SS | Rev-0 | A/C | Resub..reqd | 2018-04-05
264 | SD-0033-00 |  | 31st - 41st | 31st to 41st Floor Headboard Schedule | 1252-MKM-05Q-IDP-01-DWG-0349 | 3 OF 3 | 2017-02-12 | 2017-02-06 | 2017-02-16 | 10 | A | MKM | [45 empty] | 2017-02-06 | 2017-02-16 | 10 | A | Rev-0
HEADBOARD DETAILS | [62 empty] | B | Approved |  |  | 1 160
265 | SD-0088-02 |  | 8th to 17th Floor | 8th to 17th Floor Apartments 1BR, 2BR & 3BR Master Bedroom Head Board (SWA-309C) Details | 1252-MKM-05Q-IDP-01-DWG-0340 | 1 OF 2 | 2017-01-17 | 2018-03-06 | 2018-03-12 | 6 | B | MKM | 2018-06-21 | 2018-06-27 | 6 | B | MKM | [40 empty] | 2018-06-21 | 2018-06-27 | 6 | B | Rev-1 | B | Approved |  |  | 1 5 | MKM
266 | SD-0088-03 |  | 8th to 17th Floor | 8th to 17th Floor_3 Bedroom Apartments, Secondary King Bed_Headboard & Side Table Type-01 (SWA-318) Details | 1252-MKM-05Q-IDP-01-DWG-0340 | 2 OF 2 | 2017-01-17 | 2018-03-06 | 2018-03-12 | 6 | B | MKM | 2018-06-19 | 2018-06-27 | 8 | C | MKM | 2018-07-11 | 2018-07-16 | 5 | B | MKM | [35 empty] | 2018-07-11 | 2018-07-16 | 5 | B | Rev-2 | B | Approved |  |  | 1 5 | MKM
267 | SD-0088-03 |  | 9th to 17th Floor | 9th to 17th Floor 3 Bedroom Apartments Secondary Twin Bed_Headboard Type-03 (SWA-326) Details | 1252-MKM-05Q-IDP-01-DWG-0342 | 1 OF 1 | 2017-02-12 | 2018-03-06 | 2018-03-12 | 6 | B | MKM | 2018-06-19 | 2018-06-27 | 8 | C | MKM | 2018-07-11 | 2018-07-16 | 5 | B | MKM | [35 empty] | 2018-07-11 | 2018-07-16 | 5 | B | Rev-2 | B | Approved
268 | SD-0088-00 |  | 8th to 17th Floor | 8th to 17th Floor Apartments King Headboard Type-02 Details | 1252-MKM-05Q-IDP-01-DWG-0347 | 1 OF 1 |  | 2018-03-06 | 2018-03-12 | 6 | B | MKM | [45 empty] | 2018-03-06 | 2018-03-12 | 6 | B | Rev-0 | B | Approved
269 | SD-0088-00 |  | 8th to 17th | 8th to 17th Floor Apartments Headboard Schedule | 1252-MKM-05Q-IDP-01-DWG-0349 | 1 OF 3 | 2017-02-12 | 2018-03-06 | 2018-03-12 | 6 | B | MKM | [45 empty] | 2018-03-06 | 2018-03-12 | 6 | B | Rev-0 | B | Approved
270 | SD-0094-00 |  | 19th to 23rd | 19th to 23rd Floor Junior Suites Headboard & Bed Side Table Schedule | 1252-MKM-05Q-IDP-01-DWG-0349 | 2 OF 3 | 2017-02-12 | 2018-03-20 | 2018-03-26 | 6 | B | MKM | [45 empty] | 2018-03-20 | 2018-03-26 | 6 | B | Rev-0 | B | Approved
271 | SD-0094-01 | ARK-0047-00 | 19th to 23rd | 19th to 23rd Floor Junior Suites Head Board Type-1A Detail | 1252-MKM-05Q-IDP-01-DWG-0344 | 1 OF 2 | 2017-02-12 | 2018-03-20 | 2018-03-26 | 6 | B | MKM | 2018-06-17 | 2018-06-24 | 7 | B | MKM | 2018-12-31 | 2019-01-09 | 9 | B | MKM | [35 empty] | 2018-12-31 | 2019-01-09 | 9 | B | Rev-2 | B | Approved
272 | SD-0094-01 | ARK-0047-00 | 19th to 23rd | 19th to 23rd Floor Junior Suites Head Board Type-1A Detail | 1252-MKM-05Q-IDP-01-DWG-0344 | 2 OF 2 | 2017-02-12 | 2018-03-20 | 2018-03-26 | 6 | B | MKM | 2018-06-17 | 2018-06-24 | 7 | B | MKM | 2018-12-31 | 2019-01-09 | 9 | B | MKM | [35 empty] | 2018-12-31 | 2019-01-09 | 9 | B | Rev-2 | B | Approved
273 | SD-0094-01 |  | 19th to 41st | 19th to 41st Floor Typical Bed Side Table Details | 1252-MKM-05Q-IDP-01-DWG-0389 | 1 OF 1 |  | 2018-03-20 | 2018-03-26 | 6 | B | MKM | 2018-06-17 | 2018-06-24 | 7 | B | MKM | [40 empty] | 2018-06-17 | 2018-06-24 | 7 | B | Rev-1 |  |  |  |  | 1 5 | MKM
274 | SD-0088-02 |  | 8th to 17th Floor | 8th to 17th Floor Apartments Studio-A Master Bedroom Head Board (SWA-309A) Details | 1252-MKM-05Q-IDP-01-DWG-0395 | 1 OF 2 | 2017-01-17 | 2018-06-21 | 2018-06-27 | 6 | B | MKM | [45 empty] | 2018-06-21 | 2018-06-27 | 6 | B | Rev-0 | B | Approved |  |  | 1 5 | MKM
275 | SD-0088-02 |  | 8th to 17th Floor | 8th to 17th Floor Apartments Studio-B Master Bedroom Head Board (SWA-309B) Details | 1252-MKM-05Q-IDP-01-DWG-0395 | 2 OF 2 | 2017-01-17 | 2018-06-21 | 2018-06-27 | 6 | B | MKM | [45 empty] | 2018-06-21 | 2018-06-27 | 6 | B | Rev-0 | B | Approved |  |  | 1 5 | MKM
WARDROBE DETAILS | [62 empty] | A | Approved |  |  | 1 160
276 | SD-0020-00 |  | 8th - 17th | 8th Floor to 17th Floor Wardrobe Location Layout | 1252-MKM-05Q-IDP-01-DWG-0350 | 1 OF 3 | 2017-01-22 | 2017-01-22 | 2017-02-14 | 23 | A | MKM | [45 empty] | 2017-01-22 | 2017-02-14 | 23 | A | Rev-0 | A | Approved |  |  | 1 5 | MKM
277 | SD-0041-00 |  | 19th - 30th | 19th to 30th Floor Wardrobe Schedule | 1252-MKM-05Q-IDP-01-DWG-0350 | 2 OF 3 | 2017-02-13 | 2017-02-09 | 2017-02-23 | 14 | A | MKM | [45 empty] | 2017-02-09 | 2017-02-23 | 14 | A | Rev-0 | A | Approved |  |  | 1 5 | MKM
278 | SD-0041-00 |  | 31st - 41st | 31st to 41st Floor Wardrobe Schedule | 1252-MKM-05Q-IDP-01-DWG-0350 | 3 OF 3 | 2017-02-13 | 2017-02-09 | 2017-02-23 | 14 | A | MKM | [45 empty] | 2017-02-09 | 2017-02-23 | 14 | A | Rev-0 | A | Approved |  |  | 1 5 | MKM
279 | SD-0041-07 | ARK-0048-02 | 19th - 41st | 19th to 41st Floor Wardrobe Type-1 Detailed Drawing | 1252-MKM-05Q-IDP-01-DWG-0351 | 1 OF 4 | 2017-02-13 | 2017-02-09 | 2017-02-23 | 14 | C | MKM | 2017-03-28 | 2017-04-02 | 5 | B | MKM | 2017-12-21 | 2018-01-21 | 31 | C | MKM | 2018-01-30 | 2018-02-06 | 7 | A | MKM | 2019-02-06 | 2019-02-27 | 21 | C | MKM | 2019-03-05 | 2019-03-21 | 16 | A | MKM | [20 empty] | 2019-03-05 | 2019-03-21 | 16 | A | Rev-5 | A | Approved |  |  | 1 5 | MKM
280 | SD-0041-07 | ARK-0048-02 | 19th - 41st | 19th to 41st Floor Wardrobe Type-1 Detailed Drawing | 1252-MKM-05Q-IDP-01-DWG-0351 | 2 OF 4 | 2017-02-13 | 2017-02-09 | 2017-02-23 | 14 | C | MKM | 2017-03-28 | 2017-04-02 | 5 | B | MKM | 2017-12-21 | 2018-01-21 | 31 | C | MKM | 2018-01-30 | 2018-02-06 | 7 | C | MKM | 2018-02-21 | 2018-02-22 | 1 | A | MKM | 2019-02-06 | 2019-02-27 | 21 | C | MKM | 2019-03-05 | 2019-03-21 | 16 | A | MKM | [15 empty] | 2019-03-05 | 2019-03-21 | 16 | A | Rev-6 | A | Approved |  |  | 1 5 | MKM
281 | SD-0041-06 | ARK-0048-01 | 24th - 41st | 24th to 41st Floor Wardrobe Type-2 Detailed Drawing | 1252-MKM-05Q-IDP-01-DWG-0351 | 3 OF 4 |  | 2017-03-28 | 2017-04-02 | 5 | A | MKM | 2017-12-21 | 2018-01-21 | 31 | C | MKM | 2018-01-30 | 2018-02-06 | 7 | A | MKM | 2019-02-06 |  | 201 | OD | MKM | 2019-02-10 | 2019-03-21 | 39 | C | MKM | [25 empty] | 2019-02-10 | 2019-03-21 | 39 | C | Rev-4 | A | Approved
282 | SD-0041-06 | ARK-0048-01 | 19th - 41st | 24th to 41st Floor Wardrobe Type-2 Detailed Drawing | 1252-MKM-05Q-IDP-01-DWG-0351 | 4 OF 4 |  | 2017-03-28 | 2017-04-02 | 5 | B | MKM | 2017-12-21 | 2018-01-21 | 31 | C | MKM | 2018-01-30 | 2018-02-06 | 7 | C | MKM | 2018-02-21 | 2018-02-22 | 1 | A | MKM | 2019-02-06 |  | 201 | OD | MKM | 2019-02-10 | 2019-03-21 | 39 | C | MKM | [20 empty] | 2019-02-10 | 2019-03-21 | 39 | C | Rev-5 | A | Approved
283 | SD-0041-08 | ARK-0048-03 | 19th - 41st | 19th to 41st Floor Wardrobe Type-3 Detailed Drawing | 1252-MKM-05Q-IDP-01-DWG-0352 | 1 OF 2 | 2017-02-13 | 2017-02-09 | 2017-02-23 | 14 | D | MKM | 2017-03-28 | 2017-04-02 | 5 | A | MKM | 2017-12-21 | 2018-01-21 | 31 | C | MKM | 2018-01-30 | 2018-02-06 | 7 | A | MKM | 2019-02-06 | 2019-02-27 | 21 | C | MKM | 2019-03-07 | 2019-03-21 | 14 | B | MKM | [20 empty] | 2019-03-07 | 2019-03-21 | 14 | B | Rev-5 | A | Approved |  |  | 1 5 | MKM
284 | SD-0041-08 | ARK-0048-03 | 19th - 41st | 19th to 41st Floor Wardrobe Type-3 Detailed Drawing | 1252-MKM-05Q-IDP-01-DWG-0352 | 2 OF 2 | 2017-02-13 | 2017-02-09 | 2017-02-23 | 14 | B | MKM | 2017-03-28 | 2017-04-02 | 5 | B | MKM | 2017-12-21 | 2018-01-21 | 31 | C | MKM | 2018-01-30 | 2018-02-06 | 7 | C | MKM | 2018-02-21 | 2018-02-22 | 1 | A | MKM | 2019-02-06 | 2019-02-27 | 21 | C | MKM | 2019-03-07 | 2019-03-21 | 14 | B | MKM | [15 empty] | 2019-03-07 | 2019-03-21 | 14 | B | Rev-6 | A | Approved |  |  | 1 5 | MKM
285 | SD-0041-01 |  | 19th - 23rd | 19th to 23rd Floor Wardrobe Type-4 Detailed Drawing | 1252-MKM-05Q-IDP-01-DWG-0353 | 1 OF 1 | 2017-02-13 | 2017-02-09 | 2017-02-23 | 14 | D | MKM | 2017-03-28 | 2017-04-02 | 5 | A | MKM | [40 empty] | 2017-03-28 | 2017-04-02 | 5 | A | Rev-1 | A | Approved
286 | SD-0041-01 |  | 19th - 23rd | 19th to 23rd Floor Wardrobe Type-5 Detailed Drawing | 1252-MKM-05Q-IDP-01-DWG-0354 | 1 OF 1 | 2017-02-13 | 2017-02-09 | 2017-02-23 | 14 | D | MKM | 2017-03-28 | 2017-04-02 | 5 | A | MKM | [40 empty] | 2017-03-28 | 2017-04-02 | 5 | A | Rev-1 | B | Approved
287 | SD-0002-01 |  | 8 | Wardrobe Type-6 Detailed Drawing | 1252-MKM-05Q-IDP-01-DWG-0355 | 1 OF 1 | 2017-01-17 | 2017-01-17 | 2017-02-08 |  | B | MKM | [45 empty] | 2017-01-17 | 2017-02-08 |  | B | Rev-0 | B | Approved
288 | SD-0002-04 | ARK-0041-00 | 8 | Wardrobe Type-7 Detailed Drawing | 1252-MKM-05Q-IDP-01-DWG-0356 | 1 OF 1 | 2017-01-17 | 2017-01-17 | 2017-02-08 | 22 | B | MKM | 2018-11-27 | 2018-12-15 | 18 | B | MKM | [40 empty] | 2018-11-27 | 2018-12-15 | 18 | B | Rev-1 | A | Approved
289 | SD-0020-01 |  | 8th-17th | 8th - 17th Floor Wardrobe Type - 08 & 09 Detailed Drawing | 1252-MKM-05Q-IDP-01-DWG-0357 | 1 OF 2 | 2017-01-22 | 2017-01-22 | 2017-02-14 | 23 | C | MKM | 2017-03-16 | 2017-03-30 | 14 | A | MKM | [40 empty] | 2017-03-16 | 2017-03-30 | 14 | A | Rev-1 | A | Approved
290 | SD-0020-02 | ARK-0042-00 | 8th-17th | 8th - 17th Floor Wardrobe Type - 08 & 09 Detailed Drawing | 1252-MKM-05Q-IDP-01-DWG-0357 | 2 OF 2 |  | 2017-03-16 | 2017-03-30 | 14 | A | MKM | 2018-11-27 | 2018-12-10 | 13 | B | MKM | [40 empty] | 2018-11-27 | 2018-12-10 | 13 | B | Rev-1 | A | Approved
291 | SD-0020-02 | ARK-0042-00 | 8th-17th | 8th - 17th Floor Wardrobe Type - 10 Detailed Drawing | 1252-MKM-05Q-IDP-01-DWG-0358 | 1 OF 1 | 2017-01-22 | 2017-01-22 | 2017-02-14 | 23 | C | MKM | 2017-03-16 | 2017-03-30 | 14 | A | MKM | 2018-11-27 | 2018-12-10 | 13 | B | MKM | [35 empty] | 2018-11-27 | 2018-12-10 | 13 | B | Rev-2 | A | Approved
292 | SD-0020-01 |  | 8th-17th | 8th - 17th Floor Wardrobe Type - 11 & 12 Detailed Drawing | 1252-MKM-05Q-IDP-01-DWG-0359 | 1 OF 2 | 2017-01-22 | 2017-01-22 | 2017-02-14 | 23 | B | MKM | 2017-03-16 | 2017-03-30 | 14 | A | MKM | [40 empty] | 2017-03-16 | 2017-03-30 | 14 | A | Rev-1 | A | Approved
293 | SD-0020-01 |  | 8th-17th | 8th - 17th Floor Wardrobe Type - 11 & 12 Detailed Drawing | 1252-MKM-05Q-IDP-01-DWG-0359 | 2 OF 2 |  | 2017-03-16 | 2017-03-30 | 14 | A | MKM | [45 empty] | 2017-03-16 | 2017-03-30 | 14 | A | Rev-0
GENERAL DETAILS | [62 empty] | B | Approved |  |  | 1 160
294 | SD-0029-00 |  | 8th-17th | Vanity Counter Schedule Apartments 8th - 17th | 1252-MKM-05Q-IDP-01-DWG-0360 | 1 OF 3 | 2017-01-24 | 2017-02-01 | 2017-02-19 | 18 | B | MKM | [45 empty] | 2017-02-01 | 2017-02-19 | 18 | B | Rev-0 | B | Approved |  |  | 1 5 | MKM
295 | SD-0029-00 |  | 19th-30th | Vanity Counter Schedule 19-23 Junior Suites 24-30 STD Rooms | 1252-MKM-05Q-IDP-01-DWG-0360 | 2 OF 3 | 2017-01-24 | 2017-02-01 | 2017-02-19 | 18 | B | MKM | [45 empty] | 2017-02-01 | 2017-02-19 | 18 | B | Rev-0 | B | Approved |  |  | 1 5 | MKM
296 | SD-0029-00 |  | 31st-41st | Vanity Counter Schedule STD & Executive Rooms (31-41) | 1252-MKM-05Q-IDP-01-DWG-0360 | 3 OF 3 | 2017-01-24 | 2017-02-01 | 2017-02-19 | 18 | B | MKM | [45 empty] | 2017-02-01 | 2017-02-19 | 18 | B | Rev-0 | B | Approved |  |  | 1 5 | MKM
297 | SD-0026-00 |  |  | Vanity Counter Detail Type - 01 & 01A 8th to 41st Floor | 1252-MKM-05Q-IDP-01-DWG-0361 | 1 OF 1 | 2017-01-24 | 2017-01-29 | 2017-02-19 | 21 | B | MKM | [45 empty] | 2017-01-29 | 2017-02-19 | 21 | B | Rev-0 | B | Approved |  |  | 1 5 | MKM
298 | SD-0026-00 |  |  | Vanity Counter Detail Type - 02 8th to 17th Floor | 1252-MKM-05Q-IDP-01-DWG-0362 | 1 OF 1 | 2017-01-24 | 2017-01-29 | 2017-02-19 | 21 | B | MKM | [45 empty] | 2017-01-29 | 2017-02-19 | 21 | B | Rev-0 | B | Approved |  |  | 1 5 | MKM
299 | SD-0026-00 |  |  | Vanity Counter Detail Type - 02A 24th to 29th Floor | 1252-MKM-05Q-IDP-01-DWG-0363 | 1 OF 1 | 2017-01-24 | 2017-01-29 | 2017-02-19 | 21 | B | MKM | [45 empty] | 2017-01-29 | 2017-02-19 | 21 | B | Rev-0 | B | Approved |  |  | 1 5 | MKM
300 | SD-0026-00 |  |  | Vanity Counter Detail Type - 03 8th to 17th Floor | 1252-MKM-05Q-IDP-01-DWG-0364 | 1 OF 1 | 2017-01-24 | 2017-01-29 | 2017-02-19 | 21 | B | MKM | [45 empty] | 2017-01-29 | 2017-02-19 | 21 | B | Rev-0 | B | Approved |  |  | 1 5 | MKM
301 | SD-0026-00 |  |  | Vanity Counter Details Type - 04 8th to 17th Floor | 1252-MKM-05Q-IDP-01-DWG-0365 | 1 OF 1 | 2017-01-24 | 2017-01-29 | 2017-02-19 | 21 | B | MKM | [45 empty] | 2017-01-29 | 2017-02-19 | 21 | B | Rev-0 | B | Approved |  |  | 1 5 | MKM
302 | SD-0026-00 |  |  | Vanity Counter Detail Type - 05 19th to 23rd Floor | 1252-MKM-05Q-IDP-01-DWG-0366 | 1 OF 1 | 2017-01-24 | 2017-01-29 | 2017-02-19 | 21 | B | MKM | [45 empty] | 2017-01-29 | 2017-02-19 | 21 | B | Rev-0 | A | Approved |  |  | 1 5 | MKM
303 | SD-0038-01 |  | 19 - 23 | Niche/Display Shelf Details (19 to 23 Floor) | 1252-MKM-05Q-IDP-01-DWG-0367 | 1 OF 1 | 2017-02-01 | 2017-02-09 | 2017-02-19 | 10 | C | MKM | 2017-03-09 | 2017-03-13 | 4 | A | MKM | [40 empty] | 2017-03-09 | 2017-03-13 | 4 | A | Rev-1 | B | Approved |  |  | 1 5 | MKM
304 | SD-0057-02 | ARK-0054-00 | 8 to 17 | Skirting Schedule Details | 1252-MKM-05Q-IDP-01-DWG-0368 | 1 OF 3 | 2017-02-01 | 2017-02-20 | 2017-03-01 | 9 | C | MKM | 2017-03-09 | 2017-03-13 | 4 | B | MKM | 2019-07-14 | 2019-08-05 | 22 | B | MKM | [35 empty] | 2019-07-14 | 2019-08-05 | 22 | B | Rev-2 | B | Approved |  |  | 1 5 | MKM
305 | SD-0057-02 | ARK-0054-00 | 16, 19 to 29 | Skirting Schedule Details | 1252-MKM-05Q-IDP-01-DWG-0368 | 2 OF 3 | 2017-02-01 | 2017-02-20 | 2017-03-01 | 9 | C | MKM | 2017-03-09 | 2017-03-13 | 4 | B | MKM | 2019-07-14 | 2019-08-05 | 22 | B | MKM | [35 empty] | 2019-07-14 | 2019-08-05 | 22 | B | Rev-2 | B | Approved |  |  | 1 5 | MKM
306 | SD-0057-02 | ARK-0054-00 | 30 to 41 | Skirting Schedule Details | 1252-MKM-05Q-IDP-01-DWG-0368 | 3 OF 3 | 2017-02-01 | 2017-02-20 | 2017-03-01 | 9 | B | MKM | 2019-07-14 | 2019-08-05 | 22 | B | MKM | [40 empty] | 2019-07-14 | 2019-08-05 | 22 | B | Rev-1 | A | Approved |  |  | 1 5 | MKM
307 | SD-0043-00 |  |  | Luggage Shelf & Luggage Storage Cabinet Schedule | 1252-MKM-05Q-IDP-01-DWG-0370 | 1 OF 1 | 2017-02-01 | 2017-02-09 | 2017-02-26 | 17 | A | MKM | [45 empty] | 2017-02-09 | 2017-02-26 | 17 | A | Rev-0 | B | Approved |  |  | 1 5 | MKM
308 | SD-0043-00 |  | 8th | Luggage Shelf-Detail 8th Floor 1,2 & 3 Bedroom Apartment | 1252-MKM-05Q-IDP-01-DWG-0371 | 1 OF 1 | 2017-02-01 | 2017-02-09 | 2017-02-26 | 17 | B | MKM | [45 empty] | 2017-02-09 | 2017-02-26 | 17 | B | Rev-0 | A | Approved |  |  | 1 5 | MKM
309 | SD-0043-02 |  | 8th-17th | 8th to 17th Floor Luggage Storage Cabinet-Detail | 1252-MKM-05Q-IDP-01-DWG-0372 | 1 OF 1 | 2017-02-01 | 2017-02-09 | 2017-02-26 | 17 | B | MKM | 2017-04-03 | 2017-04-05 | 2 | B | MKM | 2017-04-17 | 2017-04-20 | 3 | A | MKM | [35 empty] | 2017-04-17 | 2017-04-20 | 3 | A | Rev-2 | B | Approved |  |  | 1 5 | MKM
310 | SD-0048-01 |  | 8th-41st | Shower Bench Detail 8th to 41st Floor | 1252-MKM-05Q-IDP-01-DWG-0373 | 1 OF 1 | 2017-02-01 | 2017-02-13 | 2017-02-19 | 6 | C | MKM | 2017-03-05 | 2017-03-08 | 3 | B | MKM | [40 empty] | 2017-03-05 | 2017-03-08 | 3 | B | Rev-1 | A | Approved |  |  | 1 5 | MKM
311 | SD-0047-01 |  | 8th | 8th Floor 2 Bedroom Apartment Wooden Paneling Details @ Kitchen Area | 1252-MKM-05Q-IDP-01-DWG-0374 | 1 OF 2 | 2017-02-01 | 2017-02-13 | 2017-02-16 | 3 | B | MKM | 2017-05-25 | 2017-05-29 | 4 | A | MKM | [40 empty] | 2017-05-25 | 2017-05-29 | 4 | A | Rev-1 | A | Approved |  |  | 1 5 | MKM
312 | SD-0047-01 |  | 8th | 8th Floor 3 Bedroom Apartment Wooden Paneling Details @ Kitchen Area | 1252-MKM-05Q-IDP-01-DWG-0374 | 2 OF 2 | 2017-02-01 | 2017-02-13 | 2017-02-16 | 3 | B | MKM | 2017-05-25 | 2017-05-29 | 4 | A | MKM | [40 empty] | 2017-05-25 | 2017-05-29 | 4 | A | Rev-1 | A | Approved |  |  | 1 5 | MKM
313 | SD-0062-01 |  | 8th - 41st | Coffee Table Details | 1252-MKM-05Q-IDP-01-DWG-0375 | 1 OF 1 |  | 2017-04-11 | 2017-04-11 | 0 | C | MKM | 2017-04-26 | 2017-04-26 | 0 | A | MKM | [40 empty] | 2017-04-26 | 2017-04-26 | 0 | A | Rev-1 | A | Approved |  |  | 1 5 | MKM
314 | SD-0066-00 |  | 8th - 17th | 8th to 17th Floor Apartments DB Cabinet Shutter-Detail | 1252-MKM-05Q-IDP-01-DWG-0376 | 1 OF 1 |  | 2017-06-29 | 2017-07-04 | 5 | A | MKM | [45 empty] | 2017-06-29 | 2017-07-04 | 5 | A | Rev-0 | A | Approved |  |  | 1 5 | MKM
315 | SD-0064-00 |  | 8th - 17th | 8th to 17th Floor Wooden Structure Details 9Above Ceiling) @ TV Unit (Type-3) | 1252-MKM-05Q-IDP-01-DWG-0377 | 1 OF 1 |  | 2017-05-04 | 2017-05-08 | 4 | A | MKM | [45 empty] | 2017-05-04 | 2017-05-08 | 4 | A | Rev-0 | B | Approved |  |  | 1 5 | MKM
316 | SD-0067-00 |  |  | Three Bedroom Corridor Shaft Door Plan & Elevations | 1252-MKM-05Q-IDP-01-DWG-0378 | 1 OF 1 |  | 2017-08-28 | 2017-09-10 | 13 | B | MKM | [45 empty] | 2017-08-28 | 2017-09-10 | 13 | B | Rev-0 | X |  |  |  | 1 5 | MKM
317 | SD-0076-00 |  | L9 | Work Desk detail -Type -1 @ Master Bedroom | 1252-MKM-05Q-IDP-01-DWG-0382 | 1 OF 2 |  | 2018-01-24 | 2018-01-30 | 6 | SS | MKM | [45 empty] | 2018-01-24 | 2018-01-30 | 6 | SS | Rev-0 | X |  |  |  | 1 5 | MKM
318 | SD-0076-00 |  | L9 | Work Desk detail -Type -1 @ Master Bedroom | 1252-MKM-05Q-IDP-01-DWG-0382 | 2 OF 2 |  | 2018-01-24 | 2018-01-30 | 6 | SS | MKM | [45 empty] | 2018-01-24 | 2018-01-30 | 6 | SS | Rev-0 | X |  |  |  | 1 5 | MKM
319 | SD-0076-00 |  | L9 | Work Desk detail -Type -2 @ King & Twin Bedrooms | 1252-MKM-05Q-IDP-01-DWG-0383 | 1 OF 1 |  | 2018-01-24 | 2018-01-30 | 6 | SS | MKM | [45 empty] | 2018-01-24 | 2018-01-30 | 6 | SS | Rev-0 | X |  |  |  | 1 5 | MKM
320 | SD-0075-00 |  | L9 | TV unit details -Type -2 & 2A @ King & Twin Bedrooms | 1252-MKM-05Q-IDP-01-DWG-0384 | 1 OF 1 |  | 2018-01-08 | 2018-01-08 | 0 | SS | MKM | [45 empty] | 2018-01-08 | 2018-01-08 | 0 | SS | Rev-0 | X |  |  |  | 1 5 | MKM
321 | SD-0077-00 |  | L9 | Bed side Table detail -Type -2 @ King & Twin Bedrooms | 1252-MKM-05Q-IDP-01-DWG-0385 | 1 OF 1 |  | 2018-03-08 | 2018-03-13 | 5 | SS | MKM | [45 empty] | 2018-03-08 | 2018-03-13 | 5 | SS | Rev-0 | X |  |  |  | 1 5 | MKM
322 | SD-0075-00 |  | L9 | Bed side Table detail -Type -1 @ Master Bedroom | 1252-MKM-05Q-IDP-01-DWG-0386 | 1 OF 1 |  | 2018-01-08 | 2018-01-08 | 0 | SS | MKM | [45 empty] | 2018-01-08 | 2018-01-08 | 0 | SS | Rev-0 | B | Approved |  |  | 1 5 | MKM
323 | SD-0076-05 | ARK-0019-03 | 8th - 17th | 8th to 17th Floor 1 Bedroom Apartment Archway Details | 1252-MKM-05Q-IDP-01-DWG-0387 | 1 OF 5 |  | 2018-01-24 | 2018-01-30 | 6 | B | MKM | 2018-08-14 | 2018-08-28 | 14 | C | MKM | 2018-09-27 | 2018-10-15 | 18 | C | MKM | 2018-12-31 | 2019-01-09 | 9 | C | MKM | 2019-02-21 | 2019-03-03 | 10 | B | MKM | [25 empty] | 2019-02-21 | 2019-03-03 | 10 | B | Rev-4 | X |  |  |  | 1 5 | MKM
324 | SD-0076-05 | ARK-0019-03 | L9 | 8th to 17th Floor 2 Bedroom Apartment Archway Details | 1252-MKM-05Q-IDP-01-DWG-0387 | 2 OF 5 |  | 2018-08-14 | 2018-08-28 | 14 | C | MKM | 2018-09-27 | 2018-10-15 | 18 | C | MKM | 2018-12-31 | 2019-01-09 | 9 | B | MKM | 2019-02-21 | 2019-03-03 | 10 | B | MKM | [30 empty] | 2019-02-21 | 2019-03-03 | 10 | B | Rev-3 | X |  |  |  | 1 5 | MKM
325 | SD-0076-05 | ARK-0019-03 | L9 | 8th to 17th Floor 3 Bedroom Apartment Archway Details | 1252-MKM-05Q-IDP-01-DWG-0387 | 3 OF 5 |  | 2018-08-14 | 2018-08-28 | 14 | C | MKM | 2018-09-27 | 2018-10-15 | 18 | C | MKM | 2018-12-31 | 2019-01-09 | 9 | C | MKM | 2019-02-21 | 2019-03-03 | 10 | B | MKM | [30 empty] | 2019-02-21 | 2019-03-03 | 10 | B | Rev-3 | X |  |  |  | 1 5 | MKM
326 | SD-0076-05 | ARK-0019-03 | L9 | 8th to 17th Floor 3 Bedroom Apartment Archway Details | 1252-MKM-05Q-IDP-01-DWG-0387 | 4 OF 5 |  | 2018-12-31 | 2019-01-09 | 9 | B | MKM | 2019-02-21 | 2019-03-03 | 10 | B | MKM | [40 empty] | 2019-02-21 | 2019-03-03 | 10 | B | Rev-1 | X |  |  |  | 1 5 | MKM
327 | SD-0076-05 | ARK-0019-03 | L9 | 8th to 17th Floor 3 Bedroom Apartment Archway Details | 1252-MKM-05Q-IDP-01-DWG-0387 | 5 OF 5 |  | 2018-12-31 | 2019-01-09 | 9 | C | MKM | 2019-02-21 | 2019-03-03 | 10 | B | MKM | [40 empty] | 2019-02-21 | 2019-03-03 | 10 | B | Rev-1 | X |  |  |  | 1 5 | MKM
328 | SD-0078-01 |  | L9 | Mock-up Rom Bed Side Wall Mirror Cladding Details | 1252-MKM-05Q-IDP-01-DWG-0388 | 1 OF 1 |  | 2018-01-30 | 2018-02-01 | 2 | C | MKM | 2018-02-04 | 2018-02-08 | 4 | D | MKM |  |  |  | SS | AS PER HASSAN | [35 empty] | 2018-02-04 | 2018-02-08 | 4 | SS | Rev-1 | X |  |  |  | 1 5 | AS PER HASSAN
329 | SD-0078-01 |  | L9 | Guest Room Mock-up Bedside Table Details | 1252-MKM-05Q-IDP-01-DWG-0389 | 1 OF 1 |  | 2018-01-30 | 2018-02-01 | 2 | C | MKM | 2018-02-04 | 2018-02-08 | 4 | SS | MKM | [40 empty] | 2018-02-04 | 2018-02-08 | 4 | SS | Rev-1 | B | Approved |  |  | 1 5 | MKM
330 | SD-0087-02 |  | L9 | Mock-up Guest Room Vanity Mirror Details | 1252-MKM-05Q-IDP-01-DWG-0390 | 1 OF 1 |  | 2018-02-19 | 2018-02-28 | 9 | C | MKM | 2018-03-06 | 2018-03-11 | 5 | C | MKM | 2018-03-18 | 2018-03-20 | 2 | B | MKM | [35 empty] | 2018-03-18 | 2018-03-20 | 2 | B | Rev-2 | B | Approved |  |  | 1 5 | MKM
331 | SD-0087-01 |  | L9 | 9th Floor Mock - Up Apartment (901) Master Bathroom Vanity Mirror Detail | 1252-MKM-05Q-IDP-01-DWG-0391 | 1 OF 1 |  | 2018-03-06 | 2018-03-11 | 5 | B | MKM | [45 empty] | 2018-03-06 | 2018-03-11 | 5 | B | Rev-0 | B | Approved |  |  | 1 5 | MKM
332 | SD-0092-00 |  | L9 | 9th to 13th Floor Three Bedroom Apartment Master Bedroom Mirror (SWA-503) Detail | 1252-MKM-05Q-IDP-01-DWG-0392 | 1 OF 1 |  | 2018-03-06 | 2018-03-12 | 6 | B | MKM | [45 empty] | 2018-03-06 | 2018-03-12 | 6 | B | Rev-0 | 0 |  |  |  | 1 5 | MKM
GENERAL DETAILS | [62 empty] | B | Approved |  |  | 1 160
333 | SD-0093-00 |  | 8th to 17th Floor | 8th to 17th Floor Apartment King & Twin Bedroom Bed Side Table Details (Type -2 & 3) | 1252-MKM-05Q-IDP-01-DWG-0385 | 1 OF 1 |  | 2018-03-15 | 2018-03-19 | 4 | B | MKM | [45 empty] | 2018-03-15 | 2018-03-19 | 4 | B | Rev-0 | B | Approved |  |  | 1 5 | MKM
334 | SD-0093-02 |  | 8th to 17th Floor | 8th to 17th Floor Apartment Master Bedroom Bed Side Table Details (Type-1) | 1252-MKM-05Q-IDP-01-DWG-0386 | 1 OF 1 |  | 2018-03-15 | 2018-03-19 | 4 | B | MKM | 2018-07-03 | 2018-07-09 | 6 | B | MKM | [40 empty] | 2018-07-03 | 2018-07-09 | 6 | B | Rev-1 | C | Resub..reqd | 2018-04-05 |  | 1 5 | MKM
335 | SD-0093-01 |  | 8th to 17th Floor | 8th to 17th Floor Bed Side Table Schedule | 1252-MKM-05Q-IDP-01-DWG-0393 | 1 OF 1 |  | 2018-03-15 | 2018-03-19 | 4 | C | MKM | 2018-03-26 | 2018-03-29 | 3 | C | MKM |  |  |  | SS | AS PER RAMZI | [35 empty] | 2018-03-26 | 2018-03-29 | 3 | SS | Rev-1 |  |  |  |  | 1 5 | AS PER RAMZI
336 | SD-0102-01 |  | 8th to 17th Floor | 24th to 29th Floor STD King Room - Type-4 Work desk Type 5 Details | 1252-MKM-05Q-IDP-01-DWG-0394 | 1 OF 1 |  | 2018-06-09 | 2018-07-24 | 45 | C | MKM | 2018-07-31 | 2018-08-06 | 6 | B | MKM | [40 empty] | 2018-07-31 | 2018-08-06 | 6 | B | Rev-1 |  |  |  |  | 1 5 | MKM
337 | SD-0115-01 | ARK-0040-00 | 8th to 17th Floor | 8th to 17th Floor 2 & 3 Bedroom Apartment Maid's Room Bed Details (SWA-334) | 1252-MKM-05Q-IDP-01-DWG-0396 | 1 OF 1 |  | 2018-09-17 | 2018-10-07 | 20 | C | MKM | 2018-11-20 | 2018-12-08 | 18 | B | MKM | [40 empty] | 2018-11-20 | 2018-12-08 | 18 | B | Rev-1 |  |  |  |  | 1 5 | MKM
338 | SD-0115-00 |  | 8th to 17th Floor | 8th to 17th Floor 2 & 3 Bedroom Apartment Maid's Room Bed Side Table Details (SWA-335) | 1252-MKM-05Q-IDP-01-DWG-0397 | 1 OF 1 |  | 2018-09-17 | 2018-10-07 | 20 | B | MKM | [45 empty] | 2018-09-17 | 2018-10-07 | 20 | B | Rev-0 |  |  |  |  | 1 5 | MKM
339 | SD-0115-01 | ARK-0040-00 | 8th to 17th Floor | 8th to 17th Floor 3 Bedroom Apartment Maid's Room Chest of Drawers Details (SWA-336) | 1252-MKM-05Q-IDP-01-DWG-0398 | 1 OF 1 |  | 2018-09-17 | 2018-10-07 | 20 | C | MKM | 2018-11-20 | 2018-12-08 | 18 | B | MKM | [40 empty] | 2018-11-20 | 2018-12-08 | 18 | B | Rev-1 |  |  |  |  | 1 5 | MKM
340 | SD-0148-02 | ARK-0037-02 |  | Guest Rooms Twin Room (SWGS-316) Bed Base Typical Details | 1252-MKM-05Q-IDP-01-DWG-0399A | 1 OF 1 |  | 2018-11-04 | 2018-11-08 | 4 | C | MKM | 2019-07-04 | 2019-07-16 | 12 | B | MKM | 2019-07-31 |  | 26 | OD | MKM | [35 empty] | 2019-07-31 |  | 26 | OD | Rev-2 |  |  |  |  | 1 5 | MKM
341 | SD-0148-02 | ARK-0037-02 |  | Apartments Master Bed (SWA-310) Bed Base Typical Details | 1252-MKM-05Q-IDP-01-DWG-0399B | 1 OF 1 |  | 2018-11-04 | 2018-11-08 | 4 | C | MKM | 2019-07-04 | 2019-07-16 | 12 | B | MKM | 2019-07-31 |  | 26 | OD | MKM | [35 empty] | 2019-07-31 |  | 26 | OD | Rev-2 |  |  |  |  | 1 5 | MKM
342 | SD-0148-02 | ARK-0037-02 |  | Apartment Secondary King (SWA-319) Bed Base Typical Details | 1252-MKM-05Q-IDP-01-DWG-0399C | 1 OF 1 |  | 2018-11-04 | 2018-11-08 | 4 | C | MKM | 2019-07-04 | 2019-07-16 | 12 | B | MKM | 2019-07-31 |  | 26 | OD | MKM | [35 empty] | 2019-07-31 |  | 26 | OD | Rev-2 |  |  |  |  | 1 5 | MKM
343 | SD-0148-02 | ARK-0037-02 |  | Apartment Secondary King (SWA-327) Bed Base Typical Details | 1252-MKM-05Q-IDP-01-DWG-0399D | 1 OF 1 |  | 2018-11-04 | 2018-11-08 | 4 | C | MKM | 2019-07-04 | 2019-07-16 | 12 | B | MKM | 2019-07-31 |  | 26 | OD | MKM | [35 empty] | 2019-07-31 |  | 26 | OD | Rev-2 |  |  |  |  | 1 5 | MKM
344 | SD-0148-02 | ARK-0037-02 |  | Guest Rooms & Junior Suites King Rooms (SWGS-301) Bed Base Typical Details | 1252-MKM-05Q-IDP-01-DWG-0399E | 1 OF 1 |  | 2018-11-04 | 2018-11-08 | 4 | C | MKM | 2019-07-04 | 2019-07-16 | 12 | B | MKM | 2019-07-31 |  | 26 | OD | MKM | [35 empty] | 2019-07-31 |  | 26 | OD | Rev-2 |  |  |  |  | 1 5 | MKM
345 | SD-0148-02 | ARK-0037-02 |  | Guest Rooms & Junior Suites King Rooms (SWGS-301) Bed Base Typical Details | 1252-MKM-05Q-IDP-01-DWG-0399E | 1 OF 1 |  | 2018-11-04 | 2018-11-08 | 4 | C | MKM | 2019-07-04 | 2019-07-16 | 12 | B | MKM | 2019-07-31 |  | 26 | OD | MKM | [35 empty] | 2019-07-31 |  | 26 | OD | Rev-2 |  |  |  |  | 1 5 | MKM
[63 empty] | B | Approved |  |  | 1 181
346 | SD-0021-00 |  |  | 8th - 17th Floor Bathroom / Toilet Schedule | 1252-MKM-05Q-IDP-01-DWG-0400 | 1 OF 2 | 2017-01-24 | 2017-01-22 | 2017-01-31 | 9 | B | MKM | [45 empty] | 2017-01-22 | 2017-01-31 | 9 | B | Rev-0 | A | Approved |  |  | 1 5 | MKM
347 | SD-0034-00 |  | 19th-41st | 19th - 41st Floor Bathroom / Toilet Schedule | 1252-MKM-05Q-IDP-01-DWG-0400 | 2 OF 2 | 2017-01-24 | 2017-02-06 | 2017-02-19 | 13 | A | MKM | [45 empty] | 2017-02-06 | 2017-02-19 | 13 | A | Rev-0 | B | Approved |  |  | 1 5 | MKM
348 | SD-0021-00 |  |  | 3 Bedroom Apartment Maids Bathroom Details (Bath-1) | 1252-MKM-05Q-IDP-01-DWG-0401 | 1 OF 1 | 2017-01-24 | 2017-01-22 | 2017-01-31 | 9 | B | MKM | [45 empty] | 2017-01-22 | 2017-01-31 | 9 | B | Rev-0 | B | Approved |  |  | 1 5 | MKM
349 | SD-0021-00 |  |  | 3 Bedroom Apartment Guest Toilet Detail (Bath-2) | 1252-MKM-05Q-IDP-01-DWG-0402 | 1 OF 1 | 2017-01-24 | 2017-01-22 | 2017-01-31 | 9 | B | MKM | [45 empty] | 2017-01-22 | 2017-01-31 | 9 | B | Rev-0 | B | Approved |  |  | 1 5 | MKM
350 | SD-0021-01 |  |  | 3 Bedroom Apartment Bedroom-3 Bathroom Details (Bath-3) | 1252-MKM-05Q-IDP-01-DWG-0403 | 1 OF 1 | 2017-01-24 | 2017-01-22 | 2017-01-31 | 9 | B | MKM | 2017-05-02 | 2017-05-09 | 7 | B | MKM | [40 empty] | 2017-05-02 | 2017-05-09 | 7 | B | Rev-1 | B | Approved |  |  | 1 5 | MKM
351 | SD-0021-01 |  |  | 3 Bedroom Apartment Twin Bedroom Bathroom Detail (Bath-4) | 1252-MKM-05Q-IDP-01-DWG-0404 | 1 OF 1 | 2017-01-24 | 2017-01-22 | 2017-01-31 | 9 | B | MKM | 2017-05-02 | 2017-05-09 | 7 | B | MKM | [40 empty] | 2017-05-02 | 2017-05-09 | 7 | B | Rev-1 | B | Approved |  |  | 1 5 | MKM
352 | SD-0021-01 |  |  | 2 Bedroom Apartment Twin Bedroom Bathroom Detail (Bath-4A) | 1252-MKM-05Q-IDP-01-DWG-0405 | 1 OF 1 | 2017-01-24 | 2017-01-22 | 2017-01-31 | 9 | B | MKM | 2017-05-02 | 2017-05-09 | 7 | B | MKM | [40 empty] | 2017-05-02 | 2017-05-09 | 7 | B | Rev-1 | B | Approved |  |  | 1 5 | MKM
353 | SD-0021-01 |  |  | 3 Bedroom Apartment Master Bedroom - 1 Bathroom Details (Bath-5) | 1252-MKM-05Q-IDP-01-DWG-0406 | 1 OF 1 | 2017-01-24 | 2017-01-22 | 2017-01-31 | 9 | B | MKM | 2017-05-02 | 2017-05-09 | 7 | B | MKM | [40 empty] | 2017-05-02 | 2017-05-09 | 7 | B | Rev-1 | B | Approved |  |  | 1 5 | MKM
354 | SD-0021-01 |  |  | 2 Bedroom Apartment Twin Bedroom - 2 Bathroom Details (Bath-5A) | 1252-MKM-05Q-IDP-01-DWG-0407 | 1 OF 1 | 2017-01-24 | 2017-01-22 | 2017-01-31 | 9 | B | MKM | 2017-05-02 | 2017-05-09 | 7 | B | MKM | [40 empty] | 2017-05-02 | 2017-05-09 | 7 | B | Rev-1 | B | Approved |  |  | 1 5 | MKM
355 | SD-0021-02 |  |  | 2 & 3 Bedroom Apartment Master Bathroom -1 Bathroom Details (Bath-5B) | 1252-MKM-05Q-IDP-01-DWG-0408 | 1 OF 1 | 2017-01-24 | 2017-01-22 | 2017-01-31 | 9 | B | MKM | 2018-04-10 | 2018-04-23 | 13 | B | MKM | [40 empty] | 2018-04-10 | 2018-04-23 | 13 | B | Rev-1 | B | Approved
356 | SD-0022-01 |  |  | Studio - A & B - Apartment Master Bedroom Details (Bath-6) | 1252-MKM-05Q-IDP-01-DWG-0409 | 1 OF 1 | 2017-01-24 | 2017-01-22 | 2017-02-01 | 10 | B | MKM | 2017-05-02 | 2017-05-09 | 7 | B | MKM | [40 empty] | 2017-05-02 | 2017-05-09 | 7 | B | Rev-1 | B | Approved
357 | SD-0022-00 |  |  | 2 Bedroom Apartment Maid's Bathroom Detail (Bath-7) | 1252-MKM-05Q-IDP-01-DWG-0410 | 1 OF 1 | 2017-01-24 | 2017-01-22 | 2017-02-01 | 10 | B | MKM | [45 empty] | 2017-01-22 | 2017-02-01 | 10 | B | Rev-0 | B | Approved
358 | SD-0022-00 |  |  | 1 Bedroom Apartment Guest Toilet Detail (Bath-8) | 1252-MKM-05Q-IDP-01-DWG-0411 | 1 OF 1 | 2017-01-24 | 2017-01-22 | 2017-02-01 | 10 | B | MKM | [45 empty] | 2017-01-22 | 2017-02-01 | 10 | B | Rev-0 | B | Approved
359 | SD-0022-00 |  |  | 1 Bedroom Apartment Guest Toilet Detail (Bath-9) | 1252-MKM-05Q-IDP-01-DWG-0412 | 1 OF 1 | 2017-01-24 | 2017-01-22 | 2017-02-01 | 10 | B | MKM | [45 empty] | 2017-01-22 | 2017-02-01 | 10 | B | Rev-0 | B | Approved
360 | SD-0022-01 |  |  | 1 Bedroom Apartment Bathroom Detail (Bath-10) | 1252-MKM-05Q-IDP-01-DWG-0413 | 1 OF 1 | 2017-01-24 | 2017-01-22 | 2017-02-01 | 10 | B | MKM | 2017-05-02 | 2017-05-09 | 7 | B | MKM | [40 empty] | 2017-05-02 | 2017-05-09 | 7 | B | Rev-1 | A | Approved
361 | SD-0022-02 |  |  | Studio - B - Apartment Master Bedroom Bathroom Details (Bath-11) | 1252-MKM-05Q-IDP-01-DWG-0414 | 1 OF 1 | 2017-01-24 | 2017-01-22 | 2017-02-01 | 10 | B | MKM | 2017-06-15 | 2017-06-20 | 5 | A | MKM | [40 empty] | 2017-06-15 | 2017-06-20 | 5 | A | Rev-1 | B | Approved |  |  | 1 5 | MKM
362 | SD-0034-01 |  |  | 1 - Bedroom Suite - A Bathroom Details (Bath-12) | 1252-MKM-05Q-IDP-01-DWG-0415 | 1 OF 1 | 2017-01-24 | 2017-02-06 | 2017-02-19 | 13 | B | MKM | 2018-04-11 | 2018-04-23 | 12 | B | MKM | [40 empty] | 2018-04-11 | 2018-04-23 | 12 | B | Rev-1 | B | Approved
363 | SD-0034-00 |  |  | 1 - Bedroom Suite - B Guest Toilet Details (Bath-13) | 1252-MKM-05Q-IDP-01-DWG-0416 | 1 OF 1 | 2017-01-24 | 2017-02-06 | 2017-02-19 | 13 | B | MKM | [45 empty] | 2017-02-06 | 2017-02-19 | 13 | B | Rev-0 | B | Approved
364 | SD-0034-01 |  |  | Junior Suite/Standard Room/Executive Room Bathroom Details (Bath-14) | 1252-MKM-05Q-IDP-01-DWG-0417 | 1 OF 1 | 2017-01-24 | 2017-02-06 | 2017-02-19 | 13 | B | MKM | 2018-04-11 | 2018-04-23 | 12 | B | MKM | [40 empty] | 2018-04-11 | 2018-04-23 | 12 | B | Rev-1 | B | Approved
365 | SD-0034-01 |  |  | Junior Suite/Standard Room/Executive Room Bathroom Details (Bath-14A) | 1252-MKM-05Q-IDP-01-DWG-0418 | 1 OF 1 | 2017-01-24 | 2017-02-06 | 2017-02-19 | 13 | B | MKM | 2018-04-11 | 2018-04-23 | 12 | B | MKM | [40 empty] | 2018-04-11 | 2018-04-23 | 12 | B | Rev-1 | B | Approved
366 | SD-0034-01 |  |  | Junior Suite/Standard Room/Executive Room Bathroom Details (Bath-14B) | 1252-MKM-05Q-IDP-01-DWG-0419 | 1 OF 1 | 2017-01-24 | 2017-02-06 | 2017-02-19 | 13 | B | MKM | 2018-04-11 | 2018-04-23 | 12 | B | MKM | [40 empty] | 2018-04-11 | 2018-04-23 | 12 | B | Rev-1 | B | Approved
367 | SD-0034-00 |  |  | Disabled Guest Toilet Detail (Bath 15) | 1252-MKM-05Q-IDP-01-DWG-0420 | 1 OF 1 | 2017-01-24 | 2017-02-06 | 2017-02-19 | 13 | B | MKM | [45 empty] | 2017-02-06 | 2017-02-19 | 13 | B | Rev-0 | A | Approved
368 | SD-0063-01 |  | 8th to 41st | 8th to 41st Floor Typical WC Ledge Details | 1252-MKM-05Q-IDP-01-DWG-0421 | 1 OF 1 |  | 2017-05-02 | 2017-05-09 | 7 | B | MKM | 2017-05-22 | 2017-05-23 | 1 | A | MKM | [40 empty] | 2017-05-22 | 2017-05-23 | 1 | A | Rev-1
369 | SD-0100-01 |  |  | 2BR, 3BR & Studio - Type B Apartments Bath-Tub Ledge & Structure Support Details | 1252-MKM-05Q-IDP-01-DWG-0422 | 1 OF 1 |  | 2018-04-25 | 2018-05-01 | 6 | B | MKM | 2018-05-10 | 2018-05-13 | 3 | B | MKM | [40 empty] | 2018-05-10 | 2018-05-13 | 3 | B | Rev-1
Door Schedule | [62 empty] | B | Approved |  |  | 1 190
370 | SD-0031-00 |  | 8th | 8th Floor Door Schedule | 1252-MKM-05Q-IDP-01-DWG-0500 | 1 OF 9 | 2017-01-30 | 2017-02-01 | 2017-02-19 | 18 | B | MKM | [45 empty] | 2017-02-01 | 2017-02-19 | 18 | B | Rev-0 | B | Approved |  |  | 1 5 | MKM
371 | SD-0031-00 |  | 9th - 13th | 9th to 13th Floor Door Schedule | 1252-MKM-05Q-IDP-01-DWG-0500 | 2 OF 9 | 2017-01-30 | 2017-02-01 | 2017-02-19 | 18 | B | MKM | [45 empty] | 2017-02-01 | 2017-02-19 | 18 | B | Rev-0 | B | Approved |  |  | 1 5 | MKM
372 | SD-0031-00 |  | 14,15 & 17 | 14th, 15th & 17th Floor Door Schedule | 1252-MKM-05Q-IDP-01-DWG-0500 | 3 OF 9 | 2017-01-30 | 2017-02-01 | 2017-02-19 | 18 | B | MKM | [45 empty] | 2017-02-01 | 2017-02-19 | 18 | B | Rev-0 | B | Approved |  |  | 1 5 | MKM
373 | SD-0031-00 |  | 16th | 16th Floor Door Schedule | 1252-MKM-05Q-IDP-01-DWG-0500 | 4 OF 9 | 2017-01-30 | 2017-02-01 | 2017-02-19 | 18 | B | MKM | [45 empty] | 2017-02-01 | 2017-02-19 | 18 | B | Rev-0 | B | Approved |  |  | 1 5 | MKM
374 | SD-0031-00 |  | 19th - 23rd | 19th to 23rd Floor Door Schedule | 1252-MKM-05Q-IDP-01-DWG-0500 | 5 OF 9 | 2017-01-30 | 2017-02-01 | 2017-02-19 | 18 | B | MKM | [45 empty] | 2017-02-01 | 2017-02-19 | 18 | B | Rev-0 | B | Approved |  |  | 1 5 | MKM
375 | SD-0031-00 |  | 24th to 29th | 24th to 29th Floor Door Schedule | 1252-MKM-05Q-IDP-01-DWG-0500 | 6 OF 9 | 2017-01-30 | 2017-02-01 | 2017-02-19 | 18 | B | MKM | [45 empty] | 2017-02-01 | 2017-02-19 | 18 | B | Rev-0 | B | Approved |  |  | 1 5 | MKM
376 | SD-0031-00 |  | 30th | 30th Floor Door Schedule | 1252-MKM-05Q-IDP-01-DWG-0500 | 7 OF 9 | 2017-01-30 | 2017-02-01 | 2017-02-19 | 18 | B | MKM | [45 empty] | 2017-02-01 | 2017-02-19 | 18 | B | Rev-0 | B | Approved |  |  | 1 5 | MKM
377 | SD-0031-00 |  | 31st - 36th | 31st to 36th Floor Door Schedule | 1252-MKM-05Q-IDP-01-DWG-0500 | 8 OF 9 | 2017-01-30 | 2017-02-01 | 2017-02-19 | 18 | B | MKM | [45 empty] | 2017-02-01 | 2017-02-19 | 18 | B | Rev-0 | B | Approved |  |  | 1 5 | MKM
378 | SD-0031-00 |  | 37th-41st | 37th to 41st Floor Door Schedule | 1252-MKM-05Q-IDP-01-DWG-0500 | 9 OF 9 | 2017-01-30 | 2017-02-01 | 2017-02-19 | 18 | B | MKM | [45 empty] | 2017-02-01 | 2017-02-19 | 18 | B | Rev-0 | A | Approved |  |  | 1 5 | MKM
379 | SD-0025-04 |  |  | Main Entrance Door - (WD1) 60Min. Fire Rated 8th to 17th Floor | 1252-MKM-05Q-IDP-01-DWG-0501 | 1 OF 1 | 2017-01-30 | 2017-01-29 | 2017-02-21 | 23 | C | MKM | 2017-03-05 | 2017-03-08 | 3 | C | MKM | 2017-04-26 | 2017-05-07 | 11 | C | MKM | 2017-05-08 | 2017-05-15 | 7 | A | MKM | [30 empty] | 2017-05-08 | 2017-05-15 | 7 | A | Rev-3 | A | Approved |  |  | 1 5 | MKM
380 | SD-0025-03 |  |  | Bathroom Door - (WD2) ''Mock Up Door'' | 1252-MKM-05Q-IDP-01-DWG-0502 | 1 OF 1 | 2017-01-30 | 2017-01-29 | 2017-02-21 | 23 | B | MKM | 2017-03-15 | 2017-03-18 | 3 | B | MKM | 2017-04-26 | 2017-04-27 | 1 | A | MKM | [35 empty] | 2017-04-26 | 2017-04-27 | 1 | A | Rev-2 | B | Approved
381 | SD-0025-05 |  |  | Maids Bathroom Door - (WD2a) 8th Floor to 17th Floor | 1252-MKM-05Q-IDP-01-DWG-0503 | 1 OF 1 | 2017-01-30 | 2017-01-29 | 2017-02-21 | 23 | B | MKM | 2017-05-17 | 2017-05-21 | 4 | B | MKM | [40 empty] | 2017-05-17 | 2017-05-21 | 4 | B | Rev-1 | B | Approved
382 | SD-0025-00 |  |  | Bedroom Door - (WD3) 8th Floor to 41st Floor | 1252-MKM-05Q-IDP-01-DWG-0504 | 1 OF 1 | 2017-01-30 | 2017-01-29 | 2017-02-21 | 23 | B | MKM | [45 empty] | 2017-01-29 | 2017-02-21 | 23 | B | Rev-0 | B | Approved
383 | SD-0025-00 |  |  | Maid Room Door - (WD3a) 8th Floor to 17th Floor | 1252-MKM-05Q-IDP-01-DWG-0505 | 1 OF 1 | 2017-01-30 | 2017-01-29 | 2017-02-21 | 23 | B | MKM | [45 empty] | 2017-01-29 | 2017-02-21 | 23 | B | Rev-0 | B | Approved
384 | SD-0025-00 |  |  | Maid Room Door - (WD3b) 8th Floor to 17th Floor | 1252-MKM-05Q-IDP-01-DWG-0506 | 1 OF 1 | 2017-01-30 | 2017-01-29 | 2017-02-21 | 23 | B | MKM | [45 empty] | 2017-01-29 | 2017-02-21 | 23 | B | Rev-0 | B | Approved
385 | SD-0025-07 |  |  | Disabled Bathroom Door - (WD13) 24th Floor to 29th Floor | 1252-MKM-05Q-IDP-01-DWG-0507 | 1 OF 1 | 2017-01-30 | 2017-01-29 | 2017-02-21 | 23 | B | MKM | 2018-04-03 | 2018-04-09 | 6 | C | MKM | 2018-04-11 | 2018-04-29 | 18 | B | MKM | [35 empty] | 2018-04-11 | 2018-04-29 | 18 | B | Rev-2 | A | Approved
386 | SD-0042-01 |  | 24th -41st | Interconnecting Door - (WD12) 60Min. Fire Rated 24th to 41st Floor | 1252-MKM-05Q-IDP-01-DWG-0508 | 1 OF 1 | 2017-01-30 | 2017-02-09 | 2017-02-19 | 10 | C | MKM | 2017-03-05 | 2017-03-15 | 10 | A | MKM | [40 empty] | 2017-03-05 | 2017-03-15 | 10 | A | Rev-1 | C | Resub..reqd | 2018-04-09
387 | SD-0042-04 |  | 19th - 41st | 19th to 41st Floor Lift Lobby Door - (WD11) 60Min. Fire Rated | 1252-MKM-05Q-IDP-01-DWG-0509 | 1 OF 2 | 2017-01-30 | 2017-02-09 | 2017-02-19 | 10 | C | MKM | 2017-03-05 | 2017-03-15 | 10 | B | MKM | 2018-03-06 | 2018-03-29 | 23 | C | MKM | 2018-04-08 | 2018-04-10 | 2 | A | MKM | 2018-07-02 | 2018-08-12 | 41 | B | MKM | [25 empty] | 2018-07-02 | 2018-08-12 | 41 | B | Rev-4 | C | Resub..reqd | 2018-04-09
388 | SD-0042-03 |  | 19th - 41st | 19th to 41st Floor Lift Lobby Door - (WD11) 60Min. Fire Rated | 1252-MKM-05Q-IDP-01-DWG-0509 | 2 OF 2 | 2017-01-30 | 2018-03-06 | 2018-03-29 | 23 | C | MKM | 2018-04-08 | 2018-04-10 | 2 | A | MKM | [40 empty] | 2018-04-08 | 2018-04-10 | 2 | A | Rev-1 | B | Approved
389 | SD-0074-01 |  |  | Mock Up Apartment Master Bathroom Door Detail - (WD-2b) | 1252-MKM-05Q-IDP-01-DWG-0513 | 1 OF 1 | 2017-01-30 | 2018-01-04 | 2018-01-07 | 3 | C | MKM | 2018-01-24 | 2018-01-30 | 6 | B | MKM | [40 empty] | 2018-01-24 | 2018-01-30 | 6 | B | Rev-1
390 | SD-0098-01 |  | 24th - 29th Floor | 24th to 29th Floor Handicapped Guest Room Main Entrance Door - (WD1a) 60min. Fire Rated | 1252-MKM-05Q-IDP-01-DWG-0514 | 1 OF 1 |  | 2018-04-12 | 2018-04-29 | 17 | C | MKM | 2018-05-16 | 2018-05-21 | 5 | B | MKM | [40 empty] | 2018-05-16 | 2018-05-21 | 5 | B | Rev-1
[63 empty] | B/C | Resub..reqd | 2018-04-10 |  | 1 199
391 | SD-0054-00 |  | 8th-41st | 8th to 41st Floor Gypsum Ceiling Suspension System Layout | 1252-MKM-05Q-IDP-01-DWG-0600 | 1 OF 1 |  | 2017-02-16 | 2017-02-23 | 7 | B | MKM | [45 empty] | 2017-02-16 | 2017-02-23 | 7 | B | Rev-0
392 | SD-0003-02 |  |  | Typical Ceiling Details at Studio (A & B) & 1,2,3 Bedrooms Types | 1252-MKM-05Q-IDP-01-DWG-0601 | 1 OF 1 | 2017-01-17 | 2016-12-27 | 2017-01-15 | 19 | C | MKM | 2017-01-29 | 2017-03-07 | 37 | B | MKM | 2017-06-13 | 2017-06-19 | 6 | B | MKM | [35 empty] | 2017-06-13 | 2017-06-19 | 6 | B | Rev-2 | B/C | Resub..reqd | 2018-04-10 |  | 1 5 | MKM
393 | SD-0056-01 |  | 8th-41st | 8th to 41st Floor Threshold & Skirting Details | 1252-MKM-05Q-IDP-01-DWG-0602 | 1 OF 1 | 2017-02-13 | 2017-02-19 | 2017-03-07 | 16 | C | MKM | 2017-05-17 | 2017-05-24 | 7 | B | MKM | [40 empty] | 2017-05-17 | 2017-05-24 | 7 | B | Rev-1 | B/C | Resub..reqd | 2018-04-10 |  | 1 5 | MKM
394 | SD-0058-00 |  | 19 to 41 | 19th to 41st Floor Typical Ceiling Details at Suite & Guestrooms | 1252-MKM-05Q-IDP-01-DWG-0603 | 1 OF 1 | 2017-02-13 | 2017-02-20 | 2017-03-01 | 9 | B | MKM | [45 empty] | 2017-02-20 | 2017-03-01 | 9 | B | Rev-0 | B/C | Resub..reqd | 2018-04-10 |  | 1 5 | MKM
395 | SD-0114-00 |  |  | (8th Floor) Gypsum Cladding Plan | 1252-MKM-05Q-IDP-01-DWG-0604 | 1 OF 1 |  | 2018-09-03 | 2018-09-09 | 6 | B | MKM | [45 empty] | 2018-09-03 | 2018-09-09 | 6 | B | Rev-0
396 | SD-0114-00 |  |  | (9th to 15th Floor) Gypsum Cladding Plan | 1252-MKM-05Q-IDP-01-DWG-0605 | 1 OF 1 |  | 2018-09-03 | 2018-09-09 | 6 | B | MKM | [45 empty] | 2018-09-03 | 2018-09-09 | 6 | B | Rev-0
397 | SD-0114-00 |  |  | (16th Floor) Gypsum Cladding Plan | 1252-MKM-05Q-IDP-01-DWG-0606 | 1 OF 1 |  | 2018-09-03 | 2018-09-09 | 6 | B | MKM | [45 empty] | 2018-09-03 | 2018-09-09 | 6 | B | Rev-0
398 | SD-0114-00 |  |  | (17th Floor) Gypsum Cladding Plan | 1252-MKM-05Q-IDP-01-DWG-0607 | 1 OF 1 |  | 2018-09-03 | 2018-09-09 | 6 | B | MKM | [45 empty] | 2018-09-03 | 2018-09-09 | 6 | B | Rev-0
399 | SD-0114-00 |  |  | (19th to 23rd Floor) Gypsum Cladding Plan | 1252-MKM-05Q-IDP-01-DWG-0608 | 1 OF 1 |  | 2018-09-03 | 2018-09-09 | 6 | B | MKM | [45 empty] | 2018-09-03 | 2018-09-09 | 6 | B | Rev-0
400 | SD-0114-00 |  |  | Typical Gypsum Cladding Plan | 1252-MKM-05Q-IDP-01-DWG-0609 | 1 OF 1 |  | 2018-09-03 | 2018-09-09 | 6 | B | MKM | [45 empty] | 2018-09-03 | 2018-09-09 | 6 | B | Rev-0
CORRIDOR | [66 empty] | 1 203
Corridor Details, Plan & Elevation @ 8th to 17th Floor | [62 empty] | A | Approved |  |  | 1 204
401 | SD-0059-06 |  | 8th | 8th Floor Corridor Wall Paneling Layout | 1252-MKM-05Q-IDP-01-DWG-0710 | 1 OF 2 | 2017-02-14 | 2017-02-26 | 2017-03-07 | 9 | C | MKM | 2017-04-06 | 2017-04-19 | 13 | C | MKM | 2017-05-16 | 2017-05-24 | 8 | A | MKM | 2018-05-06 | 2018-05-19 | 13 | B | MKM | 2018-06-04 | 2018-06-13 | 9 | B | MKM | [25 empty] | 2018-06-04 | 2018-06-13 | 9 | B | Rev-4 | B | Approved |  |  |  | MKM
402 | SD-0059-07 |  | 8th to 17th | 8th to 17th Corridor Wall Paneling Details | 1252-MKM-05Q-IDP-01-DWG-0710 | 2 OF 2 |  | 2017-05-16 | 2017-05-24 | 8 | B | MKM | 2018-05-06 | 2018-05-19 | 13 | B | MKM | 2018-06-04 | 2018-06-13 | 9 | B | MKM | 2018-07-11 | 2018-07-16 | 5 | B | MKM | [30 empty] | 2018-07-11 | 2018-07-16 | 5 | B | Rev-3 | A | Approved |  |  |  | MKM
402 | SD-0059-08 |  | 9th-17th | 9th to 17th Floor Corridor Wall Paneling Layout | 1252-MKM-05Q-IDP-01-DWG-0711 | 1 OF 1 | 2017-02-15 | 2017-02-26 | 2017-03-07 | 9 | C | MKM | 2017-04-06 | 2017-04-19 | 13 | B | MKM | 2017-05-16 | 2017-05-24 | 8 | A | MKM | 2018-05-06 | 2018-05-19 | 13 | B | MKM | 2018-06-04 | 2018-06-13 | 9 | C | MKM | 2018-07-18 | 2018-07-24 | 6 | B | MKM | [20 empty] | 2018-07-18 | 2018-07-24 | 6 | B | Rev-5 | A | Approved
403 | SD-0059-06 |  | 8th - 16th | 8th to 16th Floor Corridor Reflected Ceiling Plan & Details | 1252-MKM-05Q-IDP-01-DWG-0712 | 1 OF 1 | 2017-02-16 | 2017-02-26 | 2017-03-07 | 9 | C | MKM | 2017-04-06 | 2017-04-19 | 13 | B | MKM | 2017-05-16 | 2017-05-24 | 8 | A | MKM | 2018-05-06 | 2018-05-19 | 13 | C | MKM | 2018-06-04 | 2018-06-13 | 9 | B | MKM | [25 empty] | 2018-06-04 | 2018-06-13 | 9 | B | Rev-4 | A | Approved
403 | SD-0059-06 |  | 8th-17th | 8th to 17th Floor Corridor Elevation - 1, 2, 3, 4 | 1252-MKM-05Q-IDP-01-DWG-0713 | 1 OF 3 | 2017-02-19 | 2017-02-26 | 2017-03-07 | 9 | C | MKM | 2017-04-06 | 2017-04-19 | 13 | C | MKM | 2017-05-16 | 2017-05-24 | 8 | A | MKM | 2018-05-06 | 2018-05-19 | 13 | C | MKM | 2018-06-04 | 2018-06-13 | 9 | B | MKM | [25 empty] | 2018-06-04 | 2018-06-13 | 9 | B | Rev-4 | B | Approved
404 | SD-0059-06 |  | 8th-17th | 8th to 17th Floor Corridor Elevation - 5, 6, 7, 8 | 1252-MKM-05Q-IDP-01-DWG-0713 | 2 OF 3 | 2017-02-19 | 2017-02-26 | 2017-03-07 | 9 | C | MKM | 2017-04-06 | 2017-04-19 | 13 | C | MKM | 2017-05-16 | 2017-05-24 | 8 | B | MKM | 2018-05-06 | 2018-05-19 | 13 | C | MKM | 2018-06-04 | 2018-06-13 | 9 | B | MKM | [25 empty] | 2018-06-04 | 2018-06-13 | 9 | B | Rev-4 | A | Approved
404 | SD-0059-09 |  | 16th | 16th Floor Corridor Partial Plan & Elevation - 10, 11 | 1252-MKM-05Q-IDP-01-DWG-0713 | 3 OF 3 | 2017-02-19 | 2017-02-26 | 2017-03-07 | 9 | C | MKM | 2017-04-06 | 2017-04-19 | 13 | C | MKM | 2017-05-16 | 2017-05-24 | 8 | A | MKM | 2018-05-06 | 2018-05-19 | 13 | C | MKM | 2018-06-04 | 2018-06-13 | 9 | C | MKM | 2018-07-18 | 2018-07-24 | 6 | C | MKM | 2018-07-29 | 2018-08-02 | 4 | B | MKM | [15 empty] | 2018-07-29 | 2018-08-02 | 4 | B | Rev-6 | B | Approved
405 | SD-0059-10 | ARK-0020-00 | 17th | 17th Floor Corridor Reflected Ceiling Plan & Details | 1252-MKM-05Q-IDP-01-DWG-0714 | 1 OF 1 | 2017-02-14 | 2017-02-26 | 2017-03-07 | 9 | B | MKM | 2017-04-06 | 2017-04-19 | 13 | B | MKM | 2017-05-16 | 2017-05-24 | 8 | A | MKM | 2018-02-07 | 2018-02-15 | 8 | B | MKM | 2018-05-06 | 2018-05-19 | 13 | C | MKM | 2018-06-04 | 2018-06-13 | 9 | C | MKM | 2018-07-18 | 2018-07-24 | 6 | B | MKM | 2018-10-09 | 2018-10-21 | 12 | B | MKM | [10 empty] | 2018-10-09 | 2018-10-21 | 12 | B | Rev-7 | B | Approved |  |  | 1 5 | MKM
405 | SD-0065-00 |  | 8th | 8th Floor Reflected Ceiling Layout with Access Panel | 1252-MKM-05Q-IDP-01-DWG-0101A | 1 OF 4 |  | 2017-06-19 | 2017-06-28 | 9 | B | MKM | [45 empty] | 2017-06-19 | 2017-06-28 | 9 | B | Rev-0 | B | Approved
406 | SD-0065-00 |  | 8th | 8th Floor Reflected Ceiling Layout | 1252-MKM-05Q-IDP-01-DWG-0101A | 2 OF 4 |  | 2017-06-19 | 2017-06-28 | 9 | B | MKM | [45 empty] | 2017-06-19 | 2017-06-28 | 9 | B | Rev-0 | B | Approved
406 | SD-0065-00 |  | 8th | 8th Floor Reflected Ceiling Layout | 1252-MKM-05Q-IDP-01-DWG-0101A | 3 OF 4 |  | 2017-06-19 | 2017-06-28 | 9 | B | MKM | [45 empty] | 2017-06-19 | 2017-06-28 | 9 | B | Rev-0 | B | Approved
407 | SD-0065-00 |  | 8th | 8th Floor Reflected Ceiling Layout | 1252-MKM-05Q-IDP-01-DWG-0101A | 4 OF 4 |  | 2017-06-19 | 2017-06-28 | 9 | B | MKM | [45 empty] | 2017-06-19 | 2017-06-28 | 9 | B | Rev-0
Corridor Details, Plan & Elevation @ 19th to 41st Floor | [62 empty] | B | Approved |  |  | 1 204
408 | SD-0060-09 | ARK-0039-00 | 19th-41st | 19th to 41st Corridor Wall Paneling Layout | 1252-MKM-05Q-IDP-01-DWG-0720 | 1 OF 2 | 2017-02-15 | 2017-02-26 | 2017-03-13 | 15 | C | MKM | 2017-04-11 | 2017-04-24 | 13 | C | MKM | 2017-06-07 | 2017-06-19 | 12 | B | MKM | 2018-06-13 | 2018-06-24 | 11 | B | MKM | 2018-11-07 | 2018-12-17 | 40 | B | MKM | [25 empty] | 2018-11-07 | 2018-12-17 | 40 | B | Rev-4 | A | Approved
409 | SD-0060-007 |  | 19th-41st | 19th to 41st Corridor Wall Paneling Layout | 1252-MKM-05Q-IDP-01-DWG-0720 | 2 OF 2 | 2017-02-15 | 2017-04-11 | 2017-04-24 | 13 | C | MKM | 2017-06-07 |  | 810 | OD | MKM | 2017-06-07 | 2017-06-19 | 12 | A | MKM | 2018-06-13 | 2018-06-24 | 11 | B | MKM | 2018-07-11 | 2018-07-17 | 6 | A | MKM | 2018-07-26 | 2018-08-18 | 23 | B | MKM | [20 empty] | 2018-07-26 | 2018-08-18 | 23 | B | Rev-5 | B | Approved
410 | SD-0060-008 |  | 19th-41st | 19th to 41st Floor Corridor Reflected Ceiling Plan | 1252-MKM-05Q-IDP-01-DWG-0721 | 1 OF 1 | 2017-02-16 | 2017-02-26 | 2017-03-13 | 15 | C | MKM | 2017-04-11 | 2017-04-24 | 13 | B | MKM | 2017-06-07 | 2017-06-19 | 12 | B | MKM | 2018-06-13 | 2018-06-24 | 11 | C | MKM | 2018-07-04 | 2018-07-11 | 7 | C | MKM | 2018-07-17 | 2018-07-24 | 7 | A | MKM | 2018-08-28 | 2018-09-03 | 6 | B | MKM | [15 empty] | 2018-08-28 | 2018-09-03 | 6 | B | Rev-6 | A | Approved
411 | SD-0060-09 | ARK-0039-00 | 19th-41st | 19th to 41st Floor Corridor Wall Paneling Elevation- 'A' | 1252-MKM-05Q-IDP-01-DWG-0722 | 1 OF 6 | 2017-02-19 | 2017-02-26 | 2017-03-13 | 15 | C | MKM | 2017-04-11 | 2017-04-24 | 13 | B | MKM | 2017-06-07 | 2017-06-19 | 12 | A | MKM | 2018-06-13 | 2018-06-24 | 11 | B | MKM | 2018-11-07 | 2018-12-17 | 40 | B | MKM | [25 empty] | 2018-11-07 | 2018-12-17 | 40 | B | Rev-4 | A | Approved
412 | SD-0060-09 | ARK-0039-00 | 19th-41st | 19th to 41st Floor Corridor Wall Paneling Elevation- 'B' | 1252-MKM-05Q-IDP-01-DWG-0722 | 2 OF 6 | 2017-02-19 | 2017-02-26 | 2017-03-13 | 15 | C | MKM | 2017-04-11 | 2017-04-24 | 13 | C | MKM | 2017-06-07 | 2017-06-19 | 12 | A | MKM | 2018-06-13 | 2018-06-24 | 11 | B | MKM | 2018-11-07 | 2018-12-17 | 40 | B | MKM | [25 empty] | 2018-11-07 | 2018-12-17 | 40 | B | Rev-4 | A | Approved
413 | SD-0060-09 | ARK-0039-00 | 19th-41st | 19th to 41st Floor Corridor Wall Paneling Elevation- 'C' | 1252-MKM-05Q-IDP-01-DWG-0722 | 3 OF 6 | 2017-02-19 | 2017-02-26 | 2017-03-13 | 15 | C | MKM | 2017-04-11 | 2017-04-24 | 13 | B | MKM | 2017-06-07 | 2017-06-19 | 12 | A | MKM | 2018-06-13 | 2018-06-24 | 11 | B | MKM | 2018-11-07 | 2018-12-17 | 40 | B | MKM | [25 empty] | 2018-11-07 | 2018-12-17 | 40 | B | Rev-4 | A | Approved
414 | SD-0060-09 | ARK-0039-00 | 19th-41st | 19th to 41st Floor Corridor Wall Paneling Elevation- 'D' | 1252-MKM-05Q-IDP-01-DWG-0722 | 4 OF 6 | 2017-02-19 | 2017-02-26 | 2017-03-13 | 15 | C | MKM | 2017-04-11 | 2017-04-24 | 13 | B | MKM | 2017-06-07 | 2017-06-19 | 12 | A | MKM | 2018-06-13 | 2018-06-24 | 11 | B | MKM | 2018-11-07 | 2018-12-17 | 40 | B | MKM | [25 empty] | 2018-11-07 | 2018-12-17 | 40 | B | Rev-4 | A | Approved
415 | SD-0060-09 | ARK-0039-00 | 19th-41st | 19th to 41st Floor Corridor Wall Paneling Elevation- 'E' | 1252-MKM-05Q-IDP-01-DWG-0722 | 5 OF 6 | 2017-02-19 | 2017-02-26 | 2017-03-13 | 15 | C | MKM | 2017-04-11 | 2017-04-24 | 13 | B | MKM | 2017-06-07 | 2017-06-19 | 12 | A | MKM | 2018-06-13 | 2018-06-24 | 11 | B | MKM | 2018-11-07 | 2018-12-17 | 40 | B | MKM | [25 empty] | 2018-11-07 | 2018-12-17 | 40 | B | Rev-4 | A | Approved
416 | SD-0060-09 | ARK-0039-00 | 19th-41st | 19th to 41st Floor Corridor Wall Paneling Elevation- 'F' | 1252-MKM-05Q-IDP-01-DWG-0722 | 6 OF 6 | 2017-02-19 | 2017-02-26 | 2017-03-13 | 15 | C | MKM | 2017-04-11 | 2017-04-24 | 13 | B | MKM | 2017-06-07 | 2017-06-19 | 12 | A | MKM | 2018-06-13 | 2018-06-24 | 11 | B | MKM | 2018-11-07 | 2018-12-17 | 40 | B | MKM | [25 empty] | 2018-11-07 | 2018-12-17 | 40 | B | Rev-4
Corridor Details, Plan & Elevation | [62 empty] | A | Approved |  |  | 1 204
417 | SD-0061-04 | ARK-0038-00 | 24th-41st | 24th to 41st Floor Corridor Wall Panel Layout | 1252-MKM-05Q-IDP-01-DWG-0730 | 1 OF 2 | 2017-02-19 | 2017-03-08 | 2017-03-27 | 19 | C | MKM | 2017-04-11 | 2017-04-25 | 14 | C | MKM | 2017-07-26 | 2017-09-14 | 50 | A | MKM | 2018-11-07 | 2018-12-17 | 40 | B | MKM | [30 empty] | 2018-11-07 | 2018-12-17 | 40 | B | Rev-3 | A | Approved
418 | SD-0061-04 | ARK-0038-00 | 24th-41st | 24th to 41st Floor Corridor Wall Panel Layout | 1252-MKM-05Q-IDP-01-DWG-0730 | 2 OF 2 | 2017-02-19 | 2017-03-08 | 2017-03-27 | 19 | C | MKM | 2017-04-11 | 2017-04-25 | 14 | C | MKM | 2017-07-26 | 2017-09-14 | 50 | A | MKM | 2018-11-07 | 2018-12-17 | 40 | A | MKM | [30 empty] | 2018-11-07 | 2018-12-17 | 40 | A | Rev-3 | A | Approved
419 | SD-0061-02 |  | 24th-41st | 24th to 41st Floor Corridor Reflected Ceiling Plan & Details | 1252-MKM-05Q-IDP-01-DWG-0731 | 1 OF 1 | 2017-02-20 | 2017-03-08 | 2017-03-27 | 19 | C | MKM | 2017-04-11 | 2017-04-25 | 14 | C | MKM | 2017-07-26 | 2017-09-14 | 50 | A | MKM | [35 empty] | 2017-07-26 | 2017-09-14 | 50 | A | Rev-2 | A | Approved |  |  | 1 5 | MKM
420 | SD-0061-04 | ARK-0038-00 | 24th-41st | 19th to 41st Floor Corridor Wall Paneling Elevation- 'A' | 1252-MKM-05Q-IDP-01-DWG-0732 | 1 OF 5 | 2017-02-20 | 2017-03-08 | 2017-03-27 | 19 | C | MKM | 2017-04-11 | 2017-04-25 | 14 | B | MKM | 2017-07-26 | 2017-09-14 | 50 | A | MKM | 2018-11-07 | 2018-12-17 | 40 | B | MKM | [30 empty] | 2018-11-07 | 2018-12-17 | 40 | B | Rev-3 | A | Approved
421 | SD-0061-04 | ARK-0038-00 | 24th-41st | 19th to 41st Floor Corridor Wall Paneling Elevation- 'B' | 1252-MKM-05Q-IDP-01-DWG-0732 | 2 OF 5 | 2017-02-20 | 2017-03-08 | 2017-03-27 | 19 | C | MKM | 2017-04-11 | 2017-04-25 | 14 | B | MKM | 2017-07-26 | 2017-09-14 | 50 | A | MKM | 2018-11-07 | 2018-12-17 | 40 | B | MKM | [30 empty] | 2018-11-07 | 2018-12-17 | 40 | B | Rev-3 | A | Approved
422 | SD-0061-04 | ARK-0038-00 | 24th-41st | 19th to 41st Floor Corridor Wall Paneling Elevation- 'C' | 1252-MKM-05Q-IDP-01-DWG-0732 | 3 OF 5 | 2017-02-20 | 2017-03-08 | 2017-03-27 | 19 | C | MKM | 2017-04-11 | 2017-04-25 | 14 | B | MKM | 2017-07-26 | 2017-09-14 | 50 | A | MKM | 2018-11-07 | 2018-12-17 | 40 | B | MKM | [30 empty] | 2018-11-07 | 2018-12-17 | 40 | B | Rev-3 | A | Approved
423 | SD-0061-04 | ARK-0038-00 | 24th-41st | 24th to 41st Floor Corridor Wall Paneling Elevation 'D' | 1252-MKM-05Q-IDP-01-DWG-0732 | 4 OF 5 | 2017-02-20 | 2017-03-08 | 2017-03-27 | 19 | C | MKM | 2017-04-11 | 2017-04-25 | 14 | B | MKM | 2017-07-26 | 2017-09-14 | 50 | C | MKM | 2017-12-04 | 2017-12-05 | 1 | A | MKM | 2018-11-07 | 2018-12-17 | 40 | B | MKM | [25 empty] | 2018-11-07 | 2018-12-17 | 40 | B | Rev-4 | A | Approved
424 | SD-0061-02 |  | 24th-41st | 24th to 41st Floor Corridor Wall Paneling Elevation 'E & F' | 1252-MKM-05Q-IDP-01-DWG-0732 | 5 OF 5 | 2017-02-20 | 2017-03-08 | 2017-03-27 | 19 | C | MKM | 2017-04-11 | 2017-04-25 | 14 | B | MKM | 2017-07-26 | 2017-09-14 | 50 | A | MKM | [35 empty] | 2017-07-26 | 2017-09-14 | 50 | A | Rev-2
425 | SD-0152-02 | ARK-0049-02 | 24th-29th | 24th 29th Floor Handicapped Guest Room Wardrobe Type - 6 A Detailed Drawing | 1252-MKM-05Q-IDP-01-DWG-0733 | 5 OF 5 | 2017-02-20 | 2017-03-08 | 2017-03-27 | 19 | C | MKM | 2017-04-11 | 2017-04-25 | 14 | B | MKM | 2017-07-26 | 2017-09-14 | 50 | A | MKM | 2019-02-10 | 2019-02-27 | 17 | C | MKM | 2019-03-05 | 2019-03-25 | 20 | C | MKM | 2019-04-02 |  | 146 | B | MKM | [20 empty] | 2019-04-02 | 2019-03-25 | 146 | B | Rev-5
426 | SD-0152-02 | ARK-0049-02 | 24th-29th | 24th 29th Floor Handicapped Guest Room Wardrobe Type - 6 A Detailed Drawing | 1252-MKM-05Q-IDP-01-DWG-0733 | 5 OF 5 | 2017-02-20 | 2017-03-08 | 2017-03-27 | 19 | C | MKM | 2017-04-11 | 2017-04-25 | 14 | B | MKM | 2017-07-26 | 2017-09-14 | 50 | A | MKM | 2019-02-10 | 2019-02-27 | 17 | C | MKM | 2019-03-05 | 2019-03-25 | 20 | C | MKM | 2019-04-02 |  | 146 | B | MKM | [20 empty] | 2019-04-02 | 2019-03-25 | 146 | B | Rev-5
427 | SD-0153-00 | ARK-0050-00 | 19 to 41 | Gypsum upstand tyical details | 1252-MKM-05Q-IDP-01-DWG-0734 | 1 OF 1 |  | 2019-03-04 | 2019-03-14 | 10 | B | MKM | [45 empty] | 2019-03-04 | 2019-03-14 | 10 | B | Rev-0
Corridor Wall Feature | [5 empty] | B | [56 empty] | P |  |  |  | 1 211
428 | SD-0097-00 |  | 8th Floor | 8th Floor Corridor Wall Feature 1 | 1252-MKM-05Q-IDP-01-DWG-0715 | 1 OF 2 |  | 2018-04-03 | 2018-04-09 | 6 | B | MKM |  |  |  | SS | AS PER RAMZI | [40 empty] | 2018-04-03 | 2018-04-09 | 6 | SS | Rev-0 | P |  |  |  | 1 5 | AS PER RAMZI
429 | SD-0097-00 |  | 8th Floor | 8th Floor Corridor Wall Feature 2 | 1252-MKM-05Q-IDP-01-DWG-0715 | 2 OF 2 |  | 2018-04-03 | 2018-04-09 | 6 | B | MKM |  |  |  | SS | AS PER RAMZI | [40 empty] | 2018-04-03 | 2018-04-09 | 6 | SS | Rev-0 | P |  |  |  | 1 5 | AS PER RAMZI
430 | SD-0097-00 |  | 8th Floor | 8th Floor Corridor Wall Feature 1 & 2 Details | 1252-MKM-05Q-IDP-01-DWG-0716 | 1 OF 1 |  | 2018-04-03 | 2018-04-09 | 6 | B | MKM |  |  |  | SS | AS PER RAMZI | [40 empty] | 2018-04-03 | 2018-04-09 | 6 | SS | Rev-0 | P |  |  |  | 1 5 | AS PER RAMZI
431 | SD-0097-00 |  | 8th Floor | 8th Floor Corridor Display Unit | 1252-MKM-05Q-IDP-01-DWG-0717 | 1 OF 1 |  | 2018-04-03 | 2018-04-09 | 6 | C | MKM |  |  |  | SS | AS PER RAMZI | [40 empty] | 2018-04-03 | 2018-04-09 | 6 | SS | Rev-0 |  |  |  |  | 1 5 | AS PER RAMZI
432 | SD-0101-00 |  |  | 901 Maid Room Door - (WD3a) 3 Bedroom Apartment Option 2 | 1252-MKM-05Q-IDP-01-DWG-0718 | 1 OF 1 |  | 2018-06-07 | 2018-06-13 | 6 | B | MKM | [45 empty] | 2018-06-07 | 2018-06-13 | 6 | B | Rev-0 |  |  |  |  | 1 5 | MKM
16TH FLOOR PRIVATE ROOM | [66 empty] | 1 203
100_GENERAL ARRANGEMENT PLANS | [62 empty] | X |  |  |  | 1 211
433 | SD-0069-00 |  | 16th Floor | General Arrangement Plan | 1252-MKM-05Q-IDP-01-PA-0101 | 1 OF 1 | 26-11-2017 | 2017-11-28 | 2018-01-11 | 44 | SS | MKM | [45 empty] | 2017-11-28 | 2018-01-11 | 44 | SS | Rev-0 | X |  |  |  | 1 5 | MKM
434 | SD-0069-00 |  | 16th Floor | Reflected ceiling layout | 1252-MKM-05Q-IDP-01-PA-0102 | 1 OF 1 | 26-11-2017 | 2017-11-28 | 2018-01-11 | 44 | SS | MKM | [45 empty] | 2017-11-28 | 2018-01-11 | 44 | SS | Rev-0 | X |  |  |  | 1 5 | MKM
435 | SD-0069-00 |  | 16th Floor | Wall finishes layout | 1252-MKM-05Q-IDP-01-PA-0103 | 1 OF 1 | 26-11-2017 | 2017-11-28 | 2018-01-11 | 44 | SS | MKM | [45 empty] | 2017-11-28 | 2018-01-11 | 44 | SS | Rev-0 | X |  |  |  | 1 5 | MKM
436 | SD-0069-00 |  | 16th Floor | References layout | 1252-MKM-05Q-IDP-01-PA-0104 | 1 OF 1 | 26-11-2017 | 2017-11-28 | 2018-01-11 | 44 | SS | MKM | [45 empty] | 2017-11-28 | 2018-01-11 | 44 | SS | Rev-0 | X |  |  |  | 1 5 | MKM
437 | SD-0069-00 |  | 16th Floor | Master Bedroom - plans (1of1) | 1252-MKM-05Q-IDP-01-PA-0105 | 1 OF 1 | 26-11-2017 | 2017-11-28 | 2018-01-11 | 44 | SS | MKM | [45 empty] | 2017-11-28 | 2018-01-11 | 44 | SS | Rev-0 | X |  |  |  | 1 5 | MKM
438 | SD-0069-00 |  | 16th Floor | Master Bedroom - Elevations | 1252-MKM-05Q-IDP-01-PA-0106 | 1 OF 2 | 26-11-2017 | 2017-11-28 | 2018-01-11 | 44 | SS | MKM | [45 empty] | 2017-11-28 | 2018-01-11 | 44 | SS | Rev-0 | X |  |  |  | 1 5 | MKM
439 | SD-0069-00 |  | 16th Floor | Master Bedroom - Elevations | 1252-MKM-05Q-IDP-01-PA-0106 | 2 OF 2 | 26-11-2017 | 2017-11-28 | 2018-01-11 | 44 | SS | MKM | [45 empty] | 2017-11-28 | 2018-01-11 | 44 | SS | Rev-0 | X |  |  |  | 1 5 | MKM
440 | SD-0069-00 |  | 16th Floor | Master Dressing & Bath Room - plans | 1252-MKM-05Q-IDP-01-PA-0107 | 1 OF 1 | 26-11-2017 | 2017-11-28 | 2018-01-11 | 44 | SS | MKM | [45 empty] | 2017-11-28 | 2018-01-11 | 44 | SS | Rev-0 | X |  |  |  | 1 5 | MKM
441 | SD-0069-00 |  | 16th Floor | Master Dressing & Bath Room - Elevations | 1252-MKM-05Q-IDP-01-PA-0108 | 1 OF 2 | 29-11-2017 | 2017-11-28 | 2018-01-11 | 44 | SS | MKM | [45 empty] | 2017-11-28 | 2018-01-11 | 44 | SS | Rev-0 | X |  |  |  | 1 5 | MKM
442 | SD-0069-00 |  | 16th Floor | Master Dressing & Bath Room - Elevations | 1252-MKM-05Q-IDP-01-PA-0108 | 2 OF 2 | 29-11-2017 | 2017-11-28 | 2018-01-11 | 44 | SS | MKM | [45 empty] | 2017-11-28 | 2018-01-11 | 44 | SS | Rev-0 | X |  |  |  | 1 5 | MKM
443 | SD-0070-00 |  | 16th Floor | Twin Bedroom,Dressing,Bathroom & Gym - plans | 1252-MKM-05Q-IDP-01-PA-0109 | 1 OF 1 | 26-11-2017 | 2017-11-28 | 2018-01-30 | 63 | SS | MKM | [45 empty] | 2017-11-28 | 2018-01-30 | 63 | SS | Rev-0 | X |  |  |  | 1 5 | MKM
444 | SD-0070-00 |  | 16th Floor | Zone C Twin Bedroom,Dressing,Bathroom & Gym - Elevations | 1252-MKM-05Q-IDP-01-PA-0110 | 1 OF 2 | 26-11-2017 | 2017-11-28 | 2018-01-30 | 63 | SS | MKM | [45 empty] | 2017-11-28 | 2018-01-30 | 63 | SS | Rev-0 | X |  |  |  | 1 5 | MKM
445 | SD-0070-00 |  | 16th Floor | Zone C Twin Bedroom,Dressing,Bathroom & Gym - Elevations | 1252-MKM-05Q-IDP-01-PA-0110 | 2 OF 2 | 26-11-2017 | 2017-11-28 | 2018-01-30 | 63 | SS | MKM | [45 empty] | 2017-11-28 | 2018-01-30 | 63 | SS | Rev-0 | X |  |  |  | 1 5 | MKM
446 | SD-0070-00 |  | 16th Floor | Zone D Living Room - plans | 1252-MKM-05Q-IDP-01-PA-0111 | 1 OF 1 | 26-11-2017 | 2017-11-28 | 2018-01-30 | 63 | SS | MKM | [45 empty] | 2017-11-28 | 2018-01-30 | 63 | SS | Rev-0 | X |  |  |  | 1 5 | MKM
447 | SD-0070-00 |  | 16th Floor | Zone D Living Room - Elevations | 1252-MKM-05Q-IDP-01-PA-0112 | 1 OF 2 | 26-11-2017 | 2017-11-28 | 2018-01-30 | 63 | SS | MKM | [45 empty] | 2017-11-28 | 2018-01-30 | 63 | SS | Rev-0 | X |  |  |  | 1 5 | MKM
448 | SD-0070-00 |  | 16th Floor | Zone D Living Room - Elevations | 1252-MKM-05Q-IDP-01-PA-0112 | 2 OF 2 | 26-11-2017 | 2017-11-28 | 2018-01-30 | 63 | SS | MKM | [45 empty] | 2017-11-28 | 2018-01-30 | 63 | SS | Rev-0 | X |  |  |  | 1 5 | MKM
449 | SD-0070-00 |  | 16th Floor | Zone E Dining Room & Studio - Plans | 1252-MKM-05Q-IDP-01-PA-0113 | 1 OF 1 | 26-11-2017 | 2017-11-28 | 2018-01-30 | 63 | SS | MKM | [45 empty] | 2017-11-28 | 2018-01-30 | 63 | SS | Rev-0 | X |  |  |  | 1 5 | MKM
450 | SD-0070-00 |  | 16th Floor | Zone E Dining Room & Studio - Elevations | 1252-MKM-05Q-IDP-01-PA-0114 | 1 OF 2 | 29-11-2017 | 2017-11-28 | 2018-01-30 | 63 | SS | MKM | [45 empty] | 2017-11-28 | 2018-01-30 | 63 | SS | Rev-0 | X |  |  |  | 1 5 | MKM
451 | SD-0070-00 |  | 16th Floor | Zone E Dining Room & Studio - Elevations | 1252-MKM-05Q-IDP-01-PA-0114 | 2 OF 2 | 29-11-2017 | 2017-11-28 | 2018-01-30 | 63 | SS | MKM | [45 empty] | 2017-11-28 | 2018-01-30 | 63 | SS | Rev-0 |  |  |  |  | 1 5 | MKM
300_MILLWORK DETAILS | [62 empty] | X |  |  |  | 1 211
452 |  |  | 16th Floor | Wall cladding details | 1252-MKM-05Q-IDP-01-PA-0301 | 1 OF 1 | 29-11-2017 |  |  |  | SS | [49 empty] | SS |  | X |  |  |  | 1 5 | 0
453 |  |  | 16th Floor | Wall cladding details | 1252-MKM-05Q-IDP-01-PA-0302 | 1 OF 1 | 29-11-2017 |  |  |  | SS | [49 empty] | SS |  | X |  |  |  | 1 5 | 0
454 |  |  | 16th Floor | Wall cladding details | 1252-MKM-05Q-IDP-01-PA-0303 | 1 OF 1 | 29-11-2017 |  |  |  | SS | [49 empty] | SS |  | X |  |  |  | 1 5 | 0
455 |  |  | 16th Floor | Wall cladding details | 1252-MKM-05Q-IDP-01-PA-0304 | 1 OF 1 | 29-11-2017 |  |  |  | SS | [49 empty] | SS |  | X |  |  |  | 1 5 | 0
456 | SD-0071-00 |  | 16th Floor | TV unit - Living room | 1252-MKM-05Q-IDP-01-PA-0305 | 1 OF 1 | 26-11-2017 | 2017-11-28 |  | 636 | SS | MKM | [45 empty] | 2017-11-28 |  | 636 | SS | Rev-0 | X |  |  |  | 1 5 | MKM
457 | SD-0071-00 |  | 16th Floor | Shelving unit - Master bedroom | 1252-MKM-05Q-IDP-01-PA-0306 | 1 OF 1 | 26-11-2017 | 2017-11-28 |  | 636 | SS | MKM | [45 empty] | 2017-11-28 |  | 636 | SS | Rev-0 | X |  |  |  | 1 5 | MKM
458 | SD-0071-00 |  | 16th Floor | Vanity unit - Guest toilet | 1252-MKM-05Q-IDP-01-PA-0307 | 1 OF 1 | 26-11-2017 | 2017-11-28 |  | 636 | SS | MKM | [45 empty] | 2017-11-28 |  | 636 | SS | Rev-0 | X |  |  |  | 1 5 | MKM
459 | SD-0071-00 |  | 16th Floor | Vanity unit - Twin toilet | 1252-MKM-05Q-IDP-01-PA-0308 | 1 OF 1 | 26-11-2017 | 2017-11-28 |  | 636 | SS | MKM | [45 empty] | 2017-11-28 |  | 636 | SS | Rev-0 | X |  |  |  | 1 5 | MKM
460 | SD-0071-00 |  | 16th Floor | Vanity unit - Master bedroom | 1252-MKM-05Q-IDP-01-PA-0309 | 1 OF 1 | 26-11-2017 | 2017-11-28 |  | 636 | SS | MKM | [45 empty] | 2017-11-28 |  | 636 | SS | Rev-0 | X |  |  |  | 1 5 | MKM
461 |  |  | 16th Floor | Wardrobe details - Twin bedroom | 1252-MKM-05Q-IDP-01-PA-0310 | 1 OF 1 | 29-11-2017 |  |  |  | SS | [49 empty] | SS |  | X |  |  |  | 1 5 | 0
462 |  |  | 16th Floor | Wardrobe details - Twin bedroom | 1252-MKM-05Q-IDP-01-PA-0311 | 1 OF 1 | 29-11-2017 |  |  |  | SS | [49 empty] | SS |  | X |  |  |  | 1 5 | 0
463 |  |  | 16th Floor | Wardrobe details - Master bedroom | 1252-MKM-05Q-IDP-01-PA-0312 | 1 OF 1 | 29-11-2017 |  |  |  | SS | [49 empty] | SS |  | X |  |  |  | 1 5 | 0
464 |  |  | 16th Floor | Pantry unit details | 1252-MKM-05Q-IDP-01-PA-0314 | 1 OF 1 | 29-11-2017 |  |  |  | SS | [49 empty] | SS |  | X |  |  |  | 1 5 | 0
465 | SD-0071-00 |  | 16th Floor | Gym flooring details | 1252-MKM-05Q-IDP-01-PA-0315 | 1 OF 1 | 26-11-2017 | 2017-11-28 |  | 636 | SS | MKM | [45 empty] | 2017-11-28 |  | 636 | SS | Rev-0 | X |  |  |  | 1 5 | MKM
466 |  |  | 16th Floor | Door handles detail | 1252-MKM-05Q-IDP-01-PA-0316 | 1 OF 1 | 29-11-2017 |  |  |  | SS | [49 empty] | SS |  | X |  |  |  | 1 5 | 0
467 |  |  | 16th Floor | Ceiling details | 1252-MKM-05Q-IDP-01-PA-0317 | 1 OF 1 | 29-11-2017 |  |  |  | SS | [49 empty] | SS | [5 empty] | 1 5 | 0
500_DOORS | [62 empty] | X |  |  |  | 1 211
468 | SD-0072-00 |  | 16th Floor | Door schedule Private Room @ 16th Floor | 1252-MKM-05Q-IDP-01-PA-0500 | 1 OF 1 | 26-11-2017 | 2017-11-28 | 2017-12-12 | 14 | SS | MKM | [45 empty] | 2017-11-28 | 2017-12-12 | 14 | SS | Rev-0 | X |  |  |  | 1 5 | MKM
469 | SD-0072-00 |  | 16th Floor | Main Double Doors Details (WD04) | 1252-MKM-05Q-IDP-01-PA-0501 | 1 OF 1 | 26-11-2017 | 2017-11-28 | 2017-12-12 | 14 | SS | MKM | [45 empty] | 2017-11-28 | 2017-12-12 | 14 | SS | Rev-0 | X |  |  |  | 1 5 | MKM
470 |  |  | 16th Floor | Kitchen Door Details (WD05) | 1252-MKM-05Q-IDP-01-PA-0502 | 1 OF 1 | 29-11-2017 |  |  |  | SS | [49 empty] | SS |  | X |  |  |  | 1 5 | 0
471 |  |  | 16th Floor | Sliding Door Details @ Dining Room (WD06) | 1252-MKM-05Q-IDP-01-PA-0503 | 1 OF 1 | 29-11-2017 |  |  |  | SS | [49 empty] | SS |  | X |  |  |  | 1 5 | 0
472 | SD-0072-00 |  | 16th Floor | Master Bed Room/Passage Door (WD07) | 1252-MKM-05Q-IDP-01-PA-0504 | 1 OF 1 | 26-11-2017 | 2017-11-28 | 2017-12-12 | 14 | SS | MKM | [45 empty] | 2017-11-28 | 2017-12-12 | 14 | SS | Rev-0 | X |  |  |  | 1 5 | MKM
473 | SD-0072-00 |  | 16th Floor | Guest Toilet Door (WD08) | 1252-MKM-05Q-IDP-01-PA-0505 | 1 OF 1 | 26-11-2017 | 2017-11-28 | 2017-12-12 | 14 | SS | MKM | [45 empty] | 2017-11-28 | 2017-12-12 | 14 | SS | Rev-0 | X |  |  |  | 1 5 | MKM
474 | SD-0072-00 |  | 16th Floor | Storage Door (WD09) | 1252-MKM-05Q-IDP-01-PA-0506 | 1 OF 1 | 26-11-2017 | 2017-11-28 | 2017-12-12 | 14 | SS | MKM | [45 empty] | 2017-11-28 | 2017-12-12 | 14 | SS | Rev-0 | X |  |  |  | 1 5 | MKM
475 | SD-0072-00 |  | 16th Floor | Twin Bedroom Door (WD10) | 1252-MKM-05Q-IDP-01-PA-0507 | 1 OF 1 | 26-11-2017 | 2017-11-28 | 2017-12-12 | 14 | SS | MKM | [45 empty] | 2017-11-28 | 2017-12-12 | 14 | SS | Rev-0 | X |  |  |  | 1 5 | MKM
476 |  |  |  | Twin Dresser Door (WD14) | 1252-MKM-05Q-IDP-01-PA-0508 | 1 OF 1 | 26-11-2017 |  |  |  | SS | [49 empty] | SS |  | X |  |  |  | 1 5 | 0
477 |  |  |  | Twin Bathroom Door (WD15) | 1252-MKM-05Q-IDP-01-PA-0509 | 1 OF 1 | 26-11-2017 |  |  |  | SS | [49 empty] | SS |  | X
478 | SD-0072-00 |  | 16th Floor | Gym door (WD16) | 1252-MKM-05Q-IDP-01-PA-0510 | 1 OF 1 | 26-11-2017 | 2017-11-28 | 2017-12-12 | 14 | SS | MKM | [45 empty] | 2017-11-28 | 2017-12-12 | 14 | SS | Rev-0 | X
479 | SD-0072-00 |  | 16th Floor | Master Dresser Door (WD17) | 1252-MKM-05Q-IDP-01-PA-0511 | 1 OF 1 | 26-11-2017 | 2017-11-28 | 2017-12-12 | 14 | SS | MKM | [45 empty] | 2017-11-28 | 2017-12-12 | 14 | SS | Rev-0 | X
480 |  |  |  | Master Bathroom Door (WD18) | 1252-MKM-05Q-IDP-01-PA-0512 | 1 OF 1 | 29-11-2017 |  |  |  | SS | [49 empty] | SS |  | 0 |  |  |  | 1 5 | 0
16TH FLOOR PRIVATE ROOM | [66 empty] | 1 203
100_GENERAL ARRANGEMENT PLANS | [62 empty] | B | Approved |  |  | 1 211
481 | SD-0084-00 |  | 16th Floor | 16th Floor Private Apartment General Arrangement Layout | 1252-MKM-05Q-IDP-01-PA-0101 | 1 OF 1 |  | 2018-02-18 | 2018-03-19 | 29 | B | MKM | [45 empty] | 2018-02-18 | 2018-03-19 | 29 | B | Rev-0 | B | Approved |  |  | 1 5 | MKM
482 | SD-0084-00 |  | 16th Floor | 16th Floor Private Apartment Reflected Ceiling Layout | 1252-MKM-05Q-IDP-01-PA-0102 | 1 OF 1 |  | 2018-02-18 | 2018-03-19 | 29 | B | MKM | [45 empty] | 2018-02-18 | 2018-03-19 | 29 | B | Rev-0 | B | Approved |  |  | 1 5 | MKM
483 | SD-0084-00 |  | 16th Floor | 16th Floor Private Apartment Wall Finishes Layout | 1252-MKM-05Q-IDP-01-PA-0103 | 1 OF 1 |  | 2018-02-18 | 2018-03-19 | 29 | B | MKM | [45 empty] | 2018-02-18 | 2018-03-19 | 29 | B | Rev-0 | B | Approved |  |  | 1 5 | MKM
484 | SD-0084-00 |  | 16th Floor | 16th Floor Private Apartment References Layout | 1252-MKM-05Q-IDP-01-PA-0104 | 1 OF 1 |  | 2018-02-18 | 2018-03-19 | 29 | B | MKM | [45 empty] | 2018-02-18 | 2018-03-19 | 29 | B | Rev-0 | C | Resub..reqd | 2018-04-09 |  | 1 5 | MKM
485 | SD-0080-01 |  | 16th Floor | 16th Floor Private Apartment Master Bedroom General Arrangement Plan | 1252-MKM-05Q-IDP-01-PA-0105 | 1 OF 4 |  | 2018-02-18 | 2018-03-19 | 29 | C | MKM | 2018-04-18 | 2018-04-23 | 5 | A | MKM | [40 empty] | 2018-04-18 | 2018-04-23 | 5 | A | Rev-1 | C | Resub..reqd | 2018-04-09 |  | 1 5 | MKM
486 | SD-0080-01 |  | 16th Floor | 16th Floor Private Apartment Master Bedroom Reflected Ceiling Plan | 1252-MKM-05Q-IDP-01-PA-0105 | 2 OF 4 |  | 2018-04-18 | 2018-04-23 | 5 | B | MKM | [45 empty] | 2018-04-18 | 2018-04-23 | 5 | B | Rev-0 | C | Resub..reqd | 2018-04-09 |  | 1 5 | MKM
487 | SD-0080-01 |  | 16th Floor | 16th Floor Private Apartment Master Bedroom Wall Finishes Plan | 1252-MKM-05Q-IDP-01-PA-0105 | 3 OF 4 |  | 2018-04-18 | 2018-04-23 | 5 | A | MKM | [45 empty] | 2018-04-18 | 2018-04-23 | 5 | A | Rev-0 | C | Resub..reqd | 2018-04-09 |  | 1 5 | MKM
488 | SD-0080-01 |  | 16th Floor | 16th Floor Private Apartment Master Bedroom Flooring & Power Plan | 1252-MKM-05Q-IDP-01-PA-0105 | 4 OF 4 |  | 2018-04-18 | 2018-04-23 | 5 | B | MKM | [45 empty] | 2018-04-18 | 2018-04-23 | 5 | B | Rev-0 | C | Resub..reqd | 2018-04-09 |  | 1 5 | MKM
489 | SD-0080-02 | ARK-0052-00 | 16th Floor | 16th Floor Private Apartment Master Bedroom Elevations 1, 2, 3 & 4 | 1252-MKM-05Q-IDP-01-PA-0106 | 1 OF 2 |  | 2018-02-18 | 2018-03-19 | 29 | C | MKM | 2018-04-18 | 2018-04-23 | 5 | B | MKM | 2019-03-30 | 2019-04-16 | 17 | A | MKM | [35 empty] | 2019-03-30 | 2019-04-16 | 17 | A | Rev-2 | C | Resub..reqd | 2018-04-09 |  | 1 5 | MKM
490 | SD-0080-02 | ARK-0052-00 | 16th Floor | 16th Floor Private Apartment Master Bedroom Elevations 5, 6, 7 & 8 | 1252-MKM-05Q-IDP-01-PA-0106 | 2 OF 2 |  | 2018-02-18 | 2018-03-19 | 29 | C | MKM | 2018-04-18 | 2018-04-23 | 5 | B | MKM | 2019-03-30 | 2019-04-16 | 17 | A | MKM | [35 empty] | 2019-03-30 | 2019-04-16 | 17 | A | Rev-2 | B | Approved |  |  | 1 5 | MKM
491 | SD-0081-01 |  | 16th Floor | 16th Floor Private Apartment Master Dresser & Bathroom Plans | 1252-MKM-05Q-IDP-01-PA-0107 | 1 OF 2 |  | 2018-02-18 | 2018-03-28 | 38 | B | MKM | 2018-04-15 | 2018-04-18 | 3 | B | MKM | [40 empty] | 2018-04-15 | 2018-04-18 | 3 | B | Rev-1 | B | Approved |  |  | 1 5 | MKM
492 | SD-0081-01 |  | 16th Floor | 16th Floor Private Apartment Master Dresser & Bathroom Plans | 1252-MKM-05Q-IDP-01-PA-0107 | 2 OF 2 |  | 2018-02-18 | 2018-03-28 | 38 | B | MKM | 2018-04-15 | 2018-04-18 | 3 | B | MKM | [40 empty] | 2018-04-15 | 2018-04-18 | 3 | B | Rev-1 | C | Resub..reqd | 2018-04-09 |  | 1 5 | MKM
493 | SD-0081-01 |  | 16th Floor | 16th Floor Private Apartment Master Dresser & Bathroom Elevations 1, 2 & 3 | 1252-MKM-05Q-IDP-01-PA-0108 | 1 OF 2 |  | 2018-02-18 | 2018-03-28 | 38 | C | MKM | 2018-04-15 | 2018-04-18 | 3 | B | MKM | [40 empty] | 2018-04-15 | 2018-04-18 | 3 | B | Rev-1 | C | Resub..reqd | 2018-04-09 |  | 1 5 | MKM
494 | SD-0081-01 |  | 16th Floor | 16th Floor Private Apartment Master Dresser & Bathroom Elevations 4, 5, 6 & 7 | 1252-MKM-05Q-IDP-01-PA-0108 | 2 OF 2 |  | 2018-02-18 | 2018-03-28 | 38 | C | MKM | 2018-04-15 | 2018-04-18 | 3 | B | MKM | [40 empty] | 2018-04-15 | 2018-04-18 | 3 | B | Rev-1 | C | Resub..reqd | 2018-04-09 |  | 1 5 | MKM
495 | SD-0086-04 |  | 16th Floor | 16th Floor Private Apartment Twin Bedroom, Dressing, Bathroom, Gym & Guest Retroom General Arrangement Plan | 1252-MKM-05Q-IDP-01-PA-0109 | 1 OF 4 |  | 2018-02-18 | 2018-03-19 | 29 | C | MKM | 2018-04-17 | 2018-04-26 | 9 | B | MKM | 2018-07-12 | 2018-07-17 | 5 | B | MKM | 2018-07-31 | 2018-08-02 | 2 | B | MKM | [30 empty] | 2018-07-31 | 2018-08-02 | 2 | B | Rev-3 | C | Resub..reqd | 2018-04-09 |  | 1 5 | MKM
496 | SD-0086-03 |  | 16th Floor | 16th Floor Private Apartment Twin Bedroom, Dressing, Bathroom & Gym Plan | 1252-MKM-05Q-IDP-01-PA-0109 | 2 OF 4 |  | 2018-04-17 | 2018-04-26 | 9 | B | MKM | 2018-07-12 | 2018-07-17 | 5 | B | MKM | [40 empty] | 2018-07-12 | 2018-07-17 | 5 | B | Rev-1 | C | Resub..reqd | 2018-04-09 |  | 1 5 | MKM
497 | SD-0086-01 |  | 16th Floor | 16th Floor Private Apartment Twin Bedroom, Dressing, Bathroom & Gym Plan | 1252-MKM-05Q-IDP-01-PA-0109 | 3 OF 4 |  | 2018-04-17 | 2018-04-26 | 9 | A | MKM | [45 empty] | 2018-04-17 | 2018-04-26 | 9 | A | Rev-0 | C | Resub..reqd | 2018-04-09 |  | 1 5 | MKM
498 | SD-0086-01 |  | 16th Floor | 16th Floor Private Apartment Twin Bedroom, Dressing, Bathroom & Gym Plan | 1252-MKM-05Q-IDP-01-PA-0109 | 4 OF 4 |  | 2018-04-17 | 2018-04-26 | 9 | B | MKM | [45 empty] | 2018-04-17 | 2018-04-26 | 9 | B | Rev-0 | C | Resub..reqd | 2018-04-09 |  | 1 5 | MKM
499 | SD-0086-04 |  | 16th Floor | 16th Floor Private Apartment Twin Bedroom, Dressing, Bathroom & Gym Elevation 1,2,3,4 | 1252-MKM-05Q-IDP-01-PA-0110 | 1 OF 2 |  | 2018-02-18 | 2018-03-19 | 29 | C | MKM | 2018-04-17 | 2018-04-26 | 9 | B | MKM | 2018-07-31 | 2018-08-02 | 2 | A | MKM | [35 empty] | 2018-07-31 | 2018-08-02 | 2 | A | Rev-2 | C | Resub..reqd | 2018-04-09 |  | 1 5 | MKM
500 | SD-0086-04 |  | 16th Floor | 16th Floor Private Apartment Twin Bedroom, Dressing, Bathroom & Gym Elevation 5, 6, 7, 8, 9 | 1252-MKM-05Q-IDP-01-PA-0110 | 2 OF 2 |  | 2018-02-18 | 2018-03-19 | 29 | C | MKM | 2018-04-17 | 2018-04-26 | 9 | B | MKM | 2018-07-31 | 2018-08-02 | 2 | B | MKM | [35 empty] | 2018-07-31 | 2018-08-02 | 2 | B | Rev-2 | C | Resub..reqd | 2018-04-09 |  | 1 5 | MKM
501 | SD-0085-01 |  | 16th Floor | 16th Floor Private Apartment Living Room General Arrangement Plan | 1252-MKM-05Q-IDP-01-PA-0111 | 1 OF 4 |  | 2018-02-18 | 2018-03-21 | 31 | C | MKM | 2018-04-16 | 2018-04-26 | 10 | A | MKM | [40 empty] | 2018-04-16 | 2018-04-26 | 10 | A | Rev-1 | C | Resub..reqd | 2018-04-09 |  | 1 5 | MKM
502 | SD-0085-01 |  | 16th Floor | 16th Floor Private Apartment Living Room Reflected Ceiling Plan | 1252-MKM-05Q-IDP-01-PA-0111 | 2 OF 4 |  | 2018-04-16 | 2018-04-26 | 10 | B | MKM | [45 empty] | 2018-04-16 | 2018-04-26 | 10 | B | Rev-0 | C | Resub..reqd | 2018-04-09 |  | 1 5 | MKM
503 | SD-0085-01 |  | 16th Floor | 16th Floor Private Apartment Living Room Wall Finishes Plan | 1252-MKM-05Q-IDP-01-PA-0111 | 3 OF 4 |  | 2018-04-16 | 2018-04-26 | 10 | A | MKM | [45 empty] | 2018-04-16 | 2018-04-26 | 10 | A | Rev-0 | C | Resub..reqd | 2018-04-09 |  | 1 5 | MKM
504 | SD-0085-01 |  | 16th Floor | 16th Floor Private Apartment Living Room Floor Finish & Power Plan | 1252-MKM-05Q-IDP-01-PA-0111 | 4 OF 4 |  | 2018-04-16 | 2018-04-26 | 10 | B | MKM | [45 empty] | 2018-04-16 | 2018-04-26 | 10 | B | Rev-0 | C | Resub..reqd | 2018-04-09 |  | 1 5 | MKM
505 | SD-0085-01 |  | 16th Floor | 16th Floor Private Apartment Living Room Elevations 1 & 2 | 1252-MKM-05Q-IDP-01-PA-0112 | 1 OF 2 |  | 2018-02-18 | 2018-03-21 | 31 | C | MKM | 2018-04-24 | 2018-04-26 | 2 | A | MKM | [40 empty] | 2018-04-24 | 2018-04-26 | 2 | A | Rev-1 | C | Resub..reqd | 2018-04-09 |  | 1 5 | MKM
506 | SD-0085-01 |  | 16th Floor | 16th Floor Private Apartment Living Room Elevations 3 & 4 | 1252-MKM-05Q-IDP-01-PA-0112 | 2 OF 2 |  | 2018-02-18 | 2018-03-21 | 31 | C | MKM | 2018-04-24 | 2018-04-26 | 2 | A | MKM | [40 empty] | 2018-04-24 | 2018-04-26 | 2 | A | Rev-1 | B | Approved |  |  | 1 5 | MKM
507 | SD-0082-01 |  | 16th Floor | 16th Floor Private Apartment Dining Room & Studio General Arrangement Plan | 1252-MKM-05Q-IDP-01-PA-0113 | 1 OF 4 |  | 2018-02-18 | 2018-03-24 | 34 | B | MKM | 2018-04-16 | 2018-04-23 | 7 | A | MKM | [40 empty] | 2018-04-16 | 2018-04-23 | 7 | A | Rev-1 | C | Resub..reqd | 2018-04-09 |  | 1 5 | MKM
508 | SD-0082-02 |  | 16th Floor | 16th Floor Private Apartment Dining Room & Studio Reflected Ceiling Plan | 1252-MKM-05Q-IDP-01-PA-0113 | 2 OF 4 |  | 2018-04-16 | 2018-04-23 | 7 | B | MKM | 2018-07-11 | 2018-07-17 | 6 | B | MKM | [40 empty] | 2018-07-11 | 2018-07-17 | 6 | B | Rev-1 | C | Resub..reqd | 2018-04-09 |  | 1 5 | MKM
509 | SD-0082-01 |  | 16th Floor | 16th Floor Private Apartment Dining Room & Studio Wall Finishing Plan | 1252-MKM-05Q-IDP-01-PA-0113 | 3 OF 4 |  | 2018-04-16 | 2018-04-23 | 7 | A | MKM | [45 empty] | 2018-04-16 | 2018-04-23 | 7 | A | Rev-0 | C | Resub..reqd | 2018-04-09 |  | 1 5 | MKM
510 | SD-0082-01 |  | 16th Floor | 16th Floor Private Apartment Dining Room & Studio Flooring & Power Plan | 1252-MKM-05Q-IDP-01-PA-0113 | 4 OF 4 |  | 2018-04-16 | 2018-04-23 | 7 | B | MKM | [45 empty] | 2018-04-16 | 2018-04-23 | 7 | B | Rev-0 | C | Resub..reqd | 2018-04-09 |  | 1 5 | MKM
511 | SD-0082-01 |  | 16th Floor | 16th Floor Private Apartment Dining Room & Studio Elevation 1, 2, 3 & 4 | 1252-MKM-05Q-IDP-01-PA-0114 | 1 OF 2 |  | 2018-02-18 | 2018-03-24 | 34 | C | MKM | 2018-04-16 | 2018-04-23 | 7 | B | MKM | [40 empty] | 2018-04-16 | 2018-04-23 | 7 | B | Rev-1 | C | Resub..reqd | 2018-04-09 |  | 1 5 | MKM
512 | SD-0082-01 |  | 16th Floor | 16th Floor Private Apartment Dining Room & Studio Elevation 5, 6 & 7 | 1252-MKM-05Q-IDP-01-PA-0114 | 2 OF 2 |  | 2018-02-18 | 2018-03-24 | 34 | C | MKM | 2018-04-16 | 2018-04-23 | 7 | A | MKM | [40 empty] | 2018-04-16 | 2018-04-23 | 7 | A | Rev-1 | C | Resub..reqd | 2018-04-09 |  | 1 5 | MKM
513 | SD-0086-05 |  | 16th Floor | 16th Floor Private Apartment Guest Rest Room & Passage Elevations | 1252-MKM-05Q-IDP-01-PA-0115 | 1 OF 1 |  | 2018-02-18 | 2018-03-19 | 29 | C | MKM | 2018-04-17 | 2018-04-26 | 9 | B | MKM | 2018-08-02 | 2018-08-05 | 3 | A | MKM | [35 empty] | 2018-08-02 | 2018-08-05 | 3 | A | Rev-2 |  |  |  |  | 1 5 | MKM
300_MILLWORK DETAILS | [62 empty] | C | Resub..reqd | 2018-04-09 |  | 1 211
514 | SD-0080-01 |  | 16th Floor | 16th Floor Private Apartment Blow Up Details | 1252-MKM-05Q-IDP-01-PA-0301 | 1 OF 2 |  | 2018-02-18 | 2018-03-19 | 29 | C | MKM | 2018-04-18 | 2018-04-23 | 5 | B | MKM | [40 empty] | 2018-04-18 | 2018-04-23 | 5 | B | Rev-1 | C | Resub..reqd | 2018-04-09 |  | 1 5 | MKM
515 | SD-0080-01 |  | 16th Floor | 16th Floor Private Apartment Master Bedroom Plans | 1252-MKM-05Q-IDP-01-PA-0301 | 2 OF 2 |  | 2018-02-18 | 2018-03-19 | 29 | C | MKM | 2018-04-18 | 2018-04-23 | 5 | B | MKM | [40 empty] | 2018-04-18 | 2018-04-23 | 5 | B | Rev-1 | C | Resub..reqd | 2018-04-09 |  | 1 5 | MKM
516 | SD-0086-01 |  | 16th Floor | 16th Floor Private Apartment Twin Bedroom, Dressing, Bathroom & Gym Details | 1252-MKM-05Q-IDP-01-PA-0302 | 1 OF 2 |  | 2018-02-18 | 2018-03-19 | 29 | C | MKM | 2018-04-17 | 2018-04-26 | 9 | B | MKM | [40 empty] | 2018-04-17 | 2018-04-26 | 9 | B | Rev-1 | C | Resub..reqd | 2018-04-09 |  | 1 5 | MKM
517 | SD-0086-01 |  | 16th Floor | 16th Floor Private Apartment Twin Bedroom, Dressing, Bathroom & Gym Details | 1252-MKM-05Q-IDP-01-PA-0302 | 2 OF 2 |  | 2018-02-18 | 2018-03-19 | 29 | C | MKM | 2018-04-17 | 2018-04-26 | 9 | B | MKM | [40 empty] | 2018-04-17 | 2018-04-26 | 9 | B | Rev-1 | C | Resub..reqd | 2018-04-09 |  | 1 5 | MKM
518 | SD-0085-01 |  | 16th Floor | 16th Floor Private Apartment Ceiling Typical Details | 1252-MKM-05Q-IDP-01-PA-0303 | 1 OF 1 |  | 2018-02-18 | 2018-03-21 | 31 | C | MKM | 2018-04-16 | 2018-04-26 | 10 | B | MKM | [40 empty] | 2018-04-16 | 2018-04-26 | 10 | B | Rev-1 | C | Resub..reqd | 2018-04-09 |  | 1 5 | MKM
519 | SD-0082-01 |  | 16th Floor | 16th Floor Private Apartment Dining Room & Studio Typical Details | 1252-MKM-05Q-IDP-01-PA-0304 | 1 OF 1 |  | 2018-02-18 | 2018-03-24 | 34 | C | MKM | 2018-04-16 | 2018-04-23 | 7 | A | MKM | [40 empty] | 2018-04-16 | 2018-04-23 | 7 | A | Rev-1 | C | Resub..reqd | 2018-04-09 |  | 1 5 | MKM
520 | SD-0085-01 |  | 16th Floor | 16th Floor Private Apartment Living Room TV Unit Detail | 1252-MKM-05Q-IDP-01-PA-0305 | 1 OF 1 |  | 2018-02-18 | 2018-03-21 | 31 | C | MKM | 2018-04-16 | 2018-04-26 | 10 | B | MKM | [40 empty] | 2018-04-16 | 2018-04-26 | 10 | B | Rev-1 | C | Resub..reqd | 2018-04-09 |  | 1 5 | MKM
521 | SD-0080-01 |  | 16th Floor | 16th Floor Private Apartment Master Bedroom Shelf Details | 1252-MKM-05Q-IDP-01-PA-0306 | 1 OF 1 |  | 2018-02-18 | 2018-03-19 | 29 | C | MKM | 2018-04-18 | 2018-04-23 | 5 | B | MKM | [40 empty] | 2018-04-18 | 2018-04-23 | 5 | B | Rev-1 | C | Resub..reqd | 2018-04-09 |  | 1 5 | MKM
522 | SD-0086-01 |  | 16th Floor | 16th Floor Private Apartment Guest Toilet Vanity Unit Detail | 1252-MKM-05Q-IDP-01-PA-0307 | 1 OF 1 |  | 2018-02-18 | 2018-03-19 | 29 | C | MKM | 2018-04-17 | 2018-04-26 | 9 | B | MKM | [40 empty] | 2018-04-17 | 2018-04-26 | 9 | B | Rev-1 | C | Resub..reqd | 2018-04-09 |  | 1 5 | MKM
523 | SD-0086-01 |  | 16th Floor | 16th Floor Private Apartment Twin Toilet Vanity Unit Detail | 1252-MKM-05Q-IDP-01-PA-0308 | 1 OF 1 |  | 2018-02-18 | 2018-03-19 | 29 | C | MKM | 2018-04-17 | 2018-04-26 | 9 | B | MKM | [40 empty] | 2018-04-17 | 2018-04-26 | 9 | B | Rev-1 | C | Resub..reqd | 2018-04-09 |  | 1 5 | MKM
524 | SD-0081-01 |  | 16th Floor | 16th Floor Private Apartment Master Bedroom Vanity Unit Detail | 1252-MKM-05Q-IDP-01-PA-0309 | 1 OF 1 |  | 2018-02-18 | 2018-03-28 | 38 | C | MKM | 2018-04-15 | 2018-04-18 | 3 | B | MKM | [40 empty] | 2018-04-15 | 2018-04-18 | 3 | B | Rev-1 | C | Resub..reqd | 2018-04-09 |  | 1 5 | MKM
525 | SD-0086-02 |  | 16th Floor | 16th Floor Private Apartment Dressing Area @ Wardrobe Details | 1252-MKM-05Q-IDP-01-PA-0310 | 1 OF 4 |  | 2018-02-18 | 2018-03-19 | 29 | C | MKM | 2018-04-17 | 2018-04-26 | 9 | B | MKM | 2018-06-05 | 2018-06-12 | 7 | B | MKM | [35 empty] | 2018-06-05 | 2018-06-12 | 7 | B | Rev-2 | C | Resub..reqd | 2018-04-09 |  | 1 5 | MKM
526 | SD-0086-02 |  | 16th Floor | 16th Floor Private Apartment Dressing Area @ Wardrobe Details | 1252-MKM-05Q-IDP-01-PA-0310 | 2 OF 4 |  | 2018-02-18 | 2018-03-19 | 29 | C | MKM | 2018-04-17 | 2018-04-26 | 9 | B | MKM | 2018-06-05 | 2018-06-12 | 7 | B | MKM | [35 empty] | 2018-06-05 | 2018-06-12 | 7 | B | Rev-2 |  |  |  |  | 1 5 | MKM
527 | SD-0086-02 |  | 16th Floor | 16th Floor Private Apartment Dressing Area @ Wardrobe Details | 1252-MKM-05Q-IDP-01-PA-0310 | 3 OF 4 |  | 2018-06-05 | 2018-06-12 | 7 | B | MKM | [45 empty] | 2018-06-05 | 2018-06-12 | 7 | B | Rev-0 |  |  |  |  | 1 5 | MKM
528 | SD-0086-02 |  | 16th Floor | 16th Floor Private Apartment Dressing Area @ Wardrobe Details | 1252-MKM-05Q-IDP-01-PA-0310 | 4 OF 4 |  | 2018-06-05 | 2018-06-12 | 7 | B | MKM | [45 empty] | 2018-06-05 | 2018-06-12 | 7 | B | Rev-0 |  |  |  |  | 1 5 | MKM
529 | SD-0086-01 |  | 16th Floor | 16th Floor Private Apartment Laundry Cabinet Detail | 1252-MKM-05Q-IDP-01-PA-0313 | 1 OF 1 |  | 2018-02-18 | 2018-03-19 | 29 | B | MKM | 2018-04-17 | 2018-04-26 | 9 | B | MKM | [40 empty] | 2018-04-17 | 2018-04-26 | 9 | B | Rev-1 | C | Resub..reqd | 2018-04-09 |  | 1 5 | MKM
530 | SD-0083-03 |  | 16th Floor | 16th Floor Private Apartment Kitchen Pantry Unit Details | 1252-MKM-05Q-IDP-01-PA-0314 | 1 OF 2 |  | 2018-02-18 | 2018-03-21 | 31 | C | MKM | 2018-04-11 | 2018-04-18 | 7 | A | MKM | 2018-08-28 | 2018-09-03 | 6 | C | MKM | 2018-09-10 | 2018-09-12 | 2 | B | MKM | [30 empty] | 2018-09-10 | 2018-09-12 | 2 | B | Rev-3 | C | Resub..reqd | 2018-04-09 |  | 1 5 | MKM
531 | SD-0083-03 |  | 16th Floor | 16th Floor Private Apartment Kitchen Pantry Unit Details | 1252-MKM-05Q-IDP-01-PA-0314 | 2 OF 2 |  | 2018-02-18 | 2018-03-21 | 31 | C | MKM | 2018-04-11 | 2018-04-18 | 7 | A | MKM | 2018-08-28 | 2018-09-03 | 6 | B | MKM | 2018-09-10 | 2018-09-12 | 2 | A | MKM | [30 empty] | 2018-09-10 | 2018-09-12 | 2 | A | Rev-3 | B | Approved |  |  | 1 5 | MKM
532 | SD-0086-01 |  | 16th Floor | 16th Floor Private Apartment Gym Flooring Layout | 1252-MKM-05Q-IDP-01-PA-0315 | 1 OF 1 |  | 2018-02-18 | 2018-03-19 | 29 | B | MKM | 2018-04-17 | 2018-04-26 | 9 | B | MKM | [40 empty] | 2018-04-17 | 2018-04-26 | 9 | B | Rev-1 | C | Resub..reqd | 2018-04-09 |  | 1 5 | MKM
533 | SD-0085-01 |  | 16th Floor | 16th Floor Private Apartment Living Room DB Cabinet Details | 1252-MKM-05Q-IDP-01-PA-0316 | 1 OF 1 |  | 2018-02-18 | 2018-03-21 | 31 | C | MKM | 2018-04-16 | 2018-04-26 | 10 | A | MKM | [40 empty] | 2018-04-16 | 2018-04-26 | 10 | A | Rev-1 | C | Resub..reqd | 2018-04-09 |  | 1 5 | MKM
534 | SD-0081-01 |  | 16th Floor | 16th Floor Private Apartment Master Dresser & Bathroom Details | 1252-MKM-05Q-IDP-01-PA-0317 | 1 OF 1 |  | 2018-02-18 | 2018-03-28 | 38 | C | MKM | 2018-04-15 | 2018-04-18 | 3 | B | MKM | [40 empty] | 2018-04-15 | 2018-04-18 | 3 | B | Rev-1 | C | Resub..reqd | 2018-04-09 |  | 1 5 | MKM
535 | SD-0080-01 |  | 16th Floor | 16th Floor Private Apartment Master Bedroom TV Shelf Unit Details | 1252-MKM-05Q-IDP-01-PA-0318 | 1 OF 1 |  | 2018-02-18 | 2018-03-19 | 29 | C | MKM | 2018-04-18 | 2018-04-23 | 5 | B | MKM | [40 empty] | 2018-04-18 | 2018-04-23 | 5 | B | Rev-1 |  |  |  |  | 1 5 | MKM
536 | SD-0113-00 |  | 16th Floor | 16th Floor Private Apartment Dressing Area Wardrobe Details | 1252-MKM-05Q-IDP-01-PA-0319 | 1 OF 2 |  | 2018-08-05 | 2018-08-13 | 8 | B | MKM | [45 empty] | 2018-08-05 | 2018-08-13 | 8 | B | Rev-0 |  |  |  |  | 1 5 | MKM
537 | SD-0113-00 |  | 16th Floor | 16th Floor Private Apartment Dressing Area Wardrobe Details | 1252-MKM-05Q-IDP-01-PA-0319 | 2 OF 2 |  | 2018-08-05 | 2018-08-13 | 8 | B | MKM | [45 empty] | 2018-08-05 | 2018-08-13 | 8 | B | Rev-0 |  |  |  |  | 1 5 | MKM
538 | SD-0155-00 | ARK-0053-00 | 16th Floor | 16th Floor Private Apartment Master Bedroom TV Wall Unit Details | 1252-MKM-05Q-IDP-01-PA-0320 | 1 OF 1 |  | 2019-04-11 | 2019-04-22 | 11 | A | MKM | [45 empty] | 2019-04-11 | 2019-04-22 | 11 | A | Rev-0 |  |  |  |  | 1 5 | MKM
500_DOORS | [62 empty] | P |  |  |  | 1 211
539 | SD-0079-00 |  | 16th Floor | 16th Floor Private Apartment Door Schedule & Layout | 1252-MKM-05Q-IDP-01-PA-0500 | 1 OF 1 |  | 2018-02-18 | 2018-04-16 | 57 | B | MKM | [45 empty] | 2018-02-18 | 2018-04-16 | 57 | B | Rev-0 | P |  |  |  | 1 5 | MKM
540 | SD-0079-04 |  | 16th Floor | 16th Floor Private Apartment Main Entrance Door – (WD1) 60min. Fire Rated Details | 1252-MKM-05Q-IDP-01-PA-0501 | 1 OF 1 |  | 2018-02-18 | 2018-04-16 | 57 | C | MKM | 2018-04-25 | 2018-05-05 | 10 | C | MKM | 2018-05-10 | 2018-05-15 | 5 | B | MKM | 2018-08-07 | 2018-08-14 | 7 | B | MKM | [30 empty] | 2018-08-07 | 2018-08-14 | 7 | B | Rev-3 | P |  |  |  | 1 5 | MKM
541 | SD-0079-00 |  | 16th Floor | 16th Floor Private Apartment Handle Details @ Main Entrance Door | 1252-MKM-05Q-IDP-01-PA-0501 | 2 OF 2 |  | 2018-02-18 | 2018-04-16 | 57 | X | MKM | [45 empty] | 2018-02-18 | 2018-04-16 | 57 | X | Rev-0 | P |  |  |  | 1 5 | MKM
542 | SD-0079-02 |  | 16th Floor | 16th Floor Private Apartment Kitchen Door (WD-03) 60min. Fire Rated | 1252-MKM-05Q-IDP-01-PA-0502 | 1 OF 1 |  | 2018-02-18 | 2018-04-16 | 57 | B | MKM | 2018-05-06 | 2018-05-09 | 3 | A | MKM | [40 empty] | 2018-05-06 | 2018-05-09 | 3 | A | Rev-1 | P |  |  |  | 1 5 | MKM
543 | SD-0079-03 |  | 16th Floor | 16th Floor Private Apartment Dining Room Sliding Door – (SD1) Details | 1252-MKM-05Q-IDP-01-PA-0503 | 1 OF 1 |  | 2018-02-18 | 2018-04-16 | 57 | C | MKM | 2018-04-25 | 2018-05-05 | 10 | C | MKM | 2018-05-10 | 2018-05-15 | 5 | A | MKM | [35 empty] | 2018-05-10 | 2018-05-15 | 5 | A | Rev-2 | P |  |  |  | 1 5 | MKM
544 | SD-0079-02 |  | 16th Floor | 16th Floor Private Apartment Passage Door – (WD3a) Details | 1252-MKM-05Q-IDP-01-PA-0504 | 1 OF 2 |  | 2018-02-18 | 2018-04-16 | 57 | B | MKM | 2018-05-06 | 2018-05-09 | 3 | A | MKM | [40 empty] | 2018-05-06 | 2018-05-09 | 3 | A | Rev-1 | P |  |  |  | 1 5 | MKM
545 | SD-0079-02 |  | 16th Floor | 16th Floor Private Apartment Master Bedroom (WD-3d) Details | 1252-MKM-05Q-IDP-01-PA-0504 | 2 OF 2 |  | 2018-05-06 | 2018-05-09 | 3 | A | MKM | [45 empty] | 2018-05-06 | 2018-05-09 | 3 | A | Rev-0 | P |  |  |  | 1 5 | MKM
546 | SD-0079-02 |  | 16th Floor | 16th Floor Private Apartment Guest Toilet Door – (WD2) Details | 1252-MKM-05Q-IDP-01-PA-0505 | 1 OF 1 |  | 2018-02-18 | 2018-04-16 | 57 | B | MKM | 2018-05-06 | 2018-05-09 | 3 | A | MKM | [40 empty] | 2018-05-06 | 2018-05-09 | 3 | A | Rev-1 | P |  |  |  | 1 5 | MKM
547 | SD-0079-01 |  | 16th Floor | 16th Floor Private Apartment Storage Room Door – (WD3c) Details | 1252-MKM-05Q-IDP-01-PA-0506 | 1 OF 1 |  | 2018-02-18 | 2018-04-16 | 57 | C | MKM | 2018-04-25 | 2018-05-05 | 10 | B | MKM | [40 empty] | 2018-04-25 | 2018-05-05 | 10 | B | Rev-1 | P |  |  |  | 1 5 | MKM
548 | SD-0079-01 |  | 16th Floor | 16th Floor Private Apartment Twin Bedroom Door – (WD3b) Details | 1252-MKM-05Q-IDP-01-PA-0507 | 1 OF 1 |  | 2018-02-18 | 2018-04-16 | 57 | C | MKM | 2018-04-25 | 2018-05-05 | 10 | B | MKM | [40 empty] | 2018-04-25 | 2018-05-05 | 10 | B | Rev-1 | P |  |  |  | 1 5 | MKM
549 | SD-0079-01 |  | 16th Floor | 16th Floor Private Apartment Twin Bedroom Dressing Area Door Details (WD-2a) | 1252-MKM-05Q-IDP-01-PA-0508 | 1 OF 1 |  | 2018-02-18 | 2018-04-16 | 57 | C | MKM | 2018-04-25 | 2018-05-05 | 10 | B | MKM | [40 empty] | 2018-04-25 | 2018-05-05 | 10 | B | Rev-1 | P |  |  |  | 1 5 | MKM
550 | SD-0079-02 |  | 16th Floor | 16th Floor Private Apartment Twin Bathroom Door Details (WD-2b) | 1252-MKM-05Q-IDP-01-PA-0509 | 1 OF 1 |  | 2018-02-18 | 2018-04-16 | 57 | B | MKM | 2018-05-06 | 2018-05-09 | 3 | A | MKM | [40 empty] | 2018-05-06 | 2018-05-09 | 3 | A | Rev-1 | P
551 | SD-0079-03 |  | 16th Floor | 16th Floor Private Apartment Gym Door Details (WD3e) | 1252-MKM-05Q-IDP-01-PA-0510 | 1 OF 1 |  | 2018-02-18 | 2018-04-16 | 57 | C | MKM | 2018-04-25 | 2018-05-05 | 10 | C | MKM | 2018-05-10 | 2018-05-15 | 5 | A | MKM | [35 empty] | 2018-05-10 | 2018-05-15 | 5 | A | Rev-2 | P
552 | SD-0079-03 |  | 16th Floor | 16th Floor Private Apartment Master Bedroom – (WD3f) Details | 1252-MKM-05Q-IDP-01-PA-0511 | 1 OF 1 |  | 2018-02-18 | 2018-04-16 | 57 | C | MKM | 2018-04-25 | 2018-05-05 | 10 | C | MKM | 2018-05-10 | 2018-05-15 | 5 | A | MKM | [35 empty] | 2018-05-10 | 2018-05-15 | 5 | A | Rev-2 | P
553 | SD-0079-01 |  | 16th Floor | 16th Floor Private Apartment Master Bathroom Door – (WD 2C) Details | 1252-MKM-05Q-IDP-01-PA-0512 | 1 OF 1 |  | 2018-02-18 | 2018-04-16 | 57 | C | MKM | 2018-04-25 | 2018-05-05 | 10 | A | MKM | [40 empty] | 2018-04-25 | 2018-05-05 | 10 | A | Rev-1 | P |  |  |  | 1 5 | MKM
554 | SD-0079-02 |  | 16th Floor | 16th Floor Private Apartment Living Room Shaft Door Details | 1252-MKM-05Q-IDP-01-PA-0513 | 1 OF 1 |  | 2018-02-18 | 2018-04-16 | 57 | B | MKM | 2018-05-06 | 2018-05-09 | 3 | B | MKM | [40 empty] | 2018-05-06 | 2018-05-09 | 3 | B | Rev-1 |  |  |  |  | 1 5 | MKM
555 | SD-0099-01 |  | 16th Floor | 16th Floor Private Apartment Kitchen Shaft Door Details | 1252-MKM-05Q-IDP-01-PA-0514 | 1 OF 1 |  | 2018-04-24 | 2018-05-01 | 7 | B | MKM | 2018-05-17 | 2018-05-21 | 4 | B | MKM | [40 empty] | 2018-05-17 | 2018-05-21 | 4 | B | Rev-1 |  |  |  |  | 1 5 | MKM
556 | SD-0109-00 |  |  | 16th Floor Private Apartment Kitchen Pantry Plan & Elevations | 1252-MKM-05Q-IDP-01-PA-0515 | 1 OF 1 |  | 2018-07-11 | 2018-07-16 | 5 | B | MKM | [45 empty] | 2018-07-11 | 2018-07-16 | 5 | B | Rev-0 |  |  |  |  | 1 5 | MKM
557 | SD-0109-01 |  |  | 16th Floor Private Laundry/Storage Plan & Elevations | 1252-MKM-05Q-IDP-01-PA-0516 | 1 OF 1 |  | 2018-07-11 | 2018-07-16 | 5 | C | MKM | 2018-07-23 | 2018-07-25 | 2 | A | MKM | [40 empty] | 2018-07-23 | 2018-07-25 | 2 | A | Rev-1 |  |  |  |  | 1 5 | MKM
558 | SD-0112-00 |  |  | 16th Floor Private Laundry Shaft Door Details | 1252-MKM-05Q-IDP-01-PA-0517 | 1 OF 1 |  | 2018-07-23 | 2018-07-25 | 2 | A | MKM | [45 empty] | 2018-07-23 | 2018-07-25 | 2 | A | Rev-0 |  |  |  |  | 1 5 | MKM
Executive Suite | [66 empty] | 1 203
KEY PLAN (45 TO 50 FLOORS) | [62 empty] | B | Approved |  |  | 1 211
559 | SD-0116-00 | ARK-0001-00 |  | Executive Suite Key Plan - 45th Floor | 1252-MKM-05Q-IDP-01-WES-0100 | 1 OF 1 |  | 2018-09-23 | 2018-10-07 | 14 | B | MKM | [45 empty] | 2018-09-23 | 2018-10-07 | 14 | B | Rev-0 | B | Approved |  |  | 1 5 | MKM
560 | SD-0116-00 | ARK-0001-00 |  | Executive Suite Key Plan - 46th Floor | 1252-MKM-05Q-IDP-01-WES-0101 | 1 OF 1 |  | 2018-09-23 | 2018-10-07 | 14 | B | MKM | [45 empty] | 2018-09-23 | 2018-10-07 | 14 | B | Rev-0 | B | Approved |  |  | 1 5 | MKM
561 | SD-0116-00 | ARK-0001-00 |  | Executive Suite Key Plan - 47th Floor | 1252-MKM-05Q-IDP-01-WES-0102 | 1 OF 1 |  | 2018-09-23 | 2018-10-07 | 14 | B | MKM | [45 empty] | 2018-09-23 | 2018-10-07 | 14 | B | Rev-0 | B | Approved |  |  | 1 5 | MKM
562 | SD-0116-00 | ARK-0001-00 |  | Executive Suite Key Plan - 48th Floor | 1252-MKM-05Q-IDP-01-WES-0103 | 1 OF 1 |  | 2018-09-23 | 2018-10-07 | 14 | B | MKM | [45 empty] | 2018-09-23 | 2018-10-07 | 14 | B | Rev-0 | B | Approved |  |  | 1 5 | MKM
563 | SD-0116-00 | ARK-0001-00 |  | Executive Suite Key Plan - 49th Floor | 1252-MKM-05Q-IDP-01-WES-0104 | 1 OF 1 |  | 2018-09-23 | 2018-10-07 | 14 | B | MKM | [45 empty] | 2018-09-23 | 2018-10-07 | 14 | B | Rev-0 | B | Approved |  |  | 1 5 | MKM
564 | SD-0116-00 | ARK-0001-00 |  | Executive Suite Key Plan - 50th Floor | 1252-MKM-05Q-IDP-01-WES-0105 | 1 OF 1 |  | 2018-09-23 | 2018-10-07 | 14 | B | MKM | [45 empty] | 2018-09-23 | 2018-10-07 | 14 | B | Rev-0 | B | Approved |  |  | 1 5 | MKM
Executive Suite - Type 1 | [62 empty] | B | Approved |  |  | 1 211
565 | SD-0129-00 | ARK-0016-00 |  | Furniture Plan | 1252-MKM-05Q-IDP-01-WES1-0100 | 1 OF 1 |  | 2018-09-26 | 2018-10-07 | 11 | B | MKM | [45 empty] | 2018-09-26 | 2018-10-07 | 11 | B | Rev-0 | B | Approved |  |  | 1 5 | MKM
566 | SD-0133-00 | ARK-0022-00 |  | Power Plan | 1252-MKM-05Q-IDP-01-WES1-0120 | 1 OF 1 |  | 2018-10-11 | 2018-10-22 | 11 | B | MKM | [45 empty] | 2018-10-11 | 2018-10-22 | 11 | B | Rev-0 | B | Approved |  |  | 1 5 | MKM
567 | SD-0133-00 | ARK-0022-00 |  | Ceiling Plan | 1252-MKM-05Q-IDP-01-WES1-0200 | 1 OF 1 |  | 2018-10-11 | 2018-10-22 | 11 | B | MKM | [45 empty] | 2018-10-11 | 2018-10-22 | 11 | B | Rev-0 | B | Approved |  |  | 1 5 | MKM
568 | SD-0129-00 | ARK-0016-00 |  | Elevations-AA,BB,CC, DD & EE | 1252-MKM-05Q-IDP-01-WES1-0300 | 1 OF 1 |  | 2018-09-26 | 2018-10-07 | 11 | B | MKM | [45 empty] | 2018-09-26 | 2018-10-07 | 11 | B | Rev-0 | B | Approved |  |  | 1 5 | MKM
569 | SD-0129-00 | ARK-0016-00 |  | Elevations-FF,GG,HH,JJ & KK | 1252-MKM-05Q-IDP-01-WES1-0301 | 1 OF 1 |  | 2018-09-26 | 2018-10-07 | 11 | B | MKM | [45 empty] | 2018-09-26 | 2018-10-07 | 11 | B | Rev-0 | B | Approved |  |  | 1 5 | MKM
Executive Suite - Type 2 | [62 empty] | B | Approved |  |  | 1 211
570 | SD-0117-00 | ARK-0002-00 |  | 45th to 46th Floor Executive Suite - Type 2 Furniture Plan | 1252-MKM-05Q-IDP-01-WES2-0100 | 1 OF 1 |  | 2018-09-23 | 2018-10-07 | 14 | B | MKM | [45 empty] | 2018-09-23 | 2018-10-07 | 14 | B | Rev-0 | B | Approved |  |  | 1 5 | MKM
571 | SD-0128-00 | ARK-0015-00 |  | 45th to 46th Floor Executive Suite - Type 2 Power Plan | 1252-MKM-05Q-IDP-01-WES2-0120 | 1 OF 1 |  | 2018-09-26 | 2018-10-07 | 11 | B | MKM | [45 empty] | 2018-09-26 | 2018-10-07 | 11 | B | Rev-0 | B | Approved |  |  | 1 5 | MKM
572 | SD-0132-00 | ARK-0021-00 |  | 45th to 46th Floor Executive Suite - Type 2 Ceiling Plan | 1252-MKM-05Q-IDP-01-WES2-0200 | 1 OF 1 |  | 2018-10-11 | 2018-10-22 | 14 | B | MKM | [45 empty] | 2018-10-11 | 2018-10-22 | 14 | B | Rev-0 | B | Approved |  |  | 1 5 | MKM
573 | SD-0117-00 | ARK-0002-00 |  | 45th to 46th Floor Executive Suite - Type 2 Elevations-A & B | 1252-MKM-05Q-IDP-01-WES2-0300 | 1 OF 1 |  | 2018-09-23 | 2018-10-07 | 14 | B | MKM | [45 empty] | 2018-09-23 | 2018-10-07 | 14 | B | Rev-0 | B | Approved |  |  | 1 5 | MKM
574 | SD-0117-00 | ARK-0002-00 |  | 45th to 46th Floor Executive Suite - Type 2 Elevations-C & D | 1252-MKM-05Q-IDP-01-WES2-0301 | 1 OF 1 |  | 2018-09-23 | 2018-10-07 | 14 | B | MKM | [45 empty] | 2018-09-23 | 2018-10-07 | 14 | B | Rev-0 | B | Approved |  |  | 1 5 | MKM
Executive Suite - Type 3 | [62 empty] | B | Approved |  |  | 1 211
575 | SD-0119-00 | ARK-0004-00 |  | 45th to 46th Floor Executive Suite - Type 3 Furniture Plan | 1252-MKM-05Q-IDP-01-WES3-0100 | 1 OF 1 |  | 2018-09-23 | 2018-10-07 | 14 | B | MKM | [45 empty] | 2018-09-23 | 2018-10-07 | 14 | B | Rev-0 | B | Approved |  |  | 1 5 | MKM
576 | SD-0131-00 | ARK-0018-00 |  | Power Plan | 1252-MKM-05Q-IDP-01-WES3-0120 | 1 OF 1 |  | 2018-09-26 | 2018-10-15 | 19 | B | MKM | [45 empty] | 2018-09-26 | 2018-10-15 | 19 | B | Rev-0 | B | Approved |  |  | 1 5 | MKM
577 | SD-0136-00 | ARK-0025-00 |  | Ceiling Plan | 1252-MKM-05Q-IDP-01-WES3-0200 | 1 OF 1 |  | 2018-10-11 | 2018-10-22 | 11 | B | MKM | [45 empty] | 2018-10-11 | 2018-10-22 | 11 | B | Rev-0 | B | Approved |  |  | 1 5 | MKM
578 | SD-0119-00 | ARK-0004-00 |  | 45th to 46th Floor Executive Suite - Type 3 Elevations-A, B, C & D | 1252-MKM-05Q-IDP-01-WES3-0300 | 1 OF 1 |  | 2018-09-23 | 2018-10-07 | 14 | B | MKM | [45 empty] | 2018-09-23 | 2018-10-07 | 14 | B | Rev-0 | B | Approved |  |  | 1 5 | MKM
579 | SD-0119-00 | ARK-0004-00 |  | 45th to 46th Floor Executive Suite - Type 3 Elevations-E, F, G, H, J & K | 1252-MKM-05Q-IDP-01-WES3-0301 | 1 OF 1 |  | 2018-09-23 | 2018-10-07 | 14 | B | MKM | [45 empty] | 2018-09-23 | 2018-10-07 | 14 | B | Rev-0 | B | Approved |  |  | 1 5 | MKM
Executive Suite - Type 3A | [62 empty] | B | Approved |  |  | 1 211
580 | SD-0130-00 | ARK-0017-00 |  | Furniture Plan | 1252-MKM-05Q-IDP-01-WES3A-0100 | 1 OF 1 |  | 2018-09-26 | 2018-10-15 | 19 | B | MKM | [45 empty] | 2018-09-26 | 2018-10-15 | 19 | B | Rev-0 | B | Approved |  |  | 1 5 | MKM
581 | SD-0137-00 | ARK-0026-00 |  | Power Plan | 1252-MKM-05Q-IDP-01-WES3A-0120 | 1 OF 1 |  | 2018-10-11 | 2018-10-22 | 11 | B | MKM | [45 empty] | 2018-10-11 | 2018-10-22 | 11 | B | Rev-0 | B | Approved |  |  | 1 5 | MKM
582 | SD-0137-00 | ARK-0026-00 |  | Ceiling Plan | 1252-MKM-05Q-IDP-01-WES3A-0200 | 1 OF 1 |  | 2018-10-11 | 2018-10-22 | 11 | B | MKM | [45 empty] | 2018-10-11 | 2018-10-22 | 11 | B | Rev-0 | B | Approved |  |  | 1 5 | MKM
583 | SD-0130-00 | ARK-0017-00 |  | Elevations-A,B,C & D | 1252-MKM-05Q-IDP-01-WES3A-0300 | 1 OF 1 |  | 2018-09-26 | 2018-10-15 | 19 | B | MKM | [45 empty] | 2018-09-26 | 2018-10-15 | 19 | B | Rev-0 | B | Approved |  |  | 1 5 | MKM
584 | SD-0130-00 | ARK-0017-00 |  | Elevations-E,F,G,H,J & K | 1252-MKM-05Q-IDP-01-WES3A-0301 | 1 OF 1 |  | 2018-09-26 | 2018-10-15 | 19 | B | MKM | [45 empty] | 2018-09-26 | 2018-10-15 | 19 | B | Rev-0 | B | Approved |  |  | 1 5 | MKM
Executive Suite - Type 4 | [62 empty] | B | Approved |  |  | 1 211
585 | SD-0127-00 | ARK-0014-00 |  | 47th Floor Executive Suite - Type 4 & 4A Furniture Plan | 1252-MKM-05Q-IDP-01-WES4-0100 | 1 OF 1 |  | 2018-09-26 | 2018-10-07 | 11 | B | MKM | [45 empty] | 2018-09-26 | 2018-10-07 | 11 | B | Rev-0 | B | Approved |  |  | 1 5 | MKM
586 | SD-0134-00 | ARK-0023-00 |  | Power Plan | 1252-MKM-05Q-IDP-01-WES4-0120 | 1 OF 1 |  | 2018-10-11 | 2018-10-22 | 11 | B | MKM | [45 empty] | 2018-10-11 | 2018-10-22 | 11 | B | Rev-0 | B | Approved |  |  | 1 5 | MKM
587 | SD-0134-00 | ARK-0023-00 |  | Ceiling Plan | 1252-MKM-05Q-IDP-01-WES4-0200 | 1 OF 1 |  | 2018-10-11 | 2018-10-22 | 11 | B | MKM | [45 empty] | 2018-10-11 | 2018-10-22 | 11 | B | Rev-0 | B | Approved |  |  | 1 5 | MKM
588 | SD-0127-00 | ARK-0014-00 |  | 47th Floor Executive Suite - Type 4 & 4A Elevations A & B | 1252-MKM-05Q-IDP-01-WES4-0300 | 1 OF 1 |  | 2018-09-26 | 2018-10-07 | 11 | B | MKM | [45 empty] | 2018-09-26 | 2018-10-07 | 11 | B | Rev-0 | B | Approved |  |  | 1 5 | MKM
589 | SD-0127-00 | ARK-0014-00 |  | 47th Floor Executive Suite - Type 4 & 4A Elevations C & D | 1252-MKM-05Q-IDP-01-WES4-0301 | 1 OF 1 |  | 2018-09-26 | 2018-10-07 | 11 | B | MKM | [45 empty] | 2018-09-26 | 2018-10-07 | 11 | B | Rev-0 | B | Approved |  |  | 1 5 | MKM
590 | SD-0127-00 | ARK-0014-00 |  | 47th Floor Executive Suite - Type 4 & 4A Elevations E, F & G | 1252-MKM-05Q-IDP-01-WES4-0302 | 1 OF 1 |  | 2018-09-26 | 2018-10-07 | 11 | B | MKM | [45 empty] | 2018-09-26 | 2018-10-07 | 11 | B | Rev-0 | B | Approved |  |  | 1 5 | MKM
Executive Suite - Type 5 | [62 empty] | B | Approved |  |  | 1 211
591 | SD-0140-00 | ARK-0029-00 |  | Furniture Plan | 1252-MKM-05Q-IDP-01-WES5-0100 | 1 OF 1 |  | 2018-10-14 | 2018-10-22 | 8 | B | MKM | [45 empty] | 2018-10-14 | 2018-10-22 | 8 | B | Rev-0 | B | Approved |  |  | 1 5 | MKM
592 | SD-0140-00 | ARK-0029-00 |  | Power Plan | 1252-MKM-05Q-IDP-01-WES5-0120 | 1 OF 1 |  | 2018-10-14 | 2018-10-22 | 8 | B | MKM | [45 empty] | 2018-10-14 | 2018-10-22 | 8 | B | Rev-0 | B | Approved |  |  | 1 5 | MKM
593 | SD-0140-00 | ARK-0029-00 |  | Ceiling Plan | 1252-MKM-05Q-IDP-01-WES5-0200 | 1 OF 1 |  | 2018-10-14 | 2018-10-22 | 8 | B | MKM | [45 empty] | 2018-10-14 | 2018-10-22 | 8 | B | Rev-0 | B | Approved |  |  | 1 5 | MKM
594 | SD-0140-00 | ARK-0029-00 |  | Elevations-A & B | 1252-MKM-05Q-IDP-01-WES5-0300 | 1 OF 1 |  | 2018-10-14 | 2018-10-22 | 8 | B | MKM | [45 empty] | 2018-10-14 | 2018-10-22 | 8 | B | Rev-0 | B | Approved |  |  | 1 5 | MKM
595 | SD-0140-00 | ARK-0029-00 |  | Elevations-C & D | 1252-MKM-05Q-IDP-01-WES5-0301 | 1 OF 1 |  | 2018-10-14 | 2018-10-22 | 8 | B | MKM | [45 empty] | 2018-10-14 | 2018-10-22 | 8 | B | Rev-0 | B | Approved |  |  | 1 5 | MKM
Executive Suite - Type 6 | [62 empty] | B | Approved |  |  | 1 211
596 | SD-0138-00 | ARK-0027-00 |  | Furniture Plan | 1252-MKM-05Q-IDP-01-WES6-0100 | 1 OF 1 |  | 2018-10-14 | 2018-10-22 | 8 | B | MKM | [45 empty] | 2018-10-14 | 2018-10-22 | 8 | B | Rev-0 | B | Approved |  |  | 1 5 | MKM
597 | SD-0138-00 | ARK-0027-00 |  | Power Plan | 1252-MKM-05Q-IDP-01-WES6-0120 | 1 OF 1 |  | 2018-10-14 | 2018-10-22 | 8 | B | MKM | [45 empty] | 2018-10-14 | 2018-10-22 | 8 | B | Rev-0 | B | Approved |  |  | 1 5 | MKM
598 | SD-0138-00 | ARK-0027-00 |  | Ceiling Plan | 1252-MKM-05Q-IDP-01-WES6-0200 | 1 OF 1 |  | 2018-10-14 | 2018-10-22 | 8 | B | MKM | [45 empty] | 2018-10-14 | 2018-10-22 | 8 | B | Rev-0 | B | Approved |  |  | 1 5 | MKM
599 | SD-0138-00 | ARK-0027-00 |  | Elevations-A & B | 1252-MKM-05Q-IDP-01-WES6-0300 | 1 OF 1 |  | 2018-10-14 | 2018-10-22 | 8 | B | MKM | [45 empty] | 2018-10-14 | 2018-10-22 | 8 | B | Rev-0 | B | Approved |  |  | 1 5 | MKM
600 | SD-0138-00 | ARK-0027-00 |  | Elevations-C & D | 1252-MKM-05Q-IDP-01-WES6-0301 | 1 OF 1 |  | 2018-10-14 | 2018-10-22 | 8 | B | MKM | [45 empty] | 2018-10-14 | 2018-10-22 | 8 | B | Rev-0 | B | Approved |  |  | 1 5 | MKM
601 | SD-0138-00 | ARK-0027-00 |  | Elevations-E, F, & G | 1252-MKM-05Q-IDP-01-WES6-0302 | 1 OF 1 |  | 2018-10-14 | 2018-10-22 | 8 | B | MKM | [45 empty] | 2018-10-14 | 2018-10-22 | 8 | B | Rev-0 | B | Approved |  |  | 1 5 | MKM
Executive Suite - Type 7 | [62 empty] | B | Approved |  |  | 1 211
602 | SD-0139-00 | ARK-0028-00 |  | Furniture Plan | 1252-MKM-05Q-IDP-01-WES7-0100 | 1 OF 1 |  | 2018-10-14 | 2018-10-22 | 8 | B | MKM | [45 empty] | 2018-10-14 | 2018-10-22 | 8 | B | Rev-0 | B | Approved |  |  | 1 5 | MKM
603 | SD-0139-00 | ARK-0028-00 |  | Power Plan | 1252-MKM-05Q-IDP-01-WES7-0120 | 1 OF 1 |  | 2018-10-14 | 2018-10-22 | 8 | B | MKM | [45 empty] | 2018-10-14 | 2018-10-22 | 8 | B | Rev-0 | B | Approved |  |  | 1 5 | MKM
604 | SD-0139-00 | ARK-0028-00 |  | Ceiling Plan | 1252-MKM-05Q-IDP-01-WES7-0200 | 1 OF 1 |  | 2018-10-14 | 2018-10-22 | 8 | B | MKM | [45 empty] | 2018-10-14 | 2018-10-22 | 8 | B | Rev-0 | B | Approved |  |  | 1 5 | MKM
605 | SD-0139-00 | ARK-0028-00 |  | Elevations-A, B, C & D | 1252-MKM-05Q-IDP-01-WES7-0300 | 1 OF 1 |  | 2018-10-14 | 2018-10-22 | 8 | B | MKM | [45 empty] | 2018-10-14 | 2018-10-22 | 8 | B | Rev-0 | B | Approved |  |  | 1 5 | MKM
606 | SD-0139-00 | ARK-0028-00 |  | Elevations- E, F,G & H | 1252-MKM-05Q-IDP-01-WES7-0301 | 1 OF 1 |  | 2018-10-14 | 2018-10-22 | 8 | B | MKM | [45 empty] | 2018-10-14 | 2018-10-22 | 8 | B | Rev-0 | B | Approved |  |  | 1 5 | MKM
Executive Suite - Wardrobe Details | [62 empty] | B | Approved |  |  | 1 211
607 | SD-0141-00 | ARK-0030-00 |  | Wardrobe Details -Type 1 - Executive Suite Type 1 | 1252-MKM-05Q-IDP-01-WESW-0400 | 1 OF 1 |  | 2018-10-14 | 2018-10-25 | 11 | C | MKM | [45 empty] | 2018-10-14 | 2018-10-25 | 11 | C | Rev-0 | B | Approved |  |  | 1 5 | MKM
608 | SD-0141-00 | ARK-0030-00 |  | Wardrobe Details -Type 2 - Executive Suite Type 1 | 1252-MKM-05Q-IDP-01-WESW-0401 | 1 OF 1 |  | 2018-10-14 | 2018-10-25 | 11 | C | MKM | [45 empty] | 2018-10-14 | 2018-10-25 | 11 | C | Rev-0 | B | Approved |  |  | 1 5 | MKM
609 | SD-0141-00 | ARK-0030-00 |  | Wardrobe Details -Type 3 - Executive Suite Type 2 | 1252-MKM-05Q-IDP-01-WESW-0402 | 1 OF 1 |  | 2018-10-14 | 2018-10-25 | 11 | C | MKM | [45 empty] | 2018-10-14 | 2018-10-25 | 11 | C | Rev-0 | B | Approved |  |  | 1 5 | MKM
610 | SD-0141-00 | ARK-0030-00 |  | Wardrobe Details -Type 4 - Executive Suite Type 3 & 3A | 1252-MKM-05Q-IDP-01-WESW-0403 | 1 OF 1 |  | 2018-10-14 | 2018-10-25 | 11 | C | MKM | [45 empty] | 2018-10-14 | 2018-10-25 | 11 | C | Rev-0 | B | Approved |  |  | 1 5 | MKM
611 | SD-0141-00 | ARK-0030-00 |  | Wardrobe Details -Type 5 - Executive Suite Type 3 & 3A | 1252-MKM-05Q-IDP-01-WESW-0404 | 1 OF 1 |  | 2018-10-14 | 2018-10-25 | 11 | C | MKM | [45 empty] | 2018-10-14 | 2018-10-25 | 11 | C | Rev-0 | B | Approved |  |  | 1 5 | MKM
612 | SD-0141-00 | ARK-0030-00 |  | Wardrobe Details -Type 6 - Executive Suite Type 4 & 6 | 1252-MKM-05Q-IDP-01-WESW-0405 | 1 OF 1 |  | 2018-10-14 | 2018-10-25 | 11 | C | MKM | [45 empty] | 2018-10-14 | 2018-10-25 | 11 | C | Rev-0 | B | Approved |  |  | 1 5 | MKM
613 | SD-0150-00 | ARK-0045-00 | 48-49 | 48th to 49th Floor Executive Suite Type-5 Wardrobe Details Type-7 | 1252-MKM-05Q-IDP-01-WESW-0406 | 1 OF 2 |  | 2018-12-04 | 2018-12-10 | 6 | C | MKM | [45 empty] | 2018-12-04 | 2018-12-10 | 6 | C | Rev-0 | B | Approved |  |  | 1 5 | MKM
614 | SD-0150-00 | ARK-0045-00 | 48-49 | 48th to 49th Floor Executive Suite Type-5 Wardrobe Details Type-7 | 1252-MKM-05Q-IDP-01-WESW-0406 | 2 OF 2 |  | 2018-12-04 | 2018-12-10 | 6 | C | MKM | [45 empty] | 2018-12-04 | 2018-12-10 | 6 | C | Rev-0 | B | Approved |  |  | 1 5 | MKM
615 | SD-0141-00 | ARK-0030-00 |  | Wardrobe Details -Type 8 - Executive Suite Type 7 | 1252-MKM-05Q-IDP-01-WESW-0407 | 1 OF 1 |  | 2018-10-14 | 2018-10-25 | 11 | C | MKM | [45 empty] | 2018-10-14 | 2018-10-25 | 11 | C | Rev-0 | B | Approved |  |  | 1 5 | MKM
616 | SD-0141-00 | ARK-0030-00 |  | Wardrobe Typical Details - Executive Suite | 1252-MKM-05Q-IDP-01-WESW-0408 | 1 OF 3 |  | 2018-10-14 | 2018-10-25 | 11 | C | MKM | [45 empty] | 2018-10-14 | 2018-10-25 | 11 | C | Rev-0 | B | Approved |  |  | 1 5 | MKM
617 | SD-0141-00 | ARK-0030-00 |  | Wardrobe Typical Details - Executive Suite | 1252-MKM-05Q-IDP-01-WESW-0408 | 2 OF 3 |  | 2018-10-14 | 2018-10-25 | 11 | C | MKM | [45 empty] | 2018-10-14 | 2018-10-25 | 11 | C | Rev-0 | B | Approved |  |  | 1 5 | MKM
618 | SD-0141-00 | ARK-0030-00 |  | Wardrobe Typical Details - Executive Suite | 1252-MKM-05Q-IDP-01-WESW-0408 | 3 OF 3 |  | 2018-10-14 | 2018-10-25 | 11 | C | MKM | [45 empty] | 2018-10-14 | 2018-10-25 | 11 | C | Rev-0 | B | Approved |  |  | 1 5 | MKM
Executive Suite - Joinery | [62 empty] | B | Approved |  |  | 1 211
619 | SD-0120-00 | ARK-0005-00 |  | Headboard (WES-314A) Details @ Master Bed | 1252-MKM-05Q-IDP-01-WESD-0400 | 1 OF 4 |  | 2018-09-23 | 2018-10-07 | 14 | B | MKM | [45 empty] | 2018-09-23 | 2018-10-07 | 14 | B | Rev-0 | B | Approved |  |  | 1 5 | MKM
620 | SD-0120-00 | ARK-0005-00 |  | Headboard (WES-314B) Details @ Master Bed | 1252-MKM-05Q-IDP-01-WESD-0400 | 2 OF 4 |  | 2018-09-23 | 2018-10-07 | 14 | B | MKM | [45 empty] | 2018-09-23 | 2018-10-07 | 14 | B | Rev-0 | B | Approved |  |  | 1 5 | MKM
621 | SD-0120-00 | ARK-0005-00 |  | Headboard (WES-314C) Details @ Master Bed | 1252-MKM-05Q-IDP-01-WESD-0400 | 3 OF 4 |  | 2018-09-23 | 2018-10-07 | 14 | B | MKM | [45 empty] | 2018-09-23 | 2018-10-07 | 14 | B | Rev-0 | B | Approved |  |  | 1 5 | MKM
622 | SD-0120-00 | ARK-0005-00 |  | Headboard Typical Details @ Master Bedroom | 1252-MKM-05Q-IDP-01-WESD-0400 | 4 OF 4 |  | 2018-09-23 | 2018-10-07 | 14 | B | MKM | [45 empty] | 2018-09-23 | 2018-10-07 | 14 | B | Rev-0 | B | Approved |  |  | 1 5 | MKM
623 | SD-0121-00 | ARK-0006-00 |  | Headboard Details @ Twin Bed | 1252-MKM-05Q-IDP-01-WESD-0401 | 1 OF 2 |  | 2018-09-23 | 2018-10-07 | 14 | B | MKM | [45 empty] | 2018-09-23 | 2018-10-07 | 14 | B | Rev-0 | B | Approved |  |  | 1 5 | MKM
624 | SD-0121-00 | ARK-0006-00 |  | Headboard Details @ Twin Bed | 1252-MKM-05Q-IDP-01-WESD-0401 | 2 OF 2 |  | 2018-09-23 | 2018-10-07 | 14 | B | MKM | [45 empty] | 2018-09-23 | 2018-10-07 | 14 | B | Rev-0 | B | Approved |  |  | 1 5 | MKM
625 | SD-0143-00 | ARK-0032-00 |  | 45th to 50th Floor Executive Suite Bedside Table Details @ Master Bedroom | 1252-MKM-05Q-IDP-01-WESD-0402 | 1 OF 1 |  | 2018-10-17 | 2018-10-31 | 14 | C | MKM | [45 empty] | 2018-10-17 | 2018-10-31 | 14 | C | Rev-0 | B | Approved |  |  | 1 5 | MKM
626 | SD-0143-00 | ARK-0032-00 |  | 45th to 50th Floor Executive Suite Bedside Table Details @ Twin Bedroom | 1252-MKM-05Q-IDP-01-WESD-0402A | 1 OF 1 |  | 2018-10-17 | 2018-10-31 | 14 | C | MKM | [45 empty] | 2018-10-17 | 2018-10-31 | 14 | C | Rev-0 | B | Approved |  |  | 1 5 | MKM
627 | SD-0124-00 | ARK-0011-00 |  | T.V Unit/ Feature wall Details -Type1 (Ex.Suite Type-1,4,5 & 6) | 1252-MKM-05Q-IDP-01-WESD-0403 | 1 OF 2 |  | 2018-09-25 | 2018-10-07 | 12 | C | MKM | [45 empty] | 2018-09-25 | 2018-10-07 | 12 | C | Rev-0 | B | Approved |  |  | 1 5 | MKM
628 | SD-0124-00 | ARK-0011-00 |  | T.V Unit/ Feature wall Details -Type1 (Ex.Suite Type-1,4,5 & 6) | 1252-MKM-05Q-IDP-01-WESD-0403 | 2 OF 2 |  | 2018-09-25 | 2018-10-07 | 12 | C | MKM | [45 empty] | 2018-09-25 | 2018-10-07 | 12 | C | Rev-0 | B | Approved |  |  | 1 5 | MKM
629 | SD-0147-00 | ARK-0036-00 |  | 47th to 49th Floors Executive Suite (Type 4 & 6) Floating T.V unit (Type-02) Details | 1252-MKM-05Q-IDP-01-WESD-0404 | 1 OF 2 |  | 2018-11-13 | 2018-12-08 | 25 | B | MKM | [45 empty] | 2018-11-13 | 2018-12-08 | 25 | B | Rev-0 | B | Approved |  |  | 1 5 | MKM
630 | SD-0147-00 | ARK-0036-00 |  | 47th to 49th Floors Executive Suite (Type 4 & 6) Floating T.V unit (Type-02) Details | 1252-MKM-05Q-IDP-01-WESD-0404 | 2 OF 2 |  | 2018-11-13 | 2018-12-08 | 25 | C | MKM | [45 empty] | 2018-11-13 | 2018-12-08 | 25 | C | Rev-0 | B | Approved |  |  | 1 5 | MKM
631 | SD-0147-00 | ARK-0036-00 |  | 45th, 46th, 48th, 49th & 50th Floors Executive Suites (Type 1, 3, 3A, 5 & 7) Master Bedroom T.V Unit (Type-03) (WES-324) Details | 1252-MKM-05Q-IDP-01-WESD-0405 | 1 OF 1 |  | 2018-11-13 | 2018-12-08 | 25 | B | MKM | [45 empty] | 2018-11-13 | 2018-12-08 | 25 | B | Rev-0 | B | Approved |  |  | 1 5 | MKM
632 |  |  | 45-46 | 45th & 46th Floors Executive Suite (Type 1 & 2) T.V Unit with Mini Bar (Type-04) Details | 1252-MKM-05Q-IDP-01-WESD-0406 | 1 OF 1 |  | Under review by GLI | [49 empty] | Under review by GLI |  |  | 0 | Rev-0 | B | Approved |  |  | 1 5 | 0
633 |  |  | 45-50 | 45th, 46th & 50th Floors Executive Suites (Type 3 & 3A) T.V Unit (WES-308) Type-05 Details | 1252-MKM-05Q-IDP-01-WESD-0407 | 1 OF 1 |  | Under review by GLI | [49 empty] | Under review by GLI |  |  | 0 | Rev-0 | B | Approved |  |  | 1 5 | 0
634 |  |  | 50 | T.V Display Unit Details in Living Room (Ex. Suite Type-7) @ 50th Floor | 1252-MKM-05Q-IDP-01-WESD-0408 | 1 OF 2 |  | Under review by GLI | [49 empty] | Under review by GLI |  |  | 0 | Rev-0 | B | Approved |  |  | 1 5 | 0
635 |  |  | 50 | T.V Display Unit Details in Living Room (Ex. Suite Type-7) @ 50th Floor | 1252-MKM-05Q-IDP-01-WESD-0408 | 2 OF 2 |  | Under review by GLI | [49 empty] | Under review by GLI |  |  | 0 | Rev-0 | B | Approved |  |  | 1 5 | 0
636 | SD-0151-00 | ARK-0046-00 | 45th-50th | 45th to 50th Floor Executive Suites Typical Desk Details (Type-1) | 1252-MKM-05Q-IDP-01-WESD-0409 | 1 OF 4 |  | 2018-12-05 | 2018-12-19 | 14 | B | MKM | [45 empty] | 2018-12-05 | 2018-12-19 | 14 | B | Rev-0 | B | Approved |  |  | 1 5 | MKM
637 | SD-0151-00 | ARK-0046-00 | 45th-50th | 45th to 50th Floor Executive Suites Typical Desk Details (Type-2) | 1252-MKM-05Q-IDP-01-WESD-0409 | 2 OF 4 |  | 2018-12-05 | 2018-12-19 | 14 | B | MKM | [45 empty] | 2018-12-05 | 2018-12-19 | 14 | B | Rev-0 | B | Approved |  |  | 1 5 | MKM
638 | SD-0151-00 | ARK-0046-00 | 45th-50th | 45th to 50th Floor Executive Suites Typical Desk Details (Type-3) | 1252-MKM-05Q-IDP-01-WESD-0409 | 3 OF 4 |  | 2018-12-05 | 2018-12-19 | 14 | B | MKM | [45 empty] | 2018-12-05 | 2018-12-19 | 14 | B | Rev-0 | B | Approved |  |  | 1 5 | MKM
639 | SD-0151-00 | ARK-0046-00 | 45th-50th | 45th to 50th Floor Executive Suites Typical Desk Details (Type-1,2 & 3) | 1252-MKM-05Q-IDP-01-WESD-0409 | 4 OF 4 |  | 2018-12-05 | 2018-12-19 | 14 | B | MKM | [45 empty] | 2018-12-05 | 2018-12-19 | 14 | B | Rev-0 | B | Approved |  |  | 1 5 | MKM
640 | SD-0151-00 | ARK-0046-00 | 45th,46th&50th | Executive Suites 3 & 3A Master Bed Dressing Unit (WES-328) Detail @ 45th, 46th & 50th Floor | 1252-MKM-05Q-IDP-01-WESD-0410 | 1 OF 1 |  | 2018-12-05 | 2018-12-19 | 14 | B | MKM | [45 empty] | 2018-12-05 | 2018-12-19 | 14 | B | Rev-0 | B | Approved |  |  | 1 5 | MKM
641 | SD-0147-00 | ARK-0036-00 | 45-46 | 45th & 46th Floor Executive Suite - Type1 Minibar Details - (Type1) | 1252-MKM-05Q-IDP-01-WESD-0411 | 1 OF 1 |  | 2018-11-13 | 2018-12-08 | 25 | B | MKM | [45 empty] | 2018-11-13 | 2018-12-08 | 25 | B | Rev-0 | B | Approved |  |  | 1 5 | MKM
642 | SD-0147-00 | ARK-0036-00 | 45-50 | 45th, 46th & 50th Floor Executive Suite - Type 3 & 3A Minibar Details - (Type 2) | 1252-MKM-05Q-IDP-01-WESD-0412 | 1 OF 1 |  | 2018-11-13 | 2018-12-08 | 25 | B | MKM | [45 empty] | 2018-11-13 | 2018-12-08 | 25 | B | Rev-0 | B | Approved |  |  | 1 5 | MKM
643 | SD-0147-00 | ARK-0036-00 | 50 | 50th Floor Executive Suite - Type 7 Minibar Details - (Type 2) | 1252-MKM-05Q-IDP-01-WESD-0412A | 1 OF 1 |  | 2018-11-13 | 2018-12-08 | 25 | B | MKM | [45 empty] | 2018-11-13 | 2018-12-08 | 25 | B | Rev-0 | B | Approved |  |  | 1 5 | MKM
644 | SD-0147-00 | ARK-0036-00 | 47-49 | 47th, 48th & 49th Floor Executive Suite - Type 4 & 6 Minibar Details - (Type 3) | 1252-MKM-05Q-IDP-01-WESD-0413 | 1 OF 1 |  | 2018-11-13 | 2018-12-08 | 25 | B | MKM | [45 empty] | 2018-11-13 | 2018-12-08 | 25 | B | Rev-0 | B | Approved |  |  | 1 5 | MKM
645 | SD-0147-00 | ARK-0036-00 | 47-49 | 47th, 48th & 49th Floor Executive Suite - Type 5 Minibar Details - (Type 3) | 1252-MKM-05Q-IDP-01-WESD-0413A | 1 OF 1 |  | 2018-11-13 | 2018-12-08 | 25 | B | MKM | [45 empty] | 2018-11-13 | 2018-12-08 | 25 | B | Rev-0 | B | Approved |  |  | 1 5 | MKM
646 | SD-0149-00 | ARK-0044-00 | 45-46 | 45th & 46th Floor Executive Suite Type-1 Bar Counter Details @ Living Room | 1252-MKM-05Q-IDP-01-WESD-0414 | 1 OF 1 |  | 2018-12-04 | 2018-12-10 | 6 | B | MKM | [45 empty] | 2018-12-04 | 2018-12-10 | 6 | B | Rev-0 | B | Approved |  |  | 1 5 | MKM
647 | SD-0122-00 | ARK-0007-00 |  | Niche Details | 1252-MKM-05Q-IDP-01-WESD-0415 | 1 OF 2 |  | 2018-09-23 | 2018-10-07 | 14 | C | MKM | [45 empty] | 2018-09-23 | 2018-10-07 | 14 | C | Rev-0 | B | Approved |  |  | 1 5 | MKM
648 | SD-0123-00 | ARK-0010-00 |  | Silver Mirror Details (WES 119) | 1252-MKM-05Q-IDP-01-WESD-0416 | 1 OF 1 |  | 2018-09-25 | 2018-10-07 | 12 | C | MKM | [45 empty] | 2018-09-25 | 2018-10-07 | 12 | C | Rev-0 | B | Approved |  |  | 1 5 | MKM
649 | SD-0125-00 | ARK-0012-00 |  | Bronze Mirror Details (WES 110) | 1252-MKM-05Q-IDP-01-WESD-0417 | 1 OF 1 |  | 2018-09-26 | 2018-10-07 | 11 | C | MKM | [45 empty] | 2018-09-26 | 2018-10-07 | 11 | C | Rev-0 | B | Approved |  |  | 1 5 | MKM
Executive Suite - Bathroom Details | [62 empty] | B | Approved |  |  | 1 211
650 | SD-0144-00 | ARK-0033-00 |  | Vanity Details - Plans | 1252-MKM-05Q-IDP-01-WESB-0408 | 1 OF 1 |  | 2018-10-17 | 2018-11-04 | 18 | C | MKM | [45 empty] | 2018-10-17 | 2018-11-04 | 18 | C | Rev-0 | B | Approved |  |  | 1 5 | MKM
651 | SD-0144-00 | ARK-0033-00 |  | Vanity Details - Plans | 1252-MKM-05Q-IDP-01-WESB-0408 | 1 OF 1 |  | 2018-10-17 | 2018-11-04 | 18 | C | MKM | [45 empty] | 2018-10-17 | 2018-11-04 | 18 | C | Rev-0 | B | Approved |  |  | 1 5 | MKM
652 | SD-0144-00 | ARK-0033-00 |  | Vanity Details - Elevations & Details | 1252-MKM-05Q-IDP-01-WESB-0409 | 1 OF 1 |  | 2018-10-17 | 2018-11-04 | 18 | C | MKM | [45 empty] | 2018-10-17 | 2018-11-04 | 18 | C | Rev-0 | B | Approved |  |  | 1 5 | MKM
Executive Suite - Doors | [62 empty] | B | Approved |  |  | 1 211
653 | SD-0142-00 | ARK-0031-00 |  | Executive Suite Entrance Door - (ID1) 60min. Fire Rated 45th to 50th Floor | 1252-MKM-05Q-IDP-01-WESDD-0400 | 1 OF 1 |  | 2018-10-17 | 2018-10-31 | 14 | B | MKM | [45 empty] | 2018-10-17 | 2018-10-31 | 14 | B | Rev-0 | B | Approved |  |  | 1 5 | MKM
654 | SD-0142-00 | ARK-0031-00 |  | Executive Suite Bedroom - Non Fire Rated Door - (ID2) 45th to 50th Floor | 1252-MKM-05Q-IDP-01-WESDD-0401 | 1 OF 1 |  | 2018-10-17 | 2018-10-31 | 14 | B | MKM | [45 empty] | 2018-10-17 | 2018-10-31 | 14 | B | Rev-0 | B | Approved |  |  | 1 5 | MKM
655 | SD-0145-00 | ARK-0034-00 |  | ID3-Bathroom door (Executive Suites) | 1252-MKM-05Q-IDP-01-WESDD-0402 | 1 OF 1 |  | 2018-10-25 | 2018-11-07 | 13 | B | MKM | [45 empty] | 2018-10-25 | 2018-11-07 | 13 | B | Rev-0 | B | Approved |  |  | 1 5 | MKM
656 | SD-0146-00 | ARK-0035-00 |  | (ID4) - WC/ Shower Cubicle door 45th to 50th Executive Suites | 1252-MKM-05Q-IDP-01-WESDD-0403 | 1 OF 1 |  | issued to site on 28-10-18 | [49 empty] | issued to site on 28-10-18 |  |  | 0 | Rev-0 | B | Approved |  |  | 1 5 | 0
657 | SD-0145-00 | ARK-0034-00 |  | ID5-Entrance door (Executive Suites)(3 &3A) | 1252-MKM-05Q-IDP-01-WESDD-0404 | 1 OF 1 |  | 2018-10-25 | 2018-11-07 | 13 | B | MKM | [45 empty] | 2018-10-25 | 2018-11-07 | 13 | B | Rev-0 | B | Approved |  |  | 1 5 | MKM
658 | SD-0145-00 | ARK-0034-00 |  | ID6-Master Bedroom door (Executive Suites)(3 &3A) | 1252-MKM-05Q-IDP-01-WESDD-0405 | 1 OF 1 |  | 2018-10-25 | 2018-11-07 | 13 | C | MKM | [45 empty] | 2018-10-25 | 2018-11-07 | 13 | C | Rev-0 | B | Approved |  |  | 1 5 | MKM
659 | SD-0146-00 | ARK-0035-00 |  | 60Min. Fire Rated Door - (ID7) 45th to 50th Floor Executive Suites Type 1 | 1252-MKM-05Q-IDP-01-WESDD-0406 | 1 OF 1 |  | issued to site on 28-10-18 | [49 empty] | issued to site on 28-10-18 |  |  | 0 | Rev-0 | B | Approved |  |  | 1 5 | 0
660 | SD-0146-00 | ARK-0035-00 |  | Door Architrave Details 45th to 50th Floor Executive Suites | 1252-MKM-05Q-IDP-01-WESDD-0407 | 1 OF 1 |  | issued to site on 28-10-18 | [49 empty] | issued to site on 28-10-18 |  |  | 0 | Rev-0 | B | Approved |  |  | 1 5 | 0
Executive Suite - Typical Details | [62 empty] | B | Approved |  |  | 1 211
661 | SD-0118-00 | ARK-0003-00 |  | Typical Wall Details | 1252-MKM-05Q-IDP-01-WESTD-WD-0400 | 1 OF 1 |  | 2018-09-23 | 2018-10-07 | 14 | B | MKM | [45 empty] | 2018-09-23 | 2018-10-07 | 14 | B | Rev-0 | B | Approved |  |  | 1 5 | MKM
662 | SD-0135-00 | ARK-0024-00 |  | Typical Ceiling Details | 1252-MKM-05Q-IDP-01-WESTD-CD-0400 | 1 OF 2 |  | 2018-10-11 | 2018-10-22 | 11 | B | MKM | [45 empty] | 2018-10-11 | 2018-10-22 | 11 | B | Rev-0 | B | Approved |  |  | 1 5 | MKM
663 | SD-0135-00 | ARK-0024-00 |  | Typical Ceiling Details | 1252-MKM-05Q-IDP-01-WESTD-CD-0400 | 2 OF 2 |  | 2018-10-11 | 2018-10-22 | 11 | B | MKM | [45 empty] | 2018-10-11 | 2018-10-22 | 11 | B | Rev-0 | B | Approved |  |  | 1 5 | MKM
Lift Car Details | [62 empty] | B | Approved |  |  | 1 211
664 | SD-0126-00 | ARK-0013-00 |  | Ground Floor- 50th Floor Lift Car Details | 1252-MKM-05Q-IDP-01-WLCD-0400 | 1 OF 2 |  | 2018-09-26 | 2018-10-07 | 11 | C | MKM | 2018-12-24 | 2019-01-03 | 10 | C | MKM | 2019-01-23 |  | 215 | OD | MKM | [35 empty] | 2019-01-23 |  | 215 | OD | Rev-2 | B | Approved |  |  | 1 5 | MKM
665 | SD-0126-00 | ARK-0013-00 |  | Ground Floor- 50th Floor Lift Car Details | 1252-MKM-05Q-IDP-01-WLCD-0400 | 2OF 2 |  | 2018-09-26 | 2018-10-07 | 11 | C | MKM | 2018-12-24 | 2019-01-03 | 10 | C | MKM | 2019-01-23 |  | 215 | OD | MKM | [35 empty] | 2019-01-23 |  | 215 | OD | Rev-2 | B | Approved |  |  | 1 5 | MKM
|  |  |  | Wafi hotel Complex and Mall expansion - Plot No.:3153804 Um Hurair, Dubai. Package 8 SUMMARY OF THE LOG FOR SHOP DRAWINGS |  | NOS: | %
|  |  |  | TOTAL NO. OF SHOP DRAWINGS : |  | #REF! | #REF!
|  |  |  | TOTAL NO. OF SHOP DRAWING SUBMITTED: |  | #REF! | #REF! | [5 empty] | 2016-12-20 |  | 979 | OD | MKM
|  |  |  | BALANCE NO. OF SHOP DRAWING TO BE SUBMITTED: |  | #REF! | #REF!
|  |  |  | APPROVED (A) |  | #REF! | #REF!
|  |  |  | APPROVED AS NOTED (B) |  | #REF! | #REF!
|  |  |  | INTERNAL REVIEW RETURN FOR CORRECTION (IR) |  | #REF! | #REF!
|  |  |  | REVISE & RESUBMIT (C): |  | #REF! | #REF!
|  |  |  | REJECTED (D) |  | #REF! | #REF!
|  |  |  | SUBMITTED FOR REVIEW (P) |  | #REF! | #REF!
|  |  |  | OVERDUE (OD) |  | #REF! | #REF!
|  |  |  | CANCELLED / NOT IN GLI SCOPE (X) |  | 0
|  |  |  | FOR INFORMATION (FI) |  | #REF! | ---
|  |  |  | NO LONGER IN USE/NOT IN SCOPE (X) |  | #REF! | ---
|  |  |  | ISSUED TO SITE, AWAITED ACKNOWLEDGEMENT |  | #REF! | #REF!
Formulas:
Time Taken to Reply = IF([A - Approved]="","",IF([Date Commented]="",TODAY()-[A - Approved],[Date Commented]-[A - Approved]))
Time Taken to Reply = IF([P - Issued for Approval]="","",IF([Date Commented]="",TODAY()-[P - Issued for Approval],[Date Commented]-[P - Issued for Approval]))
Date Submitted = IF([Date Submitted]<>"",[Date Submitted],IF([Date Submitted]<>"",[Date Submitted],IF([Date Submitted]<>"",[Date Submitted],IF([Date Submitted]<>"",[Date Submitted],IF([Date Submitted]<>"",[Date Submitted],IF([Date Submitted]<>"",[Date Submitted],IF([SS - Superseded by New Revision]<>"",[SS - Superseded by New Revision],IF([P - Issued for Approval]<>"",[P - Issued for Approval],IF([A - Approved]<>"",[A - Approved],"")))))))))
Date Submitted = IF([Date Submitted]<>"",[Date Submitted],IF([Date Submitted]<>"",[Date Submitted],IF([Date Submitted]<>"",[Date Submitted],IF([Date Submitted]<>"",[Date Submitted],IF([Date Submitted]<>"",[Date Submitted],IF([Date Submitted]<>"",[Date Submitted],IF([SS - Superseded by New Revision]<>"",[SS - Superseded by New Revision],IF([A - Approved]<>"",[A - Approved],IF(#REF!<>"",#REF!,"")))))))))
Date Commented = IF([Status]="P","",IF([Status]="OD","",IF([Date Commented]<>"",[Date Commented],IF([Date Commented]<>"",[Date Commented],IF([Date Commented]<>"",[Date Commented],IF([Date Commented]<>"",[Date Commented],IF([Date Commented]<>"",[Date Commented],IF([Date Commented]<>"",[Date Commented],IF([Date Commented]<>"",[Date Commented],IF([Date Commented]<>"",[Date Commented],IF([Date Commented]<>"",[Date Commented],"")))))))))))
Status = IF(((TODAY())-[A - Approved])>14,"OD","P")
Status = IF(((TODAY())-[SS - Superseded by New Revision])>14,"OD","P")
Note on R246: Superseded due to the Design Changes
Note on R247: Superseded due to the Design Changes
Note on M248: Superseded due to the Design Changes